## WP INFO
CUT OFF DATE | 2017-03-25 | 7.7589 | 43.2658
BASELINE START DATE | 2016-08-01 | 1552 | 4.2521 | 51.0247
BASELINE FINISH DATE | 2020-10-31
PROJECT DURATION | 51.0247
REMAINING DURATION | 43.2658
SECTION NAME | SECTION START DATE | SECTION COMPLETION DATE | DURATION | REMAINING DURATION
WP | 2016-08-01 | 2020-10-31 | 51.0247 | 43.2658
SECTION 1 | 2016-08-01 | 2020-01-31 | 42.0164 | 34.2575
SECTION 2 | 2016-11-01 | 2020-10-31 | 48 | 43.2658

## DELIVERABLES
ACTIVITY | BL START | BL FINISH | PLANNED START | ACTUAL FINISH | STATUS |  | PLANNED DURATION | ELAPSED DURATION | REMAINING DURATION |  |  |  | ACTIVITY HEALTH CHECK | PHYSICAL PROGRESS
[5 empty] | BASELINE | ACTUAL | [7 empty] | PLANNED | ACTUAL | VARIANCE | MIN | BASE | MAX | MEAN | SD
WORK PACKAGE: _______________ | 2016-08-01 | 2020-10-31 | 2016-08-01 |  | Started | In Progress | 51.0247 | 7.7589 | 43.2658 | 1.96% | -3.92% | 1.1 | Behind Schedule | 2.63% | 2.53% | -0.1% | 38.9392 | 43.2658 | 48.0429 | 43.3408 | 1.5173
SECTION 1 | 2016-08-01 | 2020-01-31 | 2016-08-01 |  | Started | In Progress | 42.0164 | 7.7589 | 34.2575 | 2.38% | -4.76% | 1.1 | Behind Schedule | 3.55% | 3.17% | -0.38% | 30.8318 | 34.2575 | 38.136 | 34.333 | 1.2174
Demolition & Site Clearance-Section 1-- | 2016-10-13 | 2019-08-19 | 2016-10-13 |  | Started | In Progress | 34.1918 | 5.3589 | 28.8329 | 2.925% | -5.849% | 1.1 | Behind Schedule | 25.18% | 24.93% | -0.25% | 25.9496 | 28.8329 | 32.0597 | 28.8901 | 1.0183
Demolition & Site Clearance-Section 1-Zone B- | 2017-03-15 | 2018-11-19 | 2017-04-06 |  | Started | Not Started | 20.1863 | 0.32877 | 19.8575 | 4.954% | -9.908% | 1.15 | Not Started | 7.09% | 0% | -7.09% | 17.8718 | 19.8575 | 24.431 | 20.2888 | 1.0932
Demolition & Site Clearance-Section 1-Zone C1- | 2016-10-20 | 2018-05-24 | 2016-10-20 |  | Started | In Progress | 19.1014 | 5.1288 | 13.9726 | 5.235% | -10.47% | 1.1 | Delayed | 68.75% | 53.52% | -15.23% | 12.5753 | 13.9726 | 17.6294 | 14.3492 | 0.84235
Demolition & Site Clearance-Section 1-Zone C2- | 2016-10-13 | 2018-09-20 | 2016-10-13 |  | Started | In Progress | 23.2438 | 5.3589 | 17.8849 | 4.302% | -8.604% | 1.1 | On Schedule | 81.82% | 81.82% | 0% | 16.0964 | 17.8849 | 19.8418 | 17.913 | 0.62422
Demolition & Site Clearance-Section 1-Zone D- | 2017-04-12 | 2018-12-19 | 2017-02-01 |  | Not Started | In Progress | 20.2521 | -0.59178 | 20.2521 | 4.938% | -9.876% | 1.0 | Ahead | 0% | 12.19% | 12.19% | 6 | 20.2521 | 17.974 | 17.497 | 1.9957
Earthwork-Section 1-- | 2016-12-23 | 2019-11-11 | 2016-12-23 |  | Started | In Progress | 34.6192 | 3.0247 | 31.5945 | 2.889% | -5.777% | 1.1 | Behind Schedule | 6.79% | 5.46% | -1.33% | 28.4351 | 31.5945 | 35.4716 | 31.7141 | 1.1728
Earthwork-Section 1-Stripping- | 2016-12-23 | 2019-09-03 | 2016-12-23 |  | Started | In Progress | 32.3507 | 3.0247 | 29.326 | 3.091% | -6.182% | 1.1 | Behind Schedule | 20.79% | 18.11% | -2.68% | 26.3934 | 29.326 | 33.3206 | 29.503 | 1.1545
Earthwork-Section 1-Stripping-Zone C1 | 2016-12-31 | 2018-09-05 | 2016-12-31 |  | Started | In Progress | 20.1534 | 2.7616 | 17.3918 | 4.962% | -9.924% | 1.1 | Delayed | 61.15% | 45.89% | -15.26% | 15.6526 | 17.3918 | 21.9487 | 17.8614 | 1.0493
Earthwork-Section 1-Stripping-Zone C2 | 2016-12-23 | 2018-11-12 | 2016-12-23 |  | Started | In Progress | 22.6521 | 3.0247 | 19.6274 | 4.415% | -8.829% | 1.1 | Delayed | 70.02% | 58.12% | -11.9% | 17.6647 | 19.6274 | 24.1106 | 20.0475 | 1.0743
Earthwork-Section 1-Cut- | 2017-01-16 | 2019-09-24 | 2017-01-16 |  | Started | In Progress | 32.2521 | 2.2356 | 30.0164 | 3.101% | -6.201% | 1.1 | Behind Schedule | 7.39% | 6.11% | -1.28% | 27.0148 | 30.0164 | 33.6849 | 30.1276 | 1.1117
Earthwork-Section 1-Cut-Zone C1 | 2017-02-01 | 2018-08-07 | 2017-02-01 |  | Started | In Progress | 18.1479 | 1.7096 | 16.4384 | 5.51% | -11.02% | 1.1 | Behind Schedule | 14.32% | 9.61% | -4.71% | 14.7945 | 16.4384 | 19.0112 | 16.5932 | 0.70278
Earthwork-Section 1-Cut-Zone C2 | 2017-01-16 | 2018-11-10 | 2017-01-16 |  | Started | In Progress | 21.7973 | 2.2356 | 19.5616 | 4.588% | -9.175% | 1.1 | Behind Schedule | 10.87% | 9.84% | -1.03% | 17.6055 | 19.5616 | 21.9034 | 19.6259 | 0.71633
Earthwork-Section 1-Fill- | 2017-01-24 | 2019-09-21 | 2017-01-24 |  | Started | In Progress | 31.8904 | 1.9726 | 29.9178 | 3.136% | -6.271% | 1.1 | Behind Schedule | 6.17% | 3.32% | -2.85% | 26.926 | 29.9178 | 34.0439 | 30.1069 | 1.1863
Earthwork-Section 1-Fill-Zone C1 | 2017-03-01 | 2018-09-05 | 2017-03-01 |  | Started | In Progress | 18.1808 | 0.78904 | 17.3918 | 5.5% | -11% | 1.1 | Behind Schedule | 11.41% | 6.2% | -5.21% | 15.6526 | 17.3918 | 20.2008 | 17.5701 | 0.75803
Earthwork-Section 1-Fill-Zone C2 | 2017-01-24 | 2018-10-30 | 2017-01-24 |  | Started | In Progress | 21.1726 | 1.9726 | 19.2 | 4.723% | -9.446% | 1.1 | Behind Schedule | 16.28% | 8.69% | -7.59% | 17.28 | 19.2 | 22.758 | 19.473 | 0.913
Geotechnical Works-Section 1-- | 2017-03-29 | 2019-10-26 | 2017-02-27 |  | Not Started | In Progress | 30.937 | -0.13151 | 30.937 | 3.232% | -6.465% | 1.0 | Ahead | 0% | 0.56% | 0.56% | 27.8433 | 30.937 | 31.055 | 30.441 | 0.53528
Geotechnical Works-Section 1-Ground Treatment- | 2017-04-07 | 2019-09-26 | 2017-02-27 |  | Not Started | In Progress | 29.6548 | -0.4274 | 29.6548 | 3.372% | -6.744% | 1.0 | Ahead | 0% | 0.68% | 0.68% | 26.6893 | 29.6548 | 29.7323 | 29.1735 | 0.50716
Geotechnical Works-Section 1-Ground Treatment-Excavate & Replace | 2017-04-07 | 2019-09-13 | 2017-02-27 |  | Not Started | In Progress | 29.2274 | -0.4274 | 29.2274 | 3.421% | -6.843% | 1.0 | Ahead | 0% | 0.8% | 0.8% | 26.3047 | 29.2274 | 29.2687 | 28.7472 | 0.49401
Ground Treatment-Section 1-Excavate & Replace-Zone C1 | 2017-04-07 | 2018-12-10 | 2017-02-27 |  | Not Started | In Progress | 20.1205 | -0.4274 | 20.1205 | 4.97% | -9.94% | 1.0 | Ahead | 0% | 1.42% | 1.42% | 18.1085 | 20.1205 | 20.0242 | 19.7692 | 0.31929
Ground Treatment-Section 1-Excavate & Replace-Zone C2 | 2017-04-12 | 2018-12-10 | 2017-03-01 |  | Not Started | In Progress | 19.9562 | -0.59178 | 19.9562 | 5.011% | -10.02% | 1.0 | Ahead | 0% | 2.78% | 2.78% | 17.9605 | 19.9562 | 19.5892 | 19.5624 | 0.27145
Geotechnical Works-Section 1-Site Investigation- | 2017-03-29 | 2019-08-14 | 2017-03-13 |  | Not Started | In Progress | 28.537 | -0.13151 | 28.537 | 3.504% | -7.008% | 1.0 | Ahead | 0% | 0.23% | 0.23% | 25.6833 | 28.537 | 28.74 | 28.0952 | 0.50945
Geotechnical Works-Section 1-Site Investigation-Zone C2 | 2017-03-29 | 2018-08-10 | 2017-03-13 |  | Not Started | In Progress | 16.4055 | -0.13151 | 16.4055 | 6.096% | -12.19% | 1.0 | Ahead | 0% | 1.56% | 1.56% | 14.7649 | 16.4055 | 16.304 | 16.1151 | 0.25651
Drainage Works-Section 1-- | 2017-02-17 | 2020-01-10 | 2017-02-17 |  | Started | In Progress | 34.7507 | 1.1836 | 33.5671 | 2.878% | -5.755% | 1.1 | Behind Schedule | 1.69% | 0.3% | -1.39% | 30.2104 | 33.5671 | 37.7064 | 33.6976 | 1.2493
Drainage Works-Section 1-Surface Drain- | 2017-02-17 | 2019-11-27 | 2017-02-17 |  | Started | In Progress | 33.3041 | 1.1836 | 32.1205 | 3.003% | -6.005% | 1.1 | Behind Schedule | 2.1% | 0.28% | -1.82% | 28.9085 | 32.1205 | 36.2196 | 32.2684 | 1.2185
Drainage Works-Section 1-Surface Drain-Zone C1 | 2017-03-03 | 2019-03-11 | 2017-03-27 |  | Started | Not Started | 24.263 | 0.72329 | 23.5397 | 4.121% | -8.243% | 1.15 | Not Started | 4.41% | 0% | -4.41% | 21.1858 | 23.5397 | 28.3304 | 23.9458 | 1.1908
Drainage Works-Section 1-Surface Drain-Zone C2 | 2017-02-17 | 2019-03-13 | 2017-02-17 |  | Started | In Progress | 24.789 | 1.1836 | 23.6055 | 4.034% | -8.068% | 1.1 | Behind Schedule | 7.51% | 1.61% | -5.9% | 21.2449 | 23.6055 | 27.581 | 23.8746 | 1.056
Drainage Works-Section 1-Pipe & Box Culvert- | 2017-03-09 | 2020-01-10 | 2017-03-01 |  | Started | In Progress | 34.0932 | 0.52603 | 33.5671 | 2.933% | -5.866% | 1.0 | Behind Schedule | 1.25% | 0.35% | -0.9% | 30.2104 | 33.5671 | 34.1852 | 33.1107 | 0.66247
Drainage Works-Section 1-Pipe & Box Culvert-Zone C1 | 2017-04-05 | 2018-12-31 | 2017-03-01 |  | Not Started | In Progress | 20.8767 | -0.36164 | 20.8767 | 4.79% | -9.58% | 1.0 | Ahead | 0% | 0.64% | 0.64% | 18.789 | 20.8767 | 20.9396 | 20.5393 | 0.35843
Drainage Works-Section 1-Pipe & Box Culvert-Zone C2 | 2017-03-09 | 2019-01-11 | 2017-03-09 |  | Started | In Progress | 22.126 | 0.52603 | 21.6 | 4.52% | -9.039% | 1.1 | Behind Schedule | 6.31% | 1.1% | -5.21% | 19.44 | 21.6 | 25.0887 | 21.8214 | 0.94145
Relocation of Existing Utilities and Services-Section 1-- | 2016-10-13 | 2019-11-19 | 2016-10-13 |  | Started | In Progress | 37.2164 | 5.3589 | 31.8575 | 2.687% | -5.374% | 1.1 | Behind Schedule | 3.15% | 1.48% | -1.67% | 28.6718 | 31.8575 | 35.8752 | 31.9962 | 1.2006
Relocation of Existing Utilities and Services-Section 1-Utilities Relocation- | 2016-10-14 | 2019-09-06 | 2016-10-14 |  | Started | In Progress | 34.7507 | 5.326 | 29.4247 | 2.878% | -5.755% | 1.1 | On Schedule | 15.73% | 15.73% | 0% | 26.4822 | 29.4247 | 32.6441 | 29.4708 | 1.027
Relocation of Existing Utilities and Services-Section 1-Stage 1- | 2016-10-13 | 2019-10-31 | 2016-10-13 |  | Started | In Progress | 36.5918 | 5.3589 | 31.2329 | 2.733% | -5.466% | 1.1 | On Schedule | 18.98% | 18.98% | 0% | 28.1096 | 31.2329 | 34.6502 | 31.2819 | 1.0901
Relocation of Existing Utilities and Services-Section 1-Stage 2- | 2017-02-22 | 2019-03-26 | 2017-02-22 |  | Started | In Progress | 25.0521 | 1.0192 | 24.0329 | 3.992% | -7.983% | 1.1 | Behind Schedule | 9.32% | 1.97% | -7.35% | 6 | 24.0329 | 28.4288 | 21.7601 | 3.7381
SECTION 2 | 2016-11-01 | 2020-10-31 | 2016-11-01 |  | Started | In Progress | 48 | 4.7342 | 43.2658 | 2.083% | -4.167% | 1.1 | Ahead | 1.64% | 1.85% | 0.21% | 38.9392 | 43.2658 | 47.9088 | 43.3185 | 1.4949
Demolition & Site Clearance-Section 2-- | 2017-02-08 | 2019-07-26 | 2017-02-08 |  | Started | In Progress | 29.5233 | 1.4795 | 28.0438 | 3.387% | -6.774% | 1.1 | Ahead | 5.31% | 7.74% | 2.43% | 25.2395 | 28.0438 | 30.4307 | 27.9743 | 0.86522
Demolition & Site Clearance-Section 2-Zone C1- | 2017-03-29 | 2018-11-27 | 2017-02-08 |  | Not Started | In Progress | 19.989 | -0.13151 | 19.989 | 5.003% | -10.01% | 1.0 | Ahead | 0% | 22.02% | 22.02% | 17.9901 | 19.989 | 15.7756 | 18.9537 | -0.36909
Demolition & Site Clearance-Section 2-Zone C2- | 2017-02-08 | 2018-10-18 | 2017-02-08 |  | Started | In Progress | 20.2849 | 1.4795 | 18.8055 | 4.93% | -9.86% | 1.1 | Behind Schedule | 36.78% | 27.83% | -8.95% | 16.9249 | 18.8055 | 22.5461 | 19.1155 | 0.93687
Relocation of Existing Utilities and Services-Section 2-- | 2017-01-04 | 2020-07-30 | 2017-01-04 |  | Started | In Progress | 42.8384 | 2.6301 | 40.2082 | 2.334% | -4.669% | 1.1 | Ahead | 0.6% | 0.95% | 0.35% | 36.1874 | 40.2082 | 44.4668 | 40.2478 | 1.3799
Relocation of Existing Utilities and Services-Section 2-Utilities Relocation- | 2017-01-04 | 2020-07-28 | 2017-01-04 |  | Started | In Progress | 42.7726 | 2.6301 | 40.1425 | 2.338% | -4.676% | 1.1 | On Schedule | 6.42% | 6.42% | 0% | 36.1282 | 40.1425 | 44.5346 | 40.2054 | 1.4011
Relocation of Existing Utilities and Services-Section 2-Stage 1- | 2017-01-04 | 2020-07-30 | 2017-01-04 |  | Started | In Progress | 42.8384 | 2.6301 | 40.2082 | 2.334% | -4.669% | 1.1 | Ahead | 9.44% | 10.78% | 1.34% | 36.1874 | 40.2082 | 44.0688 | 40.1815 | 1.3136
Relocation of Existing Utilities and Services-Section 2-Stage 2- | 2017-03-17 | 2019-03-20 | 2017-02-25 |  | Started | In Progress | 24.0986 | 0.26301 | 23.8356 | 4.15% | -8.299% | 1.0 | Ahead | 0.65% | 2.02% | 1.37% | 6 | 23.8356 | 23.7334 | 20.846 | 2.9556

## N SAMPLE
N | WP | SECTION 1 | SECTION 2
1 | 44.3107 | 35.3835 | 42.8209
2 | 44.6884 | 36.5926 | 43.3264
3 | 42.1141 | 36.1829 | 42.3496
4 | 43.277 | 35.5292 | 42.4175
5 | 43.4639 | 35.8798 | 43.8154
6 | 45.7466 | 33.1508 | 43.6303
7 | 46.2134 | 34.8417 | 43.1188
8 | 42.3597 | 35.791 | 42.6786
9 | 42.8215 | 33.4944 | 42.6019
10 | 44.993 | 32.8966 | 39.8337
11 | 44.5699 | 32.0332 | 42.3329
12 | 42.1688 | 33.4191 | 40.3055
13 | 43.2414 | 34.7755 | 44.8149
14 | 43.7025 | 35.1265 | 45.3173
15 | 45.1275 | 32.7184 | 45.4231
16 | 44.8883 | 33.1418 | 42.0454
17 | 43.7089 | 33.2011 | 43.6197
18 | 43.4664 | 33.9905 | 44.4624
19 | 43.8394 | 34.3737 | 44.7013
20 | 44.7229 | 33.4258 | 45.2898
21 | 46.9571 | 33.6706 | 42.3209
22 | 43.4593 | 32.4016 | 45.0552
23 | 44.5945 | 34.5919 | 43.4975
24 | 43.4802 | 34.0335 | 44.3104
25 | 40.0169 | 34.8332 | 44.7947
26 | 44.3599 | 33.2602 | 42.0803
27 | 42.5665 | 33.2067 | 40.8529
28 | 44.0812 | 31.8226 | 42.1023
29 | 42.4858 | 35.5889 | 45.5065
30 | 41.7799 | 32.5583 | 39.8555
31 | 46.5074 | 32.8361 | 45.1379
32 | 44.8117 | 35.06 | 42.0315
33 | 42.7768 | 35.1975 | 44.0921
34 | 42.1397 | 34.8184 | 44.4332
35 | 43.2045 | 32.6223 | 44.118
36 | 45.1979 | 31.3427 | 43.2282
37 | 44.8142 | 33.2349 | 41.6365
38 | 43.4945 | 32.7197 | 42.3825
39 | 43.4706 | 36.0261 | 43.3899
40 | 43.6049 | 34.6203 | 43.8303
41 | 40.5375 | 34.717 | 44.3763
42 | 45.3377 | 36.8444 | 39.6381
43 | 42.5844 | 36.0627 | 45.3744
44 | 43.5953 | 35.0127 | 42.7323
45 | 43.3064 | 33.4788 | 44.6437
46 | 41.7044 | 31.8255 | 40.1704
47 | 40.5752 | 34.1534 | 44.1653
48 | 44.1238 | 33.9128 | 40.9772
49 | 45.2781 | 35.4378 | 43.583
50 | 43.1382 | 32.7481 | 44.4834
51 | 44.1093 | 33.499 | 43.7396
52 | 44.4107 | 32.1776 | 41.9855
53 | 43.2228 | 35.9219 | 45.5326
54 | 44.8943 | 33.4883 | 43.4071
55 | 42.2298 | 33.0824 | 43.1982
56 | 45.0845 | 34.2716 | 44.0595
57 | 42.076 | 32.3838 | 44.6371
58 | 43.4224 | 35.4867 | 43.5391
59 | 40.7579 | 36.1496 | 43.8231
60 | 40.473 | 33.4466 | 41.7683
61 | 44.4063 | 34.8183 | 43.0915
62 | 42.2043 | 34.3068 | 43.0276
63 | 41.4333 | 35.6906 | 42.6397
64 | 43.8678 | 36.0527 | 42.5509
65 | 39.67 | 36.5871 | 43.5468
66 | 43.7594 | 32.9332 | 43.4648
67 | 45.161 | 32.2429 | 44.5867
68 | 44.9494 | 34.008 | 41.9297
69 | 44.5125 | 35.0801 | 39.7663
70 | 41.9631 | 33.8339 | 43.5205
71 | 45.0251 | 31.7587 | 42.4631
72 | 45.7633 | 33.8645 | 40.7556
73 | 44.268 | 32.8891 | 44.0162
74 | 42.5904 | 32.7551 | 44.4089
75 | 41.291 | 34.4676 | 43.5204
76 | 43.0733 | 32.6367 | 45.53
77 | 42.3822 | 32.8257 | 43.8719
78 | 42.2289 | 33.7416 | 44.0039
79 | 42.0106 | 33.2092 | 42.7685
80 | 43.5603 | 33.9339 | 42.9422
81 | 42.6498 | 33.8794 | 45.4537
82 | 42.6001 | 34.275 | 42.8841
83 | 43.6768 | 35.1513 | 42.0655
84 | 44.4144 | 35.5914 | 44.3575
85 | 43.7552 | 32.0569 | 44.163
86 | 44.5067 | 37.0751 | 46.4723
87 | 44.0661 | 33.2355 | 42.6823
88 | 43.8496 | 34.5048 | 43.6878
89 | 40.9774 | 34.0849 | 43.7802
90 | 42.1422 | 36.9516 | 44.5124
91 | 44.0905 | 34.9988 | 43.0085
92 | 44.7011 | 35.8015 | 41.7998
93 | 40.568 | 34.1636 | 46.2069
94 | 44.108 | 35.8822 | 41.3256
95 | 44.2286 | 36.6573 | 44.0844
96 | 46.2941 | 30.0963 | 43.5047
97 | 40.9592 | 34.3908 | 43.0856
98 | 39.4189 | 34.764 | 41.5828
99 | 43.9082 | 34.8788 | 42.5429
100 | 42.2888 | 33.8826 | 44.452
101 | 46.0001 | 34.9912 | 42.4659
102 | 43.8267 | 33.0469 | 42.8499
103 | 42.2409 | 31.156 | 42.3034
104 | 44.647 | 34.0605 | 43.1095
105 | 44.5306 | 33.7558 | 44.4094
106 | 44.2406 | 36.316 | 42.212
107 | 45.1939 | 31.166 | 42.3365
108 | 42.1857 | 35.2195 | 41.9394
109 | 42.2252 | 32.8327 | 41.1943
110 | 44.9053 | 33.3319 | 43.2513
111 | 41.8603 | 33.5836 | 43.163
112 | 42.0554 | 35.0677 | 43.1676
113 | 44.0067 | 32.3427 | 46.1327
114 | 44.2003 | 35.6391 | 45.3788
115 | 43.8352 | 33.9983 | 42.5062
116 | 41.5826 | 34.4755 | 42.3775
117 | 43.9462 | 35.6125 | 42.8146
118 | 42.4984 | 35.6608 | 43.6127
119 | 44.7317 | 33.7934 | 42.8446
120 | 44.4053 | 34.1387 | 44.0844
121 | 44.8822 | 30.6717 | 42.0612
122 | 40.4468 | 35.4196 | 44.413
123 | 43.2639 | 34.5622 | 44.8399
124 | 43.4342 | 36.2359 | 42.394
125 | 41.023 | 34.7979 | 42.6807
126 | 43.0402 | 34.8391 | 41.3201
127 | 45.8835 | 33.0841 | 48.637
128 | 42.3329 | 33.9173 | 45.8601
129 | 46.2924 | 33.4858 | 47.9502
130 | 42.806 | 33.9945 | 43.7406
131 | 43.9757 | 35.5217 | 42.2955
132 | 44.4794 | 35.2604 | 46.2728
133 | 43.3975 | 34.4278 | 41.5407
134 | 44.0553 | 34.2831 | 42.3683
135 | 43.535 | 34.8372 | 44.9798
136 | 41.3422 | 34.5646 | 44.4148
137 | 42.6308 | 34.2337 | 38.9359
138 | 43.2897 | 35.6693 | 40.6095
139 | 42.0675 | 33.6664 | 43.3859
140 | 42.6237 | 33.0605 | 41.7164
141 | 43.5326 | 34.3002 | 43.8425
142 | 43.0616 | 32.2264 | 43.6869
143 | 45.1208 | 35.3212 | 40.97
144 | 43.2485 | 34.4713 | 42.6991
145 | 42.534 | 33.6367 | 44.0455
146 | 44.6483 | 32.885 | 41.5277
147 | 41.3452 | 34.7382 | 42.6903
148 | 42.9292 | 34.3453 | 44.6902
149 | 43.8131 | 36.0553 | 39.8756
150 | 44.6639 | 33.1781 | 40.6434
151 | 42.3774 | 33.9103 | 44.097
152 | 42.0976 | 35.2967 | 42.1449
153 | 44.5909 | 32.0814 | 43.782
154 | 42.6599 | 32.827 | 41.4179
155 | 43.4322 | 35.9501 | 45.0976
156 | 44.706 | 35.3303 | 44.6091
157 | 43.2433 | 34.9018 | 45.3216
158 | 42.4758 | 31.2299 | 41.342
159 | 43.6759 | 34.1392 | 42.9862
160 | 43.8656 | 34.8867 | 42.4642
161 | 46.5737 | 34.6549 | 45.8715
162 | 41.5954 | 33.9841 | 41.9048
163 | 42.0916 | 34.0173 | 43.6965
164 | 44.9862 | 34.4171 | 44.0009
165 | 44.9877 | 35.6102 | 42.7744
166 | 42.3097 | 33.7289 | 46.9071
167 | 42.3326 | 34.128 | 44.2306
168 | 41.026 | 33.5507 | 43.0631
169 | 44.8624 | 35.3555 | 44.6092
170 | 42.1485 | 36.4622 | 39.7811
171 | 41.7367 | 33.5501 | 42.3787
172 | 42.1414 | 33.1775 | 45.5435
173 | 45.065 | 32.7939 | 42.8798
174 | 45.4541 | 33.7098 | 44.1475
175 | 44.1706 | 34.1 | 46.3224
176 | 43.9252 | 35.1818 | 41.7718
177 | 45.0901 | 33.839 | 43.222
178 | 43.1717 | 34.0457 | 42.3781
179 | 43.6168 | 35.8285 | 43.3951
180 | 40.8099 | 33.35 | 45.5304
181 | 42.3655 | 33.0333 | 43.8139
182 | 43.846 | 36.3627 | 44.3296
183 | 44.693 | 34.963 | 43.6769
184 | 42.6723 | 33.9961 | 43.606
185 | 41.326 | 34.423 | 43.4714
186 | 43.7014 | 34.5506 | 42.2976
187 | 43.0342 | 34.8296 | 41.9024
188 | 42.9323 | 34.1364 | 43.0913
189 | 44.3222 | 33.7181 | 42.2653
190 | 44.6666 | 33.5096 | 42.2119
191 | 45.6202 | 34.0978 | 41.9633
192 | 44.1341 | 34.6755 | 44.5731
193 | 44.8319 | 33.9972 | 45.0327
194 | 44.5022 | 34.1436 | 40.9004
195 | 44.2824 | 34.1052 | 41.1603
196 | 43.6963 | 35.3884 | 43.6546
197 | 41.8291 | 34.4747 | 40.9978
198 | 43.9067 | 36.0358 | 44.0815
199 | 45.4893 | 35.5874 | 44.2822
200 | 41.2682 | 35.8833 | 41.493
201 | 41.373 | 34.6145 | 44.0151
202 | 42.9771 | 34.4086 | 43.643
203 | 40.9356 | 33.1774 | 44.6317
204 | 43.2371 | 35.399 | 42.4765
205 | 45.07 | 34.0266 | 41.7576
206 | 41.6575 | 34.857 | 41.1026
207 | 43.2578 | 33.5785 | 45.5207
208 | 44.5196 | 33.7027 | 41.9142
209 | 43.4517 | 34.3072 | 42.932
210 | 42.5372 | 34.0302 | 43.712
211 | 41.0802 | 34.9494 | 43.1612
212 | 44.9714 | 34.5766 | 41.9534
213 | 43.2031 | 36.2435 | 41.3033
214 | 42.3037 | 37.2802 | 42.8371
215 | 43.226 | 35.6269 | 41.7579
216 | 44.8092 | 32.3185 | 44.5409
217 | 43.0757 | 34.2847 | 42.3737
218 | 43.5278 | 35.969 | 40.9774
219 | 43.5624 | 33.9213 | 43.5557
220 | 45.3643 | 33.168 | 44.0131
221 | 44.2773 | 35.6579 | 42.5911
222 | 44.3973 | 35.9778 | 44.9736
223 | 43.4041 | 32.3361 | 42.6843
224 | 44.0144 | 35.8378 | 41.6363
225 | 44.9848 | 34.0841 | 42.8459
226 | 42.0408 | 35.847 | 42.594
227 | 41.6985 | 34.0351 | 43.3587
228 | 43.5871 | 34.3692 | 40.3163
229 | 44.4127 | 31.5667 | 40.1687
230 | 44.2601 | 36.0078 | 43.6912
231 | 44.0725 | 34.2352 | 43.9645
232 | 42.9319 | 33.711 | 40.9812
233 | 44.7846 | 34.7247 | 45.8579
234 | 44.075 | 34.3682 | 44.5262
235 | 44.1716 | 36.4488 | 41.1607
236 | 43.741 | 34.241 | 41.5081
237 | 42.8635 | 35.3783 | 42.7765
238 | 43.2319 | 35.667 | 43.0996
239 | 43.3816 | 36.2047 | 43.4859
240 | 46.9454 | 34.4398 | 42.5737
241 | 42.8443 | 34.608 | 45.0135
242 | 44.6734 | 33.9979 | 43.1323
243 | 41.3225 | 34.2175 | 44.1124
244 | 42.2857 | 34.4843 | 43.4997
245 | 41.1254 | 32.3545 | 41.7339
246 | 45.3348 | 32.577 | 46.3162
247 | 43.6025 | 35.1179 | 43.4782
248 | 46.5006 | 34.173 | 40.855
249 | 42.4334 | 35.3423 | 42.0663
250 | 43.1296 | 34.3276 | 42.7374
251 | 44.2649 | 33.4642 | 46.7336
252 | 42.458 | 34.7135 | 45.5365
253 | 38.1501 | 35.1857 | 43.9246
254 | 44.0407 | 34.3697 | 44.0739
255 | 41.9414 | 32.6223 | 40.1398
256 | 43.0482 | 34.7834 | 42.5896
257 | 42.2847 | 35.2013 | 42.9329
258 | 42.8892 | 34.3635 | 44.4454
259 | 41.8561 | 34.4664 | 40.9407
260 | 43.6887 | 34.6302 | 42.8614
261 | 41.5287 | 35.2798 | 42.7294
262 | 44.5034 | 34.18 | 43.6422
263 | 43.4351 | 37.7681 | 40.4491
264 | 43.9827 | 36.897 | 41.5359
265 | 43.6522 | 34.8399 | 41.8111
266 | 42.24 | 34.9206 | 40.8954
267 | 42.5383 | 33.9736 | 45.7902
268 | 45.3756 | 34.8727 | 42.0158
269 | 44.2606 | 34.8303 | 43.17
270 | 44.0481 | 34.5604 | 47.4435
271 | 44.6377 | 35.4864 | 42.8955
272 | 42.3363 | 33.1431 | 45.9831
273 | 43.4692 | 33.7138 | 45.8978
274 | 42.9704 | 33.1293 | 43.0467
275 | 42.0848 | 35.0561 | 44.2333
276 | 41.965 | 33.6603 | 43.5333
277 | 45.8262 | 36.3193 | 42.3068
278 | 44.5032 | 33.0816 | 46.3983
279 | 44.5348 | 34.334 | 43.7939
280 | 42.34 | 33.5853 | 45.2964
281 | 42.0655 | 34.4525 | 41.8238
282 | 44.6185 | 34.9577 | 44.7552
283 | 45.3317 | 34.2923 | 44.1096
284 | 44.6834 | 34.942 | 43.0476
285 | 44.0406 | 34.8732 | 41.6626
286 | 42.2173 | 35.4619 | 41.1122
287 | 43.0213 | 35.1483 | 44.0041
288 | 43.3598 | 35.4275 | 42.7726
289 | 45.8136 | 33.7315 | 45.8054
290 | 42.0843 | 33.5006 | 41.3063
291 | 41.9769 | 35.1444 | 43.3657
292 | 41.7793 | 35.929 | 46.9748
293 | 41.5384 | 33.1804 | 42.7915
294 | 44.3638 | 34.4108 | 42.6476
295 | 43.192 | 33.3932 | 44.5139
296 | 42.6089 | 32.132 | 42.0971
297 | 45.8706 | 33.0742 | 44.899
298 | 42.4459 | 32.876 | 42.8407
299 | 41.1574 | 33.3724 | 42.0844
300 | 44.6146 | 35.5697 | 43.9186
301 | 46.5066 | 33.9922 | 44.1337
302 | 46.7395 | 34.1369 | 41.2432
303 | 45.1609 | 35.7475 | 43.702
304 | 41.4341 | 33.8199 | 41.3911
305 | 43.0586 | 35.3373 | 43.3316
306 | 42.135 | 34.7953 | 41.9787
307 | 44.1391 | 34.3361 | 44.1951
308 | 44.1154 | 34.6574 | 44.2323
309 | 41.8016 | 34.9738 | 43.9683
310 | 44.3247 | 34.3222 | 45.7831
311 | 42.9832 | 33.9132 | 41.4905
312 | 43.6893 | 33.2597 | 43.5311
313 | 40.1208 | 33.8204 | 43.5751
314 | 45.0258 | 37.5635 | 43.7633
315 | 43.4262 | 33.9375 | 43.7954
316 | 40.4778 | 34.7651 | 43.2187
317 | 42.9293 | 33.1949 | 43.8932
318 | 42.5635 | 33.8778 | 42.0026
319 | 45.6705 | 35.1426 | 41.6808
320 | 42.1511 | 33.5354 | 42.9452
321 | 40.984 | 35.5978 | 45.8429
322 | 43.8557 | 34.4144 | 42.9205
323 | 43.0321 | 32.603 | 43.3966
324 | 42.6317 | 34.7978 | 42.7038
325 | 44.316 | 33.6147 | 46.8142
326 | 42.3545 | 36.9067 | 41.5622
327 | 41.2021 | 34.3933 | 42.4414
328 | 43.4206 | 33.1693 | 42.5292
329 | 43.7171 | 34.556 | 46.5407
330 | 46.033 | 35.1231 | 42.4823
331 | 43.9323 | 36.6676 | 43.9263
332 | 43.4651 | 33.4895 | 40.3429
333 | 44.6915 | 35.5213 | 43.4102
334 | 44.308 | 34.0196 | 44.7373
335 | 43.2722 | 33.5353 | 42.1994
336 | 41.3807 | 33.6163 | 45.0952
337 | 46.1054 | 34.833 | 44.0966
338 | 42.795 | 34.6225 | 43.9111
339 | 43.5842 | 34.1733 | 42.572
340 | 46.5568 | 34.0517 | 45.5216
341 | 45.8574 | 35.8313 | 43.9767
342 | 44.8544 | 34.0712 | 42.0764
343 | 42.777 | 33.4215 | 41.4904
344 | 42.7328 | 36.3091 | 44.5745
345 | 42.5059 | 34.8489 | 43.5466
346 | 41.847 | 33.7186 | 46.0353
347 | 42.0216 | 34.0325 | 40.5783
348 | 42.2194 | 33.9119 | 43.587
349 | 42.5459 | 35.9032 | 43.4711
350 | 41.9981 | 35.7914 | 44.6241
351 | 43.5801 | 34.3725 | 42.4502
352 | 44.1708 | 33.0683 | 45.7235
353 | 43.0934 | 34.407 | 40.1095
354 | 42.9491 | 34.1779 | 44.0692
355 | 42.4136 | 35.1584 | 42.6438
356 | 43.6233 | 32.4651 | 45.4187
357 | 42.6283 | 35.301 | 42.0526
358 | 44.2572 | 35.086 | 42.9103
359 | 42.52 | 32.0877 | 44.4786
360 | 43.6976 | 32.7608 | 42.3704
361 | 41.9692 | 34.8829 | 43.1388
362 | 43.9144 | 34.8563 | 43.466
363 | 42.333 | 35.2805 | 44.0148
364 | 41.8195 | 33.2469 | 45.2111
365 | 43.4924 | 34.9131 | 43.4864
366 | 41.6243 | 33.8661 | 42.0351
367 | 43.3087 | 35.3313 | 43.2073
368 | 44.2137 | 32.3984 | 43.7422
369 | 42.9491 | 33.4816 | 43.3119
370 | 43.3257 | 33.2993 | 42.745
371 | 45.666 | 36.2867 | 39.8518
372 | 44.6782 | 35.938 | 44.1667
373 | 45.1102 | 32.7007 | 43.4989
374 | 44.0828 | 35.7341 | 41.6111
375 | 44.819 | 35.7044 | 40.4625
376 | 45.393 | 35.3634 | 43.4938
377 | 42.3925 | 34.3148 | 40.7167
378 | 42.0538 | 35.8207 | 43.88
379 | 42.7648 | 34.0784 | 43.9762
380 | 41.5143 | 36.5092 | 41.7955
381 | 43.2175 | 34.8016 | 43.7649
382 | 44.0366 | 33.3967 | 42.3205
383 | 45.1807 | 35.9733 | 42.9696
384 | 42.1613 | 34.5264 | 44.9653
385 | 43.3036 | 34.6312 | 44.3666
386 | 43.565 | 31.3934 | 44.1265
387 | 42.2532 | 37.0989 | 42.5893
388 | 42.6561 | 33.6727 | 42.8644
389 | 41.1595 | 34.8231 | 44.7326
390 | 42.9682 | 34.1572 | 41.001
391 | 43.9527 | 34.9633 | 44.6514
392 | 44.6036 | 33.5939 | 43.2821
393 | 42.7796 | 36.1782 | 42.0966
394 | 46.652 | 35.9955 | 40.5113
395 | 41.4775 | 33.6105 | 43.048
396 | 43.5386 | 35.7754 | 44.6429
397 | 44.5023 | 34.1917 | 41.7627
398 | 44.001 | 34.1347 | 41.4454
399 | 41.3286 | 33.6299 | 42.739
400 | 44.9702 | 34.1019 | 42.8368
401 | 41.7706 | 34.7798 | 46.0167
402 | 46.1819 | 32.7143 | 42.536
403 | 42.4621 | 33.7041 | 45.4085
404 | 42.0607 | 32.5074 | 43.4798
405 | 45.1852 | 34.5702 | 44.2718
406 | 43.9722 | 34.1127 | 42.3882
407 | 41.5544 | 37.7503 | 46.3412
408 | 42.2485 | 34.4478 | 41.8199
409 | 44.5987 | 34.7517 | 43.445
410 | 42.7543 | 31.4949 | 44.3251
411 | 46.331 | 34.6719 | 44.2946
412 | 44.1562 | 33.4959 | 45.674
413 | 44.2083 | 33.6804 | 43.1699
414 | 43.0454 | 33.5601 | 45.4154
415 | 40.4247 | 35.1295 | 42.6216
416 | 44.5656 | 33.5712 | 42.1341
417 | 42.668 | 36.2114 | 43.2084
418 | 41.6516 | 34.3001 | 45.7234
419 | 43.1957 | 35.7406 | 43.3668
420 | 42.9914 | 32.4929 | 43.8071
421 | 43.9096 | 35.8271 | 41.9779
422 | 43.5093 | 33.9723 | 43.0126
423 | 44.3661 | 34.38 | 43.1404
424 | 43.6939 | 31.6006 | 42.7639
425 | 45.1475 | 33.9057 | 43.6223
426 | 43.9613 | 35.0337 | 45.5304
427 | 43.8976 | 33.8216 | 39.7799
428 | 42.9727 | 35.6399 | 40.8192
429 | 45.0035 | 34.7148 | 43.2924
430 | 42.1761 | 35.7233 | 41.0845
431 | 43.2309 | 35.7261 | 42.5689
432 | 45.9451 | 36.3126 | 43.2211
433 | 44.0126 | 34.3389 | 43.815
434 | 45.3974 | 35.051 | 45.6686
435 | 45.8903 | 35.5081 | 42.1979
436 | 43.5323 | 35.1513 | 40.4993
437 | 40.4105 | 34.3213 | 44.4505
438 | 44.5633 | 31.6416 | 43.6292
439 | 41.9512 | 36.1161 | 43.3989
440 | 46.6202 | 33.8266 | 41.7341
441 | 43.195 | 36.5668 | 43.2852
442 | 39.7802 | 37.3091 | 44.7913
443 | 44.2961 | 34.0588 | 43.2657
444 | 42.9417 | 33.6695 | 42.1519
445 | 43.5228 | 34.7268 | 44.4145
446 | 42.6482 | 33.2482 | 43.7101
447 | 43.8403 | 34.5856 | 40.6564
448 | 44.3023 | 32.6115 | 42.1265
449 | 41.5381 | 31.9392 | 40.4733
450 | 45.8575 | 35.4447 | 41.8627
451 | 41.877 | 34.0126 | 42.5707
452 | 40.4215 | 37.689 | 42.5932
453 | 42.2001 | 35.0923 | 44.8817
454 | 43.6486 | 33.8295 | 42.7066
455 | 42.9116 | 34.5755 | 44.6363
456 | 43.5733 | 33.3156 | 42.4192
457 | 43.5972 | 33.7334 | 42.0781
458 | 43.6927 | 35.3601 | 41.9635
459 | 43.9924 | 36.8902 | 46.8906
460 | 44.5824 | 33.8532 | 42.6564
461 | 45.3496 | 34.7635 | 46.1899
462 | 43.9612 | 33.9389 | 42.6677
463 | 40.1172 | 32.9859 | 43.5945
464 | 44.4621 | 35.8255 | 43.2453
465 | 46.9325 | 34.1786 | 45.7894
466 | 42.1823 | 35.9619 | 42.2146
467 | 42.1199 | 35.4146 | 44.4897
468 | 42.5567 | 34.6934 | 43.0901
469 | 43.9622 | 34.6671 | 45.3992
470 | 41.0159 | 33.9509 | 39.8601
471 | 43.5688 | 33.5597 | 42.1808
472 | 41.5442 | 34.5411 | 41.3933
473 | 42.136 | 34.6611 | 44.2753
474 | 42.2982 | 33.7896 | 44.1812
475 | 41.495 | 33.6641 | 45.1993
476 | 45.2609 | 33.9328 | 42.3976
477 | 42.8422 | 33.9745 | 41.5079
478 | 43.6397 | 33.7617 | 44.5991
479 | 43.5792 | 34.4621 | 41.3895
480 | 39.9934 | 35.2231 | 42.67
481 | 44.9565 | 34.3564 | 44.4423
482 | 43.0952 | 34.8371 | 42.6657
483 | 44.5322 | 33.6413 | 44.0848
484 | 44.7597 | 33.8676 | 42.6895
485 | 42.8264 | 35.4315 | 44.2574
486 | 41.5054 | 34.4934 | 41.0699
487 | 42.9103 | 33.7744 | 41.9849
488 | 45.7503 | 34.2629 | 44.0126
489 | 41.2931 | 36.8025 | 44.8232
490 | 44.6558 | 32.7042 | 41.5205
491 | 46.3008 | 34.7666 | 42.6216
492 | 45.9627 | 35.8669 | 47.2831
493 | 42.0558 | 34.1 | 44.4691
494 | 45.655 | 33.6237 | 42.6441
495 | 42.0486 | 34.7638 | 43.4188
496 | 43.0967 | 34.2619 | 41.7541
497 | 44.3465 | 35.4113 | 42.855
498 | 44.1306 | 35.7155 | 41.998
499 | 44.5552 | 32.2732 | 43.4039
500 | 41.136 | 31.8794 | 43.0654
501 | 42.1423 | 34.4776 | 41.2584
502 | 40.0594 | 33.8215 | 44.3953
503 | 40.6245 | 34.9599 | 42.1227
504 | 42.8577 | 33.1346 | 45.7052
505 | 43.4116 | 32.8518 | 44.603
506 | 44.241 | 34.355 | 44.5595
507 | 43.7438 | 33.9629 | 47.1141
508 | 43.8342 | 32.9639 | 43.1967
509 | 44.5379 | 34.0878 | 42.1545
510 | 42.0439 | 33.874 | 41.4485
511 | 43.8198 | 34.032 | 42.0361
512 | 41.304 | 34.4213 | 43.5994
513 | 41.3217 | 34.5748 | 42.5882
514 | 42.4618 | 33.888 | 43.0865
515 | 41.6214 | 29.885 | 42.2604
516 | 42.0953 | 33.9998 | 43.413
517 | 44.9015 | 36.1142 | 43.3099
518 | 43.9575 | 35.6496 | 41.7753
519 | 43.7321 | 35.1243 | 43.2026
520 | 42.6004 | 34.883 | 45.1588
521 | 43.1602 | 34.4042 | 48.0334
522 | 43.9459 | 33.8513 | 43.5682
523 | 43.4276 | 34.3855 | 42.4104
524 | 42.4743 | 34.2358 | 41.5815
525 | 44.5425 | 32.9724 | 42.5517
526 | 42.1895 | 35.4994 | 41.8391
527 | 42.4361 | 35.0655 | 42.8688
528 | 42.9451 | 33.5992 | 43.2829
529 | 41.5692 | 35.6306 | 45.0603
530 | 46.6014 | 32.2636 | 44.7927
531 | 42.3786 | 34.3677 | 43.4639
532 | 44.5696 | 33.3528 | 41.6451
533 | 44.3294 | 32.1911 | 42.8492
534 | 43.8593 | 33.9762 | 41.5182
535 | 44.9256 | 32.6475 | 42.9254
536 | 43.6206 | 35.4416 | 42.999
537 | 42.3793 | 33.0655 | 45.505
538 | 44.0345 | 32.3701 | 45.0891
539 | 44.7397 | 35.0026 | 41.1612
540 | 43.9369 | 33.9147 | 41.7221
541 | 43.6423 | 33.3926 | 43.1547
542 | 45.5396 | 35.2445 | 42.724
543 | 42.5045 | 35.6473 | 41.2073
544 | 45.928 | 36.2958 | 43.8692
545 | 43.7434 | 35.9516 | 43.26
546 | 44.2238 | 33.1847 | 42.0917
547 | 45.4031 | 34.1437 | 45.7834
548 | 42.9119 | 32.2043 | 43.6876
549 | 43.283 | 34.3269 | 44.0608
550 | 44.0732 | 32.6115 | 44.1431
551 | 43.9359 | 35.626 | 41.0141
552 | 42.5444 | 34.0628 | 43.8515
553 | 42.3739 | 32.7542 | 42.9612
554 | 43.5028 | 35.868 | 41.6985
555 | 44.5657 | 34.3133 | 43.1444
556 | 41.9798 | 33.9884 | 44.2094
557 | 44.0815 | 33.7401 | 41.7785
558 | 42.2451 | 34.9058 | 42.0974
559 | 41.2204 | 34.1383 | 44.051
560 | 45.0013 | 32.4474 | 44.9204
561 | 42.8586 | 32.2769 | 45.1912
562 | 43.2069 | 33.9147 | 42.9503
563 | 39.8325 | 34.3188 | 42.0609
564 | 44.5338 | 35.2179 | 43.4939
565 | 43.5635 | 33.9205 | 45.0621
566 | 43.6167 | 32.652 | 44.982
567 | 43.7813 | 33.9642 | 44.7336
568 | 46.4456 | 35.6309 | 41.8095
569 | 43.5283 | 32.3188 | 43.3433
570 | 43.0019 | 33.1377 | 42.7832
571 | 43.1714 | 35.2621 | 44.5386
572 | 43.1307 | 33.6367 | 40.3954
573 | 44.3615 | 35.7873 | 44.1862
574 | 42.9009 | 32.6605 | 45.5331
575 | 43.1288 | 33.0798 | 39.565
576 | 43.4146 | 33.1043 | 45.5213
577 | 42.0629 | 33.9512 | 43.873
578 | 45.057 | 35.371 | 42.8403
579 | 41.3401 | 33.8549 | 44.309
580 | 43.3337 | 35.9112 | 42.9296
581 | 41.097 | 33.956 | 41.589
582 | 43.686 | 35.2742 | 41.0143
583 | 41.8121 | 34.2641 | 41.4304
584 | 43.9423 | 32.8169 | 44.381
585 | 40.1868 | 34.0015 | 44.5589
586 | 43.2862 | 34.7321 | 40.7549
587 | 43.3925 | 33.0026 | 43.4879
588 | 42.1114 | 32.2993 | 40.872
589 | 43.9484 | 35.5261 | 43.1823
590 | 46.4716 | 33.5871 | 41.8827
591 | 41.8765 | 35.1955 | 43.7281
592 | 43.7546 | 36.4712 | 43.0368
593 | 43.8037 | 35.2693 | 43.1744
594 | 45.0059 | 34.5252 | 44.3348
595 | 45.9218 | 33.8111 | 42.2516
596 | 42.9489 | 33.9923 | 41.8868
597 | 46.3814 | 33.7128 | 46.4495
598 | 42.8696 | 37.597 | 43.8902
599 | 46.7396 | 32.4882 | 42.3996
600 | 42.3446 | 33.4714 | 43.0777
601 | 43.3105 | 32.2369 | 44.6431
602 | 44.1339 | 34.3561 | 45.6088
603 | 44.8753 | 33.0569 | 44.107
604 | 43.3501 | 36.1844 | 44.1036
605 | 42.1648 | 35.0913 | 44.2567
606 | 42.0554 | 35.1223 | 41.74
607 | 42.6598 | 33.9501 | 42.915
608 | 42.7914 | 34.4095 | 41.3062
609 | 43.4471 | 34.7002 | 43.1873
610 | 41.7085 | 33.8657 | 41.0061
611 | 43.9767 | 35.9863 | 43.9172
612 | 43.2115 | 32.4948 | 45.6978
613 | 43.926 | 34.2072 | 41.838
614 | 42.3781 | 36.0516 | 40.6851
615 | 46.6819 | 31.3882 | 43.8712
616 | 43.7795 | 34.1412 | 44.8918
617 | 46.3311 | 34.5915 | 42.8069
618 | 46.4791 | 33.1773 | 43.6474
619 | 43.9757 | 34.1422 | 43.2864
620 | 43.245 | 32.2257 | 46.657
621 | 42.4905 | 36.0347 | 40.7405
622 | 45.5293 | 34.1846 | 42.2638
623 | 46.9033 | 34.0673 | 41.1647
624 | 42.5944 | 34.0875 | 42.5036
625 | 42.6359 | 36.5098 | 42.53
626 | 45.7781 | 36.1228 | 46.8652
627 | 41.7373 | 37.412 | 41.968
628 | 41.4202 | 33.9053 | 43.3899
629 | 41.9204 | 33.528 | 43.4418
630 | 45.824 | 35.2165 | 41.5493
631 | 42.9663 | 34.1807 | 38.9193
632 | 42.9556 | 33.6717 | 42.7196
633 | 44.1572 | 32.7176 | 41.1525
634 | 43.7023 | 32.9221 | 41.3361
635 | 43.8282 | 35.5767 | 44.6797
636 | 42.3916 | 32.2278 | 44.2936
637 | 43.9962 | 33.4549 | 42.3914
638 | 43.488 | 35.1245 | 41.6314
639 | 45.0014 | 33.774 | 44.4254
640 | 42.2901 | 33.7127 | 44.3409
641 | 43.7529 | 34.1276 | 41.8708
642 | 42.2765 | 34.2544 | 42.1509
643 | 42.7119 | 35.4445 | 45.2239
644 | 44.102 | 34.1884 | 40.693
645 | 43.0313 | 34.4314 | 41.7003
646 | 41.9165 | 35.762 | 43.4502
647 | 44.0517 | 31.8333 | 43.7251
648 | 43.0571 | 34.2088 | 40.9898
649 | 42.8287 | 36.4703 | 45.3836
650 | 41.9131 | 34.5868 | 43.1811
651 | 43.7519 | 34.7506 | 43.4745
652 | 42.6816 | 33.5275 | 44.9641
653 | 43.146 | 31.7405 | 44.4707
654 | 47.125 | 32.7758 | 41.5671
655 | 45.7662 | 33.4955 | 43.3008
656 | 43.4445 | 34.9974 | 42.9245
657 | 44.3917 | 33.1617 | 43.5049
658 | 42.5284 | 33.1261 | 43.839
659 | 42.4266 | 33.8083 | 44.6083
660 | 43.9849 | 34.9911 | 42.826
661 | 42.8405 | 35.168 | 46.7714
662 | 44.2294 | 34.2245 | 42.5166
663 | 42.7147 | 33.6108 | 43.3349
664 | 44.2369 | 33.9941 | 42.1741
665 | 42.0021 | 33.7836 | 42.1952
666 | 44.3307 | 33.7142 | 44.0829
667 | 41.5188 | 36.4693 | 45.118
668 | 43.0276 | 37.6814 | 40.7957
669 | 43.4548 | 34.1284 | 41.4224
670 | 41.961 | 34.7506 | 44.6666
671 | 43.911 | 33.1191 | 44.7954
672 | 42.3873 | 35.7246 | 43.8486
673 | 44.832 | 33.3668 | 38.563
674 | 44.0004 | 35.5896 | 42.0219
675 | 42.2438 | 34.3361 | 43.7168
676 | 46.2112 | 34.1919 | 45.8149
677 | 43.7254 | 35.2218 | 42.0022
678 | 43.7738 | 32.5316 | 42.4503
679 | 46.589 | 32.6248 | 43.3747
680 | 42.2379 | 36.078 | 43.5935
681 | 39.5883 | 34.8356 | 42.7115
682 | 43.5865 | 33.61 | 45.6996
683 | 41.9781 | 34.2854 | 44.2528
684 | 43.5236 | 34.5628 | 45.2891
685 | 45.1045 | 34.6658 | 44.298
686 | 45.8025 | 34.9534 | 44.9263
687 | 46.7272 | 33.0491 | 43.9148
688 | 44.984 | 33.4875 | 43.8964
689 | 42.5949 | 31.5282 | 44.3519
690 | 45.5278 | 36.8376 | 44.8065
691 | 43.1339 | 36.0693 | 40.8366
692 | 43.5773 | 33.2526 | 42.868
693 | 42.1175 | 33.4996 | 44.0931
694 | 45.3613 | 36.0726 | 41.4447
695 | 43.122 | 33.6951 | 44.1298
696 | 43.1089 | 35.7373 | 41.1271
697 | 41.9719 | 34.6332 | 42.9055
698 | 43.0952 | 34.4172 | 43.9743
699 | 41.7165 | 35.0678 | 42.4741
700 | 41.3465 | 35.1589 | 42.4397
701 | 44.4055 | 34.0365 | 45.4023
702 | 43.8339 | 36.3524 | 45.111
703 | 42.4099 | 34.4691 | 43.6488
704 | 42.5115 | 31.5729 | 44.7147
705 | 46.1903 | 34.4345 | 42.4169
706 | 42.0282 | 34.6131 | 41.6952
707 | 45.4736 | 34.6986 | 43.4162
708 | 44.6409 | 35.385 | 42.7067
709 | 45.6864 | 34.4111 | 43.4277
710 | 45.0152 | 33.2406 | 41.7546
711 | 43.2067 | 34.7148 | 43.5351
712 | 42.5766 | 34.2464 | 43.1943
713 | 43.9477 | 35.5237 | 40.9858
714 | 40.78 | 31.4257 | 44.0586
715 | 40.2633 | 33.5545 | 42.9183
716 | 45.1073 | 34.277 | 44.559
717 | 42.1486 | 33.3485 | 41.7761
718 | 41.0543 | 31.7947 | 43.0793
719 | 43.9538 | 35.4357 | 43.014
720 | 42.1912 | 32.1811 | 45.9935
721 | 43.0362 | 33.1933 | 43.6472
722 | 41.2788 | 34.9092 | 42.864
723 | 44.0513 | 33.8299 | 43.7665
724 | 44.3651 | 35.0388 | 44.8046
725 | 42.683 | 34.4549 | 42.5221
726 | 42.8175 | 35.3364 | 42.1133
727 | 43.2221 | 33.3153 | 45.6449
728 | 44.8872 | 35.0861 | 44.7424
729 | 44.2544 | 35.0765 | 45.2002
730 | 41.754 | 36.2013 | 45.586
731 | 42.0748 | 36.8193 | 43.7093
732 | 41.0975 | 35.9567 | 42.2721
733 | 42.1544 | 34.3988 | 41.3779
734 | 43.6359 | 32.8329 | 45.2661
735 | 41.2348 | 35.9623 | 42.2758
736 | 44.5228 | 34.051 | 43.41
737 | 43.0285 | 33.7921 | 42.0008
738 | 42.617 | 34.2088 | 42.9088
739 | 41.6878 | 36.532 | 43.2267
740 | 43.1755 | 35.8705 | 42.8325
741 | 45.604 | 33.9824 | 44.6922
742 | 43.7682 | 35.6916 | 42.8381
743 | 44.6439 | 35.8663 | 42.5658
744 | 41.1105 | 34.1689 | 43.8264
745 | 41.6173 | 34.1097 | 40.9076
746 | 41.7164 | 37.3201 | 44.5609
747 | 45.476 | 33.1388 | 43.8023
748 | 42.2684 | 34.6571 | 42.5863
749 | 41.709 | 33.5068 | 45.0804
750 | 43.6604 | 32.8653 | 41.603
751 | 45.2702 | 33.3272 | 42.4654
752 | 43.933 | 35.3054 | 42.4555
753 | 43.6076 | 34.204 | 42.5448
754 | 43.1797 | 33.9632 | 42.9664
755 | 42.2327 | 37.0703 | 42.0964
756 | 41.8671 | 33.3354 | 44.9727
757 | 43.22 | 35.7765 | 42.7045
758 | 46.7823 | 32.7388 | 41.7015
759 | 45.278 | 35.2214 | 44.7614
760 | 44.2075 | 35.4035 | 44.5838
761 | 43.6606 | 31.9523 | 41.9511
762 | 42.6292 | 32.1518 | 42.0695
763 | 43.8266 | 34.0505 | 42.6833
764 | 42.8681 | 35.831 | 45.1283
765 | 41.4518 | 35.0731 | 42.1401
766 | 41.7345 | 34.0384 | 43.5443
767 | 42.1575 | 34.6597 | 41.4281
768 | 44.0757 | 34.3858 | 45.0943
769 | 42.7057 | 33.1372 | 44.9799
770 | 45.003 | 31.9431 | 43.2764
771 | 42.6161 | 34.2468 | 42.279
772 | 43.1233 | 35.5406 | 44.0961
773 | 42.8548 | 34.2848 | 43.4984
774 | 42.1108 | 34.1935 | 43.7158
775 | 42.3413 | 35.6422 | 42.6317
776 | 42.6009 | 33.3833 | 42.3726
777 | 42.7166 | 35.5796 | 42.9575
778 | 40.2871 | 33.5729 | 44.159
779 | 43.609 | 36.4865 | 42.0751
780 | 42.7936 | 34.0356 | 42.6295
781 | 41.8816 | 33.3391 | 45.134
782 | 40.5548 | 34.6886 | 46.0353
783 | 43.0032 | 36.3279 | 44.9245
784 | 43.9282 | 33.3537 | 43.6948
785 | 42.672 | 32.6726 | 44.9476
786 | 43.9288 | 33.5536 | 43.5703
787 | 40.8108 | 35.5018 | 42.1321
788 | 40.2784 | 35.0788 | 46.0086
789 | 40.6601 | 34.7588 | 42.7234
790 | 41.4075 | 32.3841 | 39.8893
791 | 43.7012 | 34.1453 | 44.7623
792 | 42.6854 | 34.8806 | 43.6931
793 | 42.6974 | 34.7257 | 42.1984
794 | 44.0193 | 33.3468 | 42.7608
795 | 42.6775 | 34.4691 | 41.9108
796 | 42.9816 | 32.5685 | 43.1371
797 | 40.6792 | 34.3392 | 44.2721
798 | 42.861 | 35.2338 | 42.3692
799 | 43.751 | 33.533 | 43.4247
800 | 45.9915 | 33.8845 | 44.871
801 | 42.3755 | 35.413 | 45.9849
802 | 42.2109 | 36.1063 | 42.7789
803 | 43.7774 | 35.1718 | 45.0339
804 | 42.7684 | 36.7693 | 41.9669
805 | 44.2399 | 35.6712 | 41.9643
806 | 41.2334 | 34.0445 | 44.9589
807 | 42.8141 | 36.8431 | 40.7073
808 | 43.2205 | 33.4833 | 43.0652
809 | 43.9363 | 33.8376 | 42.6935
810 | 44.1028 | 32.2618 | 41.3259
811 | 46.2592 | 32.7569 | 42.9733
812 | 42.5909 | 32.9347 | 42.2955
813 | 42.3958 | 34.5941 | 43.2981
814 | 43.1985 | 34.0768 | 42.7452
815 | 43.4948 | 33.76 | 44.1098
816 | 42.5733 | 33.7921 | 41.598
817 | 44.0631 | 34.0704 | 45.3413
818 | 43.2535 | 32.8138 | 43.5799
819 | 43.5877 | 35.1921 | 43.3536
820 | 44.2727 | 31.7445 | 45.0884
821 | 40.5033 | 34.1482 | 42.1876
822 | 42.8364 | 32.3036 | 44.5186
823 | 43.5931 | 35.1957 | 46.1139
824 | 42.5901 | 33.5865 | 42.0226
825 | 45.6677 | 34.3393 | 43.5912
826 | 43.3815 | 33.4113 | 44.1442
827 | 42.6795 | 33.2973 | 42.3797
828 | 42.2058 | 34.8206 | 45.2349
829 | 41.8376 | 33.0054 | 41.8707
830 | 44.6026 | 34.3188 | 43.6894
831 | 44.5204 | 34.676 | 42.7014
832 | 45.0123 | 33.1568 | 44.1815
833 | 45.9453 | 35.2193 | 41.682
834 | 43.3688 | 35.2116 | 43.7831
835 | 40.0692 | 36.1705 | 45.1878
836 | 42.5243 | 36.3762 | 43.6401
837 | 41.9034 | 35.2108 | 44.0104
838 | 43.812 | 34.8686 | 43.227
839 | 42.0985 | 33.8104 | 45.3362
840 | 41.7681 | 33.4063 | 47.7454
841 | 43.2936 | 31.8334 | 44.5436
842 | 43.5081 | 33.4809 | 43.4782
843 | 45.8493 | 37.609 | 43.5104
844 | 45.9331 | 36.6783 | 41.8286
845 | 44.6259 | 35.1414 | 42.6015
846 | 44.9863 | 32.1684 | 44.5608
847 | 43.1154 | 35.008 | 44.1273
848 | 41.4106 | 31.996 | 41.4435
849 | 41.4545 | 32.5991 | 44.938
850 | 46.3046 | 35.1426 | 42.2398
851 | 44.7151 | 32.5829 | 44.4464
852 | 44.0561 | 35.1798 | 43.2882
853 | 43.8422 | 36.4271 | 45.0481
854 | 42.9703 | 34.8316 | 43.2419
855 | 41.1906 | 35.5898 | 44.2685
856 | 43.3725 | 32.9007 | 43.5883
857 | 43.7977 | 35.8498 | 44.7696
858 | 42.5738 | 33.3934 | 44.5683
859 | 47.7091 | 35.0027 | 43.4565
860 | 42.5366 | 34.5784 | 46.1154
861 | 42.7096 | 34.2226 | 43.7539
862 | 43.9799 | 33.7252 | 43.418
863 | 40.3413 | 33.6648 | 42.4628
864 | 46.2969 | 34.3583 | 44.092
865 | 42.6472 | 34.6946 | 43.8796
866 | 44.0768 | 33.2073 | 43.2495
867 | 43.9413 | 34.363 | 43.961
868 | 44.8045 | 32.3651 | 42.0165
869 | 46.7988 | 35.3349 | 42.4948
870 | 43.2048 | 36.4475 | 41.4649
871 | 43.6404 | 34.9835 | 43.4851
872 | 43.4412 | 34.6479 | 43.6466
873 | 43.5517 | 35.7583 | 43.4285
874 | 42.6316 | 31.7799 | 44.713
875 | 43.8052 | 37.4246 | 39.3539
876 | 44.0945 | 34.1904 | 42.7484
877 | 43.5813 | 34.2886 | 39.9785
878 | 44.6653 | 34.3294 | 44.849
879 | 40.686 | 32.7371 | 42.5567
880 | 44.2007 | 35.5378 | 43.8639
881 | 43.3664 | 33.1259 | 44.3254
882 | 43.9935 | 33.1504 | 42.0401
883 | 44.6996 | 36.2879 | 44.1064
884 | 42.733 | 34.3573 | 44.192
885 | 42.6278 | 32.232 | 44.7079
886 | 43.7648 | 33.4435 | 43.0498
887 | 43.1596 | 33.4134 | 42.9886
888 | 43.3868 | 34.4564 | 42.7747
889 | 43.6181 | 35.6367 | 41.8804
890 | 42.8063 | 32.8616 | 44.6808
891 | 42.9501 | 37.5798 | 41.6841
892 | 43.8563 | 32.8188 | 45.0267
893 | 42.6001 | 34.8919 | 43.4539
894 | 44.6202 | 33.9713 | 44.8233
895 | 41.0793 | 33.4778 | 43.4325
896 | 44.2814 | 35.3048 | 43.2887
897 | 42.3887 | 33.2773 | 43.7977
898 | 42.7569 | 33.7847 | 41.8457
899 | 43.9891 | 33.2272 | 43.2196
900 | 42.4289 | 34.8955 | 44.9729
901 | 42.1484 | 36.3358 | 43.1372
902 | 42.2999 | 35.0871 | 41.4689
903 | 39.813 | 34.5981 | 41.7196
904 | 43.2036 | 34.7944 | 43.1911
905 | 40.757 | 35.4983 | 42.8872
906 | 41.5193 | 35.7652 | 44.4739
907 | 46.9688 | 33.6079 | 44.3196
908 | 42.9522 | 35.0019 | 44.6999
909 | 44.0584 | 32.4002 | 45.7246
910 | 42.8326 | 35.4535 | 44.9029
911 | 43.0597 | 31.3618 | 43.0409
912 | 44.104 | 33.8821 | 43.6995
913 | 44.2429 | 35.3797 | 45.5151
914 | 44.0207 | 33.6071 | 39.9425
915 | 42.8521 | 34.2813 | 42.1668
916 | 42.6651 | 34.3559 | 41.1428
917 | 41.5559 | 34.0735 | 44.1895
918 | 44.8105 | 34.2536 | 43.6488
919 | 40.3592 | 34.4211 | 40.3422
920 | 42.7272 | 33.6433 | 42.9707
921 | 44.5251 | 33.8612 | 41.7558
922 | 42.9294 | 34.766 | 40.872
923 | 46.2697 | 33.9892 | 41.9539
924 | 43.1755 | 36.4328 | 41.1806
925 | 40.597 | 34.8662 | 43.8732
926 | 44.2948 | 35.723 | 43.2026
927 | 45.2062 | 35.2037 | 41.8391
928 | 43.8512 | 35.8194 | 42.8677
929 | 42.3304 | 34.9016 | 44.2782
930 | 43.5145 | 35.7967 | 42.3558
931 | 44.6902 | 33.5248 | 43.0567
932 | 44.4 | 34.18 | 45.1481
933 | 44.6392 | 33.7985 | 41.6891
934 | 45.371 | 33.3645 | 46.5499
935 | 41.3483 | 33.2947 | 45.8282
936 | 42.7668 | 33.0416 | 43.6931
937 | 38.4518 | 35.385 | 41.6079
938 | 44.6786 | 32.9111 | 42.1018
939 | 42.2194 | 33.6752 | 41.4307
940 | 43.7775 | 33.7133 | 42.4245
941 | 44.455 | 35.5542 | 40.8739
942 | 43.1677 | 36.752 | 44.4046
943 | 44.8619 | 35.6369 | 41.7329
944 | 42.4866 | 32.127 | 43.1087
945 | 45.1584 | 34.8377 | 42.3428
946 | 44.0156 | 35.7485 | 44.6001
947 | 44.805 | 34.2062 | 42.3162
948 | 41.03 | 33.8477 | 42.7979
949 | 41.2073 | 35.5954 | 44.2412
950 | 42.751 | 32.4092 | 44.1987
951 | 43.1737 | 33.3389 | 44.8142
952 | 42.7289 | 35.4642 | 44.223
953 | 44.7747 | 34.2965 | 42.4534
954 | 46.3558 | 33.2912 | 40.3442
955 | 45.1889 | 34.0967 | 42.402
956 | 44.9336 | 33.4806 | 43.5002
957 | 43.5011 | 34.1909 | 43.7926
958 | 42.9772 | 35.5568 | 42.9237
959 | 44.1322 | 33.6482 | 44.2566
960 | 44.433 | 35.3736 | 42.4052
961 | 44.6066 | 36.2255 | 43.6173
962 | 39.7049 | 30.6385 | 44.3346
963 | 44.4445 | 36.3615 | 42.554
964 | 43.7872 | 33.0845 | 45.5728
965 | 44.806 | 36.9593 | 43.9307
966 | 43.8146 | 32.9406 | 44.6729
967 | 44.9509 | 31.6507 | 44.7774
968 | 41.4826 | 33.5324 | 45.7673
969 | 44.1979 | 33.8844 | 42.4164
970 | 42.3753 | 34.3517 | 41.2609
971 | 42.6996 | 33.7028 | 43.8346
972 | 44.7414 | 33.9757 | 42.8716
973 | 42.3628 | 35.4086 | 45.6407
974 | 41.4533 | 32.9618 | 44.1745
975 | 41.8946 | 34.326 | 44.8242
976 | 43.8955 | 35.1017 | 44.1165
977 | 43.9723 | 35.331 | 43.9404
978 | 40.9068 | 36.0274 | 41.9234
979 | 40.0862 | 33.7871 | 43.4234
980 | 41.1621 | 35.0094 | 41.7992
981 | 45.0209 | 36.0223 | 44.5885
982 | 43.2118 | 33.5767 | 42.8158
983 | 40.6287 | 35.0394 | 45.406
984 | 40.6465 | 34.1655 | 43.5864
985 | 41.3064 | 33.8085 | 42.0862
986 | 42.1406 | 34.6327 | 41.4819
987 | 44.8419 | 36.2818 | 43.9847
988 | 42.4733 | 32.7735 | 43.4921
989 | 43.3341 | 34.3674 | 42.3912
990 | 42.5319 | 36.1254 | 43.5779
991 | 46.4631 | 31.3039 | 43.0714
992 | 40.407 | 33.4307 | 41.2139
993 | 42.9677 | 35.4684 | 41.6544
994 | 40.1726 | 34.3127 | 44.6026
995 | 42.2186 | 35.4332 | 41.3687
996 | 44.3814 | 34.3908 | 44.5714
997 | 43.6258 | 36.6335 | 42.8556
998 | 41.8684 | 35.0444 | 47.0771
999 | 42.4841 | 32.8429 | 42.2458
1000 | 45.2509 | 34.7474 | 42.8644
1001 | 44.1828 | 36.654 | 42.9972
1002 | 42.7177 | 33.5232 | 42.9063
1003 | 44.4963 | 34.7064 | 40.502
1004 | 40.2543 | 35.175 | 45.527
1005 | 44.5217 | 34.2306 | 42.2806
1006 | 42.38 | 33.886 | 43.6579
1007 | 45.1522 | 32.9434 | 43.1873
1008 | 42.437 | 37.4191 | 42.1266
1009 | 42.4125 | 32.8101 | 42.0388
1010 | 41.9944 | 36.415 | 43.4026
1011 | 42.6467 | 33.4761 | 46.0331
1012 | 40.7272 | 33.9075 | 41.714
1013 | 44.0827 | 33.2504 | 46.2
1014 | 43.9047 | 36.8524 | 42.8463
1015 | 44.2354 | 33.6018 | 43.5441
1016 | 41.3253 | 34.2859 | 43.7295
1017 | 46.2538 | 31.7806 | 43.07
1018 | 45.1588 | 36.4238 | 44.3789
1019 | 43.2417 | 34.5315 | 44.2662
1020 | 48.3954 | 34.6013 | 43.9865
1021 | 41.416 | 35.1189 | 43.9904
1022 | 46.2239 | 32.8831 | 42.5678
1023 | 45.1215 | 34.4803 | 44.1118
1024 | 42.5635 | 32.4676 | 44.7624
1025 | 41.5959 | 33.6513 | 44.7164
1026 | 44.4051 | 34.4764 | 44.6808
1027 | 41.6431 | 33.4036 | 42.9476
1028 | 43.7658 | 30.7719 | 42.6044
1029 | 42.7012 | 34.8606 | 45.7701
1030 | 43.4532 | 35.2412 | 42.4321
1031 | 44.63 | 34.4757 | 40.7828
1032 | 41.013 | 35.5262 | 43.9476
1033 | 46.2918 | 33.0766 | 41.4253
1034 | 43.2342 | 35.9346 | 42.7405
1035 | 44.464 | 33.1315 | 43.5757
1036 | 41.0797 | 32.1135 | 41.3778
1037 | 44.8331 | 35.6284 | 42.3753
1038 | 41.9188 | 34.6437 | 44.9916
1039 | 43.7356 | 31.6428 | 44.3999
1040 | 47.0081 | 34.1041 | 42.2059
1041 | 44.3578 | 33.5292 | 41.7781
1042 | 41.5554 | 34.728 | 41.9716
1043 | 41.7067 | 35.3985 | 47.037
1044 | 46.5977 | 33.0819 | 44.2032
1045 | 42.6045 | 31.9394 | 44.4217
1046 | 43.4631 | 34.3325 | 45.6818
1047 | 42.7585 | 34.7123 | 43.2265
1048 | 44.1208 | 35.8817 | 44.1172
1049 | 42.4618 | 35.8297 | 43.0673
1050 | 45.194 | 34.7084 | 43.4932
1051 | 45.3088 | 36.991 | 44.1206
1052 | 42.6357 | 34.6594 | 43.2214
1053 | 40.4565 | 36.6725 | 43.7751
1054 | 41.476 | 35.1496 | 42.0878
1055 | 41.9234 | 35.073 | 42.7422
1056 | 41.4242 | 35.7344 | 41.7497
1057 | 42.9574 | 32.9709 | 41.6526
1058 | 42.9112 | 33.976 | 44.1687
1059 | 42.6492 | 31.9365 | 43.9897
1060 | 41.3542 | 33.1761 | 42.3879
1061 | 46.298 | 32.2541 | 41.854
1062 | 43.651 | 35.4763 | 43.248
1063 | 43.6614 | 34.3932 | 42.9135
1064 | 42.6715 | 32.6388 | 41.6465
1065 | 44.0163 | 34.4358 | 43.1291
1066 | 41.6674 | 33.4957 | 42.3711
1067 | 43.9452 | 35.7886 | 42.7423
1068 | 44.9032 | 34.7059 | 40.899
1069 | 42.9085 | 34.9157 | 45.597
1070 | 43.8221 | 35.3939 | 43.5963
1071 | 42.6534 | 34.0106 | 43.2921
1072 | 43.8032 | 33.6755 | 44.2189
1073 | 42.6884 | 34.5613 | 43.7939
1074 | 43.2915 | 32.8257 | 46.6521
1075 | 44.0484 | 35.3043 | 44.6776
1076 | 42.1398 | 33.2159 | 43.6807
1077 | 41.2846 | 34.1738 | 49.4257
1078 | 42.6847 | 34.5944 | 44.0546
1079 | 43.3322 | 35.9961 | 45.4456
1080 | 42.9452 | 32.9975 | 43.0952
1081 | 43.7397 | 35.748 | 42.5357
1082 | 42.1341 | 34.1102 | 44.011
1083 | 42.593 | 32.9009 | 42.828
1084 | 44.4562 | 34.2387 | 45.0712
1085 | 43.7483 | 34.5561 | 44.0278
1086 | 42.9978 | 35.9016 | 42.6146
1087 | 42.2842 | 33.3128 | 44.1107
1088 | 42.2423 | 35.9167 | 44.54
1089 | 44.602 | 36.0286 | 44.026
1090 | 43.0759 | 33.0789 | 46.186
1091 | 42.002 | 32.8548 | 40.4702
1092 | 43.5117 | 33.8737 | 44.3329
1093 | 43.1276 | 33.9992 | 42.7454
1094 | 43.8019 | 36.0168 | 44.3406
1095 | 42.8536 | 35.3642 | 43.6235
1096 | 42.8939 | 34.8489 | 46.2585
1097 | 43.286 | 35.5012 | 41.5583
1098 | 39.9953 | 34.9763 | 42.2434
1099 | 44.4015 | 33.2857 | 41.2337
1100 | 43.1053 | 35.5293 | 44.4574
1101 | 42.9279 | 34.5894 | 42.3288
1102 | 41.1076 | 35.4059 | 43.9444
1103 | 42.7587 | 32.8455 | 41.5662
1104 | 43.7469 | 33.1582 | 43.6201
1105 | 41.5382 | 33.9202 | 44.8684
1106 | 45.414 | 33.4544 | 43.5014
1107 | 41.7448 | 32.693 | 43.3459
1108 | 43.6943 | 34.9143 | 42.3483
1109 | 43.3913 | 34.6152 | 42.1654
1110 | 41.6771 | 34.0569 | 41.9731
1111 | 45.2783 | 34.105 | 38.5072
1112 | 42.3969 | 33.5958 | 42.8277
1113 | 42.8635 | 34.0904 | 42.2044
1114 | 44.0608 | 33.3604 | 44.2131
1115 | 44.2017 | 35.3587 | 44.8488
1116 | 44.7415 | 33.6934 | 41.0135
1117 | 46.7559 | 33.3712 | 40.897
1118 | 42.7425 | 33.7876 | 41.935
1119 | 44.9518 | 34.537 | 44.0204
1120 | 42.9682 | 34.7005 | 42.2237
1121 | 42.3964 | 35.3093 | 44.1298
1122 | 45.4316 | 35.8753 | 46.7498
1123 | 41.6861 | 33.5187 | 45.0199
1124 | 42.4393 | 31.5638 | 44.8281
1125 | 44.4453 | 32.8921 | 45.4965
1126 | 42.8222 | 34.0279 | 42.764
1127 | 42.655 | 33.9843 | 44.9686
1128 | 43.6954 | 34.0007 | 41.9355
1129 | 44.2032 | 34.8723 | 41.6774
1130 | 39.9466 | 33.7227 | 44.7248
1131 | 44.6119 | 36.0735 | 43.4873
1132 | 42.0734 | 35.4022 | 43.5793
1133 | 44.8133 | 33.8301 | 43.3504
1134 | 41.3454 | 34.5873 | 42.5509
1135 | 42.9978 | 35.5992 | 41.7188
1136 | 44.0778 | 34.3276 | 43.5855
1137 | 43.578 | 33.3451 | 44.0171
1138 | 40.4945 | 33.0882 | 40.4871
1139 | 44.8823 | 32.1334 | 42.588
1140 | 46.3644 | 37.2069 | 44.6835
1141 | 42.8334 | 33.4814 | 41.1356
1142 | 41.5423 | 36.4696 | 42.4238
1143 | 41.0278 | 32.5142 | 41.4208
1144 | 44.0254 | 34.6862 | 42.949
1145 | 42.7522 | 33.1443 | 45.1282
1146 | 44.5803 | 36.37 | 42.915
1147 | 42.7043 | 33.9045 | 43.0193
1148 | 45.147 | 32.601 | 45.6627
1149 | 43.7663 | 34.0984 | 43.9731
1150 | 43.9814 | 38.3292 | 42.9445
1151 | 44.0166 | 32.4614 | 45.3542
1152 | 41.977 | 32.9568 | 44.0789
1153 | 41.1869 | 34.1348 | 41.8025
1154 | 42.9369 | 31.492 | 43.2793
1155 | 43.2249 | 32.9467 | 40.8906
1156 | 45.6841 | 32.8585 | 43.9419
1157 | 43.7595 | 32.0412 | 44.0748
1158 | 44.2314 | 37.1927 | 45.7349
1159 | 44.2316 | 36.8989 | 41.3973
1160 | 42.8343 | 34.1405 | 45.362
1161 | 43.0609 | 35.4909 | 42.3442
1162 | 43.4737 | 34.2215 | 41.4531
1163 | 41.9892 | 34.1805 | 44.9962
1164 | 44.4135 | 34.9854 | 41.4453
1165 | 43.0014 | 36.6656 | 43.9283
1166 | 44.1066 | 35.8217 | 43.5842
1167 | 43.5039 | 35.244 | 42.8366
1168 | 45.6581 | 34.2412 | 42.2135
1169 | 43.9949 | 35.1062 | 42.353
1170 | 43.3858 | 34.083 | 43.9968
1171 | 43.2731 | 32.924 | 43.6257
1172 | 44.7986 | 33.9656 | 42.434
1173 | 47.0911 | 34.8528 | 40.8773
1174 | 44.8181 | 34.0381 | 40.0835
1175 | 41.8582 | 34.9191 | 44.3216
1176 | 41.179 | 33.877 | 42.9859
1177 | 43.7577 | 34.8019 | 44.1857
1178 | 42.5699 | 33.3281 | 40.8395
1179 | 41.3645 | 33.6212 | 41.9999
1180 | 43.6746 | 35.3316 | 44.217
1181 | 45.1915 | 35.0309 | 43.1343
1182 | 43.2279 | 36.7115 | 44.2083
1183 | 46.2065 | 34.6436 | 43.8324
1184 | 42.1065 | 32.7776 | 45.0524
1185 | 43.5906 | 33.3582 | 40.791
1186 | 42.7734 | 32.8927 | 46.551
1187 | 44.6647 | 34.4421 | 40.7458
1188 | 44.6583 | 33.5578 | 43.7264
1189 | 42.1839 | 34.3905 | 42.1966
1190 | 42.2726 | 34.7613 | 42.7158
1191 | 43.9496 | 33.8514 | 41.575
1192 | 43.857 | 36.6074 | 44.7853
1193 | 41.9155 | 34.3395 | 43.8787
1194 | 44.0456 | 34.2062 | 43.6894
1195 | 43.9756 | 34.6342 | 42.2988
1196 | 43.8467 | 37.5859 | 42.2292
1197 | 46.0102 | 35.7307 | 46.5862
1198 | 42.4556 | 32.7115 | 43.4937
1199 | 44.1966 | 34.7742 | 42.6686
1200 | 46.5691 | 33.8488 | 44.5747
1201 | 40.3516 | 34.8699 | 43.0455
1202 | 43.1932 | 35.6194 | 44.1207
1203 | 40.9639 | 36.8715 | 41.3975
1204 | 43.3715 | 34.2579 | 43.991
1205 | 44.1029 | 32.984 | 43.8831
1206 | 42.7949 | 35.589 | 42.9155
1207 | 40.5296 | 37.1619 | 40.4983
1208 | 43.8862 | 35.5336 | 42.3074
1209 | 45.0063 | 34.9881 | 42.5416
1210 | 45.7046 | 35.3539 | 42.2221
1211 | 40.918 | 34.3478 | 42.9105
1212 | 41.649 | 33.6567 | 45.4786
1213 | 41.2963 | 33.0615 | 43.3411
1214 | 41.9433 | 31.708 | 45.0928
1215 | 44.1646 | 33.3097 | 42.4953
1216 | 43.3983 | 32.5643 | 42.7467
1217 | 45.4262 | 32.4799 | 40.4301
1218 | 43.408 | 34.7218 | 45.3395
1219 | 45.4919 | 34.2306 | 42.549
1220 | 43.7047 | 35.7847 | 42.1235
1221 | 45.0398 | 34.415 | 45.5426
1222 | 45.2268 | 35.7214 | 45.8858
1223 | 42.4861 | 33.3127 | 43.7578
1224 | 42.849 | 35.1828 | 43.0593
1225 | 45.0026 | 33.101 | 46.0435
1226 | 42.5595 | 33.7903 | 45.1714
1227 | 38.7312 | 33.9113 | 41.269
1228 | 44.8281 | 34.5886 | 43.7249
1229 | 44.2157 | 35.5616 | 41.8723
1230 | 42.7885 | 33.2215 | 40.7391
1231 | 41.9724 | 34.0031 | 44.1438
1232 | 43.5102 | 35.1156 | 42.6913
1233 | 44.6686 | 32.9055 | 43.2336
1234 | 43.8228 | 35.801 | 44.6609
1235 | 43.6225 | 36.5687 | 41.6255
1236 | 44.572 | 31.9799 | 46.8197
1237 | 43.7238 | 32.6974 | 43.2469
1238 | 42.9361 | 35.7252 | 43.6638
1239 | 45.4103 | 33.7773 | 46.5414
1240 | 47.109 | 33.9352 | 43.4016
1241 | 40.9316 | 36.3062 | 46.5386
1242 | 43.5337 | 32.946 | 43.7056
1243 | 42.6421 | 34.5062 | 40.5296
1244 | 42.903 | 36.3726 | 44.7541
1245 | 42.9827 | 36.0796 | 45.5541
1246 | 44.3257 | 33.1811 | 41.2577
1247 | 42.4457 | 32.9701 | 44.4727
1248 | 45.1554 | 33.4285 | 45.2336
1249 | 41.4851 | 34.0715 | 41.2662
1250 | 43.1154 | 34.3971 | 41.6912
1251 | 42.9904 | 32.7915 | 44.4829
1252 | 43.1523 | 35.9932 | 43.281
1253 | 41.7689 | 33.0242 | 42.0441
1254 | 44.362 | 33.6212 | 42.3481
1255 | 41.2762 | 34.9589 | 43.4813
1256 | 43.8009 | 32.8097 | 45.6508
1257 | 41.9592 | 35.6527 | 43.0606
1258 | 41.234 | 34.5632 | 44.3987
1259 | 40.3544 | 35.5853 | 45.9692
1260 | 43.5649 | 32.4334 | 42.7687
1261 | 44.4954 | 34.8805 | 43.5233
1262 | 43.5298 | 34.8089 | 44.9427
1263 | 45.3847 | 33.7948 | 41.0088
1264 | 44.807 | 36.1182 | 45.0035
1265 | 42.4785 | 36.3621 | 42.1405
1266 | 42.3089 | 36.3616 | 42.1617
1267 | 44.3544 | 35.8298 | 43.7114
1268 | 41.5895 | 35.8177 | 43.4167
1269 | 41.7469 | 32.3505 | 42.1096
1270 | 43.7288 | 32.9488 | 45.9295
1271 | 42.1504 | 34.5518 | 43.6844
1272 | 44.8041 | 34.5218 | 42.8938
1273 | 44.0743 | 36.5986 | 43.9071
1274 | 44.4853 | 32.8532 | 43.4636
1275 | 43.6613 | 33.2321 | 43.2864
1276 | 45.0192 | 34.5351 | 45.0419
1277 | 41.0914 | 33.4577 | 42.3829
1278 | 43.5832 | 35.2619 | 41.8679
1279 | 41.4569 | 35.4106 | 44.9058
1280 | 42.8685 | 35.6819 | 44.7555
1281 | 44.4982 | 34.551 | 41.651
1282 | 42.8163 | 34.1445 | 44.231
1283 | 44.2969 | 31.7822 | 42.3854
1284 | 45.5881 | 33.4286 | 44.0452
1285 | 42.0451 | 31.9726 | 44.6486
1286 | 43.0955 | 35.46 | 43.3404
1287 | 43.7516 | 34.2037 | 43.0525
1288 | 43.3242 | 35.5742 | 45.1397
1289 | 43.0347 | 37.2058 | 43.3155
1290 | 41.7111 | 34.2489 | 42.9715
1291 | 44.1535 | 34.3446 | 43.1312
1292 | 44.2198 | 33.3321 | 42.2733
1293 | 46.1777 | 34.152 | 42.779
1294 | 44.1301 | 36.7009 | 44.569
1295 | 41.7728 | 33.3726 | 43.6834
1296 | 42.9823 | 35.0942 | 45.3681
1297 | 43.7043 | 36.2892 | 44.4044
1298 | 43.3211 | 34.7012 | 45.5452
1299 | 42.3262 | 34.1306 | 44.2426
1300 | 41.2971 | 32.7919 | 41.2613
1301 | 43.7644 | 32.1382 | 41.1425
1302 | 41.7738 | 32.7522 | 43.3749
1303 | 43.8587 | 34.4369 | 42.2022
1304 | 42.069 | 34.0991 | 45.2426
1305 | 43.3224 | 33.3497 | 45.0426
1306 | 43.0417 | 34.994 | 45.0449
1307 | 43.9099 | 35.3543 | 42.7749
1308 | 45.729 | 32.896 | 43.672
1309 | 45.8559 | 33.8218 | 44.8808
1310 | 45.29 | 35.8261 | 42.0046
1311 | 45.5101 | 33.0459 | 43.9916
1312 | 43.2478 | 34.6798 | 43.6809
1313 | 44.8834 | 35.4886 | 42.2869
1314 | 42.1754 | 35.35 | 42.6985
1315 | 42.3316 | 37.7315 | 41.9893
1316 | 44.6377 | 34.9475 | 44.8945
1317 | 45.6778 | 35.5336 | 42.3391
1318 | 44.1074 | 35.6863 | 43.2261
1319 | 41.5536 | 33.2209 | 41.9876
1320 | 40.9362 | 33.5419 | 42.5941
1321 | 41.1001 | 36.5897 | 45.8034
1322 | 43.1094 | 35.0631 | 44.0217
1323 | 44.1464 | 33.2946 | 44.0766
1324 | 41.4318 | 33.7988 | 43.5435
1325 | 44.4392 | 35.6684 | 41.2309
1326 | 43.4691 | 32.2862 | 46.0652
1327 | 46.4689 | 35.3125 | 43.8718
1328 | 43.0887 | 34.2689 | 42.8686
1329 | 43.8692 | 33.7044 | 44.4309
1330 | 41.9566 | 33.3049 | 43.0155
1331 | 47.025 | 33.6728 | 43.6164
1332 | 43.6256 | 36.3627 | 44.3823
1333 | 41.8591 | 35.7488 | 43.3204
1334 | 42.6825 | 33.7908 | 44.1505
1335 | 43.643 | 35.1439 | 42.8358
1336 | 46.4463 | 33.269 | 41.5253
1337 | 40.9058 | 33.0676 | 42.5865
1338 | 41.369 | 32.8718 | 44.4638
1339 | 44.4849 | 34.6387 | 43.5798
1340 | 44.1774 | 36.0624 | 44.4648
1341 | 44.194 | 33.3278 | 43.2683
1342 | 42.5735 | 32.7768 | 42.5836
1343 | 44.3397 | 33.0014 | 42.0884
1344 | 41.7184 | 35.5112 | 44.5319
1345 | 45.3772 | 33.8735 | 44.5815
1346 | 44.641 | 33.245 | 43.9493
1347 | 42.7733 | 32.9313 | 43.044
1348 | 43.2675 | 34.4377 | 43.4709
1349 | 41.8569 | 34.3339 | 44.6098
1350 | 41.5287 | 33.7661 | 44.8196
1351 | 43.8284 | 33.9981 | 43.3181
1352 | 41.798 | 33.8712 | 43.9097
1353 | 39.9248 | 33.2429 | 41.3151
1354 | 43.8567 | 35.1682 | 45.8224
1355 | 41.5953 | 35.4817 | 42.4031
1356 | 43.8931 | 32.1107 | 44.297
1357 | 43.7475 | 32.7242 | 40.773
1358 | 44.7849 | 32.2445 | 43.8034
1359 | 40.6888 | 34.6229 | 43.9627
1360 | 41.4834 | 32.0776 | 42.7527
1361 | 45.3751 | 32.8867 | 44.6954
1362 | 44.1048 | 33.9805 | 45.9636
1363 | 41.9148 | 34.8688 | 42.2324
1364 | 39.3303 | 34.478 | 41.1144
1365 | 45.1511 | 34.0514 | 44.2516
1366 | 41.9616 | 35.3354 | 42.9103
1367 | 42.3203 | 35.9601 | 44.0855
1368 | 42.9691 | 34.4562 | 41.9334
1369 | 43.033 | 34.1179 | 44.4437
1370 | 40.0302 | 35.1627 | 42.4612
1371 | 45.8979 | 35.1599 | 43.593
1372 | 45.2883 | 35.3085 | 40.2097
1373 | 42.813 | 34.5468 | 43.3382
1374 | 45.2153 | 33.5741 | 42.2207
1375 | 41.6287 | 35.2986 | 45.16
1376 | 41.4839 | 33.4639 | 43.3439
1377 | 43.3994 | 33.6122 | 43.83
1378 | 44.3418 | 31.7848 | 43.9471
1379 | 43.8457 | 34.3401 | 45.6764
1380 | 42.8421 | 33.0366 | 42.8696
1381 | 43.35 | 35.1751 | 44.8625
1382 | 46.9124 | 32.1633 | 43.1296
1383 | 41.5659 | 35.7233 | 44.3976
1384 | 42.3401 | 33.8976 | 42.4587
1385 | 42.5432 | 34.0243 | 44.5061
1386 | 41.5124 | 33.8368 | 44.255
1387 | 43.6123 | 34.8314 | 43.1362
1388 | 44.7784 | 33.8638 | 39.4231
1389 | 40.927 | 35.2715 | 41.6816
1390 | 42.6231 | 33.1795 | 44.0086
1391 | 41.7503 | 32.6634 | 43.9176
1392 | 45.2668 | 35.8471 | 43.6542
1393 | 45.6912 | 33.4373 | 44.1253
1394 | 43.0372 | 33.7655 | 41.5579
1395 | 45.9106 | 34.8351 | 41.9366
1396 | 44.8247 | 33.6058 | 46.3084
1397 | 41.5141 | 36.9477 | 43.6239
1398 | 43.6835 | 34.7413 | 45.9918
1399 | 40.5899 | 32.7771 | 41.4649
1400 | 42.9547 | 33.4539 | 43.2352
1401 | 43.9685 | 35.8713 | 43.8448
1402 | 40.3327 | 35.7291 | 44.1096
1403 | 41.5976 | 36.7008 | 44.2413
1404 | 43.0135 | 35.3337 | 43.5689
1405 | 46.093 | 33.5754 | 39.5971
1406 | 41.7062 | 36.3417 | 44.7801
1407 | 42.2919 | 35.8436 | 41.8629
1408 | 38.5986 | 32.568 | 41.3268
1409 | 44.2617 | 32.1571 | 43.7657
1410 | 43.7469 | 34.0857 | 46.1523
1411 | 43.0169 | 34.6565 | 46.1654
1412 | 43.5542 | 32.6046 | 43.4477
1413 | 42.3924 | 34.8375 | 42.9786
1414 | 42.2952 | 36.6586 | 43.0525
1415 | 46.1981 | 34.1538 | 43.6741
1416 | 42.2218 | 32.5315 | 42.4859
1417 | 41.2159 | 32.7044 | 42.4822
1418 | 43.8106 | 35.9005 | 42.4825
1419 | 43.6616 | 33.616 | 43.6868
1420 | 43.8434 | 33.3169 | 40.9472
1421 | 44.9365 | 34.1252 | 43.562
1422 | 42.5502 | 34.6129 | 46.4215
1423 | 44.1823 | 33.5026 | 44.3758
1424 | 41.9141 | 34.1316 | 42.9389
1425 | 45.9976 | 35.1163 | 43.9908
1426 | 44.7446 | 33.5605 | 43.8815
1427 | 43.0982 | 34.6645 | 43.3423
1428 | 44.116 | 34.7568 | 45.6819
1429 | 45.3882 | 32.8782 | 45.6273
1430 | 42.3176 | 35.2845 | 43.3715
1431 | 46.6677 | 34.9793 | 44.8326
1432 | 43.479 | 33.6579 | 42.9621
1433 | 44.2076 | 35.1324 | 42.6998
1434 | 42.386 | 34.6281 | 42.365
1435 | 46.1436 | 32.478 | 44.1002
1436 | 42.1447 | 32.7132 | 43.5797
1437 | 42.546 | 34.2466 | 44.3818
1438 | 40.9662 | 34.0796 | 43.3159
1439 | 42.9497 | 34.956 | 43.4726
1440 | 45.0287 | 35.6777 | 46.1841
1441 | 44.571 | 35.409 | 43.171
1442 | 42.5837 | 32.8872 | 42.3001
1443 | 43.6431 | 34.4992 | 43.5208
1444 | 42.3841 | 34.5833 | 45.283
1445 | 43.9626 | 35.2001 | 42.851
1446 | 46.2415 | 35.1745 | 44.5862
1447 | 42.3023 | 35.9806 | 43.944
1448 | 45.2417 | 36.5278 | 42.7588
1449 | 45.9208 | 34.5159 | 40.7217
1450 | 47.0495 | 31.7379 | 41.9362
1451 | 42.8979 | 33.9713 | 41.1513
1452 | 42.8951 | 32.3912 | 44.9717
1453 | 45.2399 | 36.2495 | 44.9623
1454 | 44.6127 | 35.1448 | 45.5064
1455 | 44.2424 | 36.2426 | 45.0214
1456 | 42.3923 | 33.4332 | 43.5148
1457 | 44.8349 | 33.7874 | 41.9853
1458 | 42.0311 | 33.4408 | 43.7054
1459 | 45.1313 | 36.3172 | 42.7119
1460 | 42.7633 | 33.8148 | 41.512
1461 | 41.8362 | 34.4272 | 42.6698
1462 | 45.1707 | 31.316 | 43.8783
1463 | 44.7247 | 33.1434 | 45.6541
1464 | 42.4312 | 32.6205 | 45.7087
1465 | 44.5678 | 34.6119 | 46.1919
1466 | 43.8457 | 35.4454 | 42.3777
1467 | 45.0106 | 32.5631 | 44.4273
1468 | 42.9439 | 34.0155 | 44.3654
1469 | 41.2167 | 32.9299 | 41.8225
1470 | 42.5005 | 32.7893 | 44.6999
1471 | 45.4668 | 31.9282 | 42.8522
1472 | 43.3889 | 34.0271 | 45.3538
1473 | 44.2563 | 33.9393 | 43.0986
1474 | 44.3122 | 34.8201 | 43.5402
1475 | 45.5098 | 34.8516 | 41.6118
1476 | 44.2945 | 33.5898 | 42.2046
1477 | 44.4614 | 33.9866 | 42.7615
1478 | 42.1533 | 33.8137 | 43.4297
1479 | 43.2422 | 34.0064 | 41.8039
1480 | 42.5785 | 36.1851 | 45.3661
1481 | 42.2216 | 35.1828 | 42.6763
1482 | 43.4325 | 35.3789 | 42.8815
1483 | 43.3763 | 32.5832 | 43.4425
1484 | 41.353 | 33.6101 | 43.0973
1485 | 46.0412 | 35.0426 | 43.3179
1486 | 43.8331 | 34.3263 | 46.4437
1487 | 41.4241 | 32.818 | 41.865
1488 | 42.8727 | 33.5416 | 44.7336
1489 | 43.3057 | 35.1616 | 43.0121
1490 | 43.3112 | 32.7949 | 38.4712
1491 | 41.9727 | 35.4062 | 41.0053
1492 | 42.7148 | 33.5045 | 44.9675
1493 | 43.2912 | 36.6232 | 44.6299
1494 | 43.0735 | 33.0572 | 42.4168
1495 | 44.4527 | 34.2675 | 44.3852
1496 | 44.9033 | 34.7649 | 42.0223
1497 | 43.1784 | 33.0618 | 44.1423
1498 | 42.7881 | 33.2098 | 42.5239
1499 | 44.6661 | 32.8422 | 41.9401
1500 | 43.1107 | 35.1702 | 44.3893
1501 | 42.6576 | 31.0442 | 43.2025
1502 | 45.3606 | 33.7151 | 43.2848
1503 | 41.504 | 33.8125 | 44.4676
1504 | 42.4188 | 34.4001 | 44.9337
1505 | 43.3038 | 33.7278 | 44.3051
1506 | 41.989 | 35.5269 | 44.0291
1507 | 45.5534 | 34.39 | 42.2752
1508 | 46.1191 | 32.1591 | 41.8333
1509 | 43.8816 | 33.3679 | 42.2263
1510 | 46.0193 | 33.9822 | 44.9859
1511 | 43.8282 | 36.908 | 41.5979
1512 | 40.1808 | 36.3412 | 44.9894
1513 | 44.1722 | 33.1231 | 44.0573
1514 | 44.9235 | 34.3187 | 43.1604
1515 | 41.4838 | 34.1956 | 43.8574
1516 | 44.7108 | 35.1544 | 43.6
1517 | 43.1468 | 36.0015 | 40.8659
1518 | 45.6507 | 33.5976 | 41.755
1519 | 43.8275 | 35.0532 | 44.2775
1520 | 40.0927 | 32.9777 | 40.8122
1521 | 39.8675 | 34.8348 | 44.4737
1522 | 44.5923 | 33.0307 | 39.6976
1523 | 41.2791 | 35.8303 | 43.5578
1524 | 43.1763 | 35.457 | 42.3414
1525 | 44.249 | 34.385 | 45.9164
1526 | 42.182 | 33.5484 | 44.6048
1527 | 41.6341 | 35.5623 | 41.6397
1528 | 43.0806 | 34.4997 | 42.9013
1529 | 43.1104 | 34.0457 | 44.3668
1530 | 45.2597 | 35.3599 | 41.4594
1531 | 42.1019 | 35.2121 | 41.7616
1532 | 44.1306 | 35.6624 | 44.8719
1533 | 43.9159 | 33.8944 | 44.5617
1534 | 45.0195 | 34.1549 | 44.7226
1535 | 44.469 | 35.0565 | 44.4514
1536 | 43.8588 | 33.5174 | 42.5674
1537 | 43.42 | 34.08 | 45.6599
1538 | 42.934 | 35.1738 | 45.3872
1539 | 44.1291 | 34.604 | 41.9603
1540 | 42.6391 | 34.0351 | 44.0451
1541 | 44.916 | 35.1726 | 42.2732
1542 | 43.1292 | 34.8 | 43.2189
1543 | 42.5256 | 33.4356 | 43.9089
1544 | 44.9704 | 34.4633 | 41.1235
1545 | 43.3884 | 35.4171 | 42.205
1546 | 40.1574 | 35.6364 | 42.6657
1547 | 46.1508 | 36.3808 | 41.359
1548 | 46.5989 | 34.493 | 42.3814
1549 | 46.9179 | 32.4093 | 44.5249
1550 | 44.5331 | 33.6086 | 43.0923
1551 | 44.5317 | 35.1455 | 43.5892
1552 | 44.4631 | 34.2067 | 45.2607
1553 | 43.9237 | 33.9834 | 46.182
1554 | 45.4648 | 32.217 | 44.8442
1555 | 42.7314 | 36.8334 | 43.6953
1556 | 43.2942 | 36.2934 | 42.2883
1557 | 38.7912 | 35.0318 | 41.6623
1558 | 42.3544 | 35.8558 | 43.1057
1559 | 42.2649 | 34.733 | 43.6138
1560 | 43.0495 | 35.8943 | 43.7131
1561 | 43.5973 | 35.0753 | 43.2036
1562 | 43.4401 | 35.276 | 42.0681
1563 | 44.6943 | 33.6844 | 38.3072
1564 | 46.6811 | 36.0919 | 42.9885
1565 | 44.4971 | 34.8818 | 42.9986
1566 | 46.0946 | 36.1642 | 41.5185
1567 | 43.384 | 30.6037 | 42.1312
1568 | 42.1789 | 34.6476 | 41.6595
1569 | 43.1955 | 34.2644 | 41.4384
1570 | 41.0843 | 33.4754 | 46.6262
1571 | 41.9634 | 31.1582 | 46.1278
1572 | 45.2907 | 34.9056 | 45.1578
1573 | 40.1197 | 33.0241 | 42.61
1574 | 41.8989 | 32.9225 | 45.3282
1575 | 43.1397 | 35.9888 | 42.18
1576 | 46.8917 | 34.855 | 42.6585
1577 | 44.0413 | 32.0676 | 43.1753
1578 | 43.8741 | 34.7346 | 43.9127
1579 | 45.9142 | 35.1683 | 44.1607
1580 | 42.352 | 37.9655 | 43.442
1581 | 44.8917 | 32.0453 | 43.1383
1582 | 41.5817 | 34.6312 | 42.8043
1583 | 43.9954 | 35.55 | 45.5267
1584 | 44.1744 | 34.4671 | 43.4772
1585 | 43.8557 | 32.4725 | 44.0642
1586 | 44.9938 | 33.7405 | 42.6361
1587 | 38.6999 | 31.1975 | 42.5391
1588 | 44.6515 | 34.924 | 41.679
1589 | 42.9238 | 31.5898 | 40.198
1590 | 45.6452 | 33.5028 | 44.4495
1591 | 42.5344 | 34.4339 | 44.4462
1592 | 42.9735 | 33.5435 | 44.4882
1593 | 43.2542 | 34.7341 | 42.9598
1594 | 42.6425 | 33.0971 | 44.4808
1595 | 44.0329 | 32.9275 | 44.7421
1596 | 42.7577 | 32.7042 | 42.0636
1597 | 43.1204 | 35.721 | 42.9329
1598 | 43.4802 | 35.8642 | 42.9715
1599 | 43.4248 | 33.7624 | 45.6077
1600 | 41.7128 | 34.3963 | 42.5748
1601 | 44.0356 | 33.9474 | 41.0121
1602 | 43.3374 | 33.5904 | 44.5054
1603 | 43.5271 | 33.8948 | 45.108
1604 | 41.8895 | 37.8562 | 39.4719
1605 | 41.3456 | 34.0964 | 43.0133
1606 | 42.7117 | 34.8789 | 43.8135
1607 | 43.4136 | 35.2384 | 44.3399
1608 | 38.415 | 34.9988 | 44.2497
1609 | 40.9693 | 33.3499 | 43.8268
1610 | 42.475 | 34.237 | 42.5572
1611 | 40.7507 | 34.8399 | 44.1406
1612 | 42.7432 | 34.2803 | 41.5202
1613 | 42.8182 | 32.0284 | 42.0989
1614 | 42.0213 | 33.9963 | 43.0725
1615 | 44.3865 | 34.6675 | 44.2287
1616 | 42.1616 | 34.5772 | 43.3695
1617 | 42.5573 | 32.789 | 45.0028
1618 | 44.2823 | 34.0409 | 40.5878
1619 | 45.5505 | 33.1539 | 43.6561
1620 | 45.8188 | 34.2588 | 42.8426
1621 | 42.3749 | 35.099 | 43.8695
1622 | 43.4896 | 34.4978 | 44.1493
1623 | 44.296 | 33.6751 | 43.7584
1624 | 43.8565 | 33.699 | 43.3272
1625 | 43.6794 | 33.417 | 43.9003
1626 | 42.756 | 35.5036 | 40.0352
1627 | 42.8292 | 31.8996 | 41.5671
1628 | 41.2004 | 33.4128 | 40.8269
1629 | 42.4443 | 36.6855 | 43.4053
1630 | 41.0248 | 32.8665 | 43.7062
1631 | 43.6643 | 34.3899 | 43.9396
1632 | 45.3208 | 36.9055 | 44.8318
1633 | 43.0564 | 35.0754 | 42.9373
1634 | 42.0823 | 34.8831 | 44.4998
1635 | 46.524 | 33.4334 | 45.0302
1636 | 44.1691 | 34.3165 | 42.6369
1637 | 42.0569 | 34.9897 | 46.5161
1638 | 43.0213 | 32.6876 | 40.9785
1639 | 41.4732 | 34.6973 | 42.7051
1640 | 42.6551 | 36.7822 | 45.4715
1641 | 43.5859 | 34.6479 | 41.0798
1642 | 39.1425 | 35.3343 | 44.1802
1643 | 44.8271 | 32.1554 | 45.8493
1644 | 45.7998 | 35.849 | 45.3675
1645 | 43.2685 | 32.7422 | 44.0236
1646 | 42.9163 | 33.7728 | 41.6102
1647 | 43.0679 | 33.9925 | 40.0015
1648 | 44.7377 | 33.2081 | 43.0556
1649 | 43.7375 | 31.8911 | 42.9042
1650 | 41.0473 | 34.291 | 42.296
1651 | 43.3231 | 35.2809 | 43.7742
1652 | 47.6685 | 33.7989 | 44.7427
1653 | 42.7541 | 33.1125 | 42.4944
1654 | 40.7447 | 31.1459 | 41.4404
1655 | 41.2502 | 33.0627 | 43.8227
1656 | 42.6763 | 33.5878 | 42.1623
1657 | 44.0881 | 37.2598 | 43.8736
1658 | 43.102 | 36.3771 | 43.1717
1659 | 44.617 | 34.0551 | 44.3652
1660 | 45.0209 | 37.2608 | 43.3124
1661 | 41.4245 | 35.4508 | 44.2726
1662 | 42.64 | 32.1204 | 43.5047
1663 | 42.8748 | 33.8936 | 45.8347
1664 | 43.7043 | 35.8805 | 44.3566
1665 | 43.5359 | 34.9947 | 43.5642
1666 | 45.2107 | 33.4704 | 42.7722
1667 | 41.1657 | 35.1052 | 39.9749
1668 | 44.4524 | 32.9325 | 44.2639
1669 | 43.667 | 36.0378 | 42.1552
1670 | 40.801 | 34.2901 | 44.5163
1671 | 42.0143 | 33.4889 | 42.4777
1672 | 45.8125 | 34.4328 | 43.4518
1673 | 41.5691 | 35.8117 | 41.7092
1674 | 43.2804 | 34.2796 | 43.2563
1675 | 44.039 | 34.1949 | 46.8481
1676 | 42.229 | 35.3652 | 42.0514
1677 | 41.4355 | 34.7639 | 42.4347
1678 | 43.1056 | 35.235 | 44.7615
1679 | 43.0429 | 34.4138 | 44.7068
1680 | 44.2293 | 35.1493 | 43.8989
1681 | 44.0945 | 31.5427 | 41.753
1682 | 43.1949 | 32.9545 | 41.5534
1683 | 40.2378 | 34.2847 | 41.9765
1684 | 43.4209 | 34.1346 | 43.3838
1685 | 42.561 | 37.1048 | 43.4179
1686 | 42.6835 | 36.4389 | 46.0225
1687 | 42.099 | 33.8695 | 44.6971
1688 | 43.288 | 34.8076 | 44.1142
1689 | 41.3183 | 35.4609 | 42.6395
1690 | 43.3398 | 33.8419 | 47.9181
1691 | 45.8245 | 37.0682 | 40.5568
1692 | 42.1572 | 35.1168 | 43.9601
1693 | 42.4614 | 34.5152 | 41.9654
1694 | 43.9391 | 36.1202 | 42.9685
1695 | 38.6318 | 34.9028 | 42.0173
1696 | 40.9874 | 33.7836 | 43.6416
1697 | 44.2637 | 33.8981 | 44.5232
1698 | 42.7196 | 32.5356 | 44.7202
1699 | 41.8342 | 32.3955 | 44.9649
1700 | 43.4143 | 36.9394 | 43.0677
1701 | 43.5921 | 33.2249 | 43.473
1702 | 43.0474 | 34.8687 | 41.3375
1703 | 41.878 | 32.2019 | 46.4341
1704 | 44.1603 | 34.9053 | 41.0283
1705 | 41.1628 | 33.7639 | 42.7666
1706 | 43.7684 | 32.4981 | 43.1998
1707 | 41.2677 | 32.67 | 41.0659
1708 | 45.7338 | 31.3783 | 44.0362
1709 | 42.5937 | 33.7507 | 44.1487
1710 | 45.5114 | 34.0667 | 43.6725
1711 | 42.3685 | 34.3312 | 42.2844
1712 | 43.2694 | 36.3051 | 43.749
1713 | 44.9121 | 35.3377 | 43.2547
1714 | 44.6828 | 37.1561 | 44.7464
1715 | 42.1206 | 31.638 | 43.4092
1716 | 45.6928 | 36.8805 | 43.2403
1717 | 42.89 | 33.2084 | 41.3087
1718 | 43.5668 | 32.8386 | 45.2542
1719 | 42.1086 | 34.6112 | 43.623
1720 | 41.7622 | 32.8374 | 44.1432
1721 | 45.4965 | 33.0547 | 46.6031
1722 | 43.8228 | 35.4923 | 41.1774
1723 | 42.5453 | 35.1105 | 42.0412
1724 | 42.1432 | 34.7171 | 42.3983
1725 | 41.7759 | 33.9259 | 41.3434
1726 | 44.7379 | 33.0556 | 42.2742
1727 | 42.854 | 34.7607 | 42.8808
1728 | 43.3844 | 34.514 | 43.53
1729 | 41.2575 | 34.7121 | 45.7796
1730 | 42.0212 | 31.7751 | 44.9011
1731 | 44.1368 | 33.8961 | 43.5845
1732 | 43.1999 | 34.5718 | 45.642
1733 | 42.3593 | 34.6991 | 41.2742
1734 | 44.2871 | 35.7913 | 44.425
1735 | 44.654 | 34.3854 | 44.6233
1736 | 45.1384 | 33.8696 | 43.9833
1737 | 42.8598 | 33.7517 | 45.4603
1738 | 41.7306 | 30.9735 | 42.6678
1739 | 42.0813 | 34.7716 | 43.4071
1740 | 44.4449 | 34.3836 | 43.4859
1741 | 43.5899 | 34.2258 | 40.4096
1742 | 41.9079 | 32.8992 | 42.5985
1743 | 41.1565 | 34.4808 | 45.7346
1744 | 41.6439 | 35.3337 | 44.8263
1745 | 43.5568 | 33.316 | 43.3365
1746 | 43.8904 | 34.5046 | 43.5183
1747 | 45.391 | 35.949 | 44.4795
1748 | 44.3429 | 32.5856 | 40.4374
1749 | 41.9308 | 34.6546 | 41.5247
1750 | 42.3235 | 33.4087 | 44.0287
1751 | 41.0114 | 34.7933 | 43.1294
1752 | 43.3442 | 32.4991 | 43.4876
1753 | 42.8703 | 34.8528 | 43.7621
1754 | 40.4974 | 35.3465 | 45.6276
1755 | 45.9492 | 34.2709 | 43.7119
1756 | 40.2397 | 32.4924 | 45.8927
1757 | 45.1534 | 32.6693 | 44.9017
1758 | 44.4398 | 34.1345 | 42.5628
1759 | 45.1766 | 33.3409 | 41.5826
1760 | 47.1381 | 33.0641 | 43.3065
1761 | 43.9473 | 34.8656 | 45.0852
1762 | 42.5805 | 31.9726 | 42.6167
1763 | 43.0448 | 34.0349 | 44.9476
1764 | 43.7866 | 34.8014 | 42.3224
1765 | 43.0925 | 33.108 | 45.4722
1766 | 44.5541 | 35.6131 | 43.9519
1767 | 42.6544 | 33.6678 | 44.7822
1768 | 41.4273 | 32.2888 | 40.8
1769 | 42.9555 | 36.1541 | 42.3699
1770 | 41.0065 | 34.9486 | 43.0112
1771 | 43.3845 | 33.3708 | 43.2859
1772 | 42.3239 | 35.2534 | 42.7531
1773 | 42.6336 | 33.4157 | 42.0199
1774 | 40.7017 | 35.1699 | 43.4897
1775 | 43.5818 | 34.1814 | 41.8882
1776 | 42.418 | 34.7532 | 41.2126
1777 | 43.6153 | 33.1124 | 44.7832
1778 | 43.6579 | 32.7565 | 43.9228
1779 | 45.9649 | 34.0841 | 41.8151
1780 | 43.7423 | 34.767 | 43.6013
1781 | 39.913 | 36.8026 | 41.4009
1782 | 46.3837 | 34.5269 | 44.8173
1783 | 43.084 | 34.9179 | 41.6242
1784 | 42.9994 | 35.0284 | 44.8414
1785 | 43.2974 | 33.7767 | 44.9022
1786 | 42.2557 | 34.033 | 44.7352
1787 | 45.0317 | 35.2265 | 43.284
1788 | 42.8346 | 34.7852 | 44.2825
1789 | 46.3105 | 33.5657 | 39.894
1790 | 43.2417 | 35.5496 | 43.3513
1791 | 40.234 | 34.4018 | 45.7874
1792 | 42.4265 | 34.048 | 41.3281
1793 | 42.4605 | 34.6426 | 44.2075
1794 | 45.7228 | 34.6095 | 43.0405
1795 | 44.8584 | 34.847 | 39.0794
1796 | 44.9141 | 32.6342 | 42.763
1797 | 40.5621 | 33.3838 | 44.338
1798 | 44.3296 | 34.3853 | 44.3612
1799 | 41.3762 | 33.8633 | 45.4001
1800 | 43.8208 | 33.321 | 43.4668
1801 | 42.6175 | 32.6441 | 42.0724
1802 | 44.6683 | 34.1136 | 42.1937
1803 | 44.5875 | 34.7598 | 40.8886
1804 | 43.2728 | 34.532 | 46.4227
1805 | 43.2829 | 34.0512 | 43.6078
1806 | 41.4698 | 33.7089 | 42.9074
1807 | 42.6569 | 33.4075 | 44.5116
1808 | 40.7266 | 34.1211 | 45.6588
1809 | 43.2551 | 33.8975 | 43.8903
1810 | 41.7894 | 36.2003 | 45.244
1811 | 43.4135 | 34.4538 | 42.6052
1812 | 42.5096 | 32.9833 | 43.6976
1813 | 40.3242 | 32.21 | 46.1494
1814 | 44.3462 | 32.9491 | 41.3271
1815 | 42.2096 | 32.047 | 44.1778
1816 | 46.0736 | 33.8563 | 42.3834
1817 | 45.3213 | 34.264 | 45.1013
1818 | 41.7971 | 33.2757 | 43.533
1819 | 43.6091 | 33.9952 | 45.0335
1820 | 44.7864 | 33.8353 | 44.4494
1821 | 42.6717 | 36.0198 | 43.4902
1822 | 44.8834 | 34.9837 | 43.4688
1823 | 42.0099 | 35.1858 | 40.7474
1824 | 41.6948 | 33.1622 | 43.8806
1825 | 41.7203 | 35.6132 | 42.3178
1826 | 42.6787 | 35.1017 | 41.3221
1827 | 43.0283 | 32.7411 | 42.8861
1828 | 44.1646 | 33.1507 | 45.2777
1829 | 43.1283 | 34.9148 | 43.0804
1830 | 45.1318 | 34.5544 | 43.2213
1831 | 45.6115 | 34.0083 | 42.5952
1832 | 42.3646 | 35.3389 | 40.9198
1833 | 45.2422 | 34.665 | 44.1043
1834 | 43.4599 | 31.9243 | 42.9767
1835 | 41.2586 | 35.0221 | 44.1275
1836 | 43.5974 | 36.0927 | 42.6016
1837 | 44.2675 | 34.8395 | 44.7631
1838 | 43.7296 | 34.2613 | 44.0742
1839 | 43.6362 | 32.6932 | 44.5005
1840 | 41.2759 | 33.9706 | 43.758
1841 | 45.226 | 32.4708 | 45.7307
1842 | 43.3043 | 34.1671 | 42.3627
1843 | 45.7903 | 34.914 | 41.3898
1844 | 45.4852 | 32.9965 | 44.7527
1845 | 45.3296 | 33.2453 | 40.1562
1846 | 42.2442 | 33.8875 | 45.7124
1847 | 42.3684 | 30.7901 | 41.3503
1848 | 44.576 | 34.5839 | 43.5581
1849 | 42.1003 | 36.3608 | 43.8109
1850 | 44.5467 | 33.8059 | 42.6371
1851 | 43.9665 | 34.7388 | 42.5058
1852 | 42.4588 | 34.9788 | 44.0355
1853 | 44.5423 | 34.8837 | 44.241
1854 | 42.8263 | 35.7309 | 41.3374
1855 | 42.4119 | 32.2436 | 44.8339
1856 | 45.7801 | 35.0528 | 40.9758
1857 | 42.671 | 35.221 | 43.3978
1858 | 42.8362 | 34.0437 | 42.8702
1859 | 43.1286 | 33.1547 | 43.6056
1860 | 47.2866 | 34.5595 | 44.3111
1861 | 43.818 | 34.6514 | 44.5029
1862 | 40.9977 | 34.2959 | 42.5515
1863 | 42.2019 | 34.0273 | 42.9259
1864 | 45.7031 | 33.8414 | 46.5112
1865 | 41.5659 | 33.5657 | 43.7716
1866 | 40.8987 | 34.6253 | 42.5212
1867 | 40.3636 | 32.1755 | 43.476
1868 | 42.4225 | 34.3995 | 45.4533
1869 | 43.9024 | 34.0235 | 41.9954
1870 | 42.6604 | 34.5102 | 46.3842
1871 | 43.9386 | 36.1977 | 42.7794
1872 | 43.5061 | 32.7361 | 43.4992
1873 | 43.6525 | 35.5598 | 40.3613
1874 | 42.9728 | 34.2439 | 46.488
1875 | 41.7756 | 35.6404 | 44.9094
1876 | 40.864 | 35.266 | 47.4932
1877 | 43.0553 | 33.6371 | 43.6354
1878 | 41.9722 | 33.3747 | 45.2167
1879 | 44.1057 | 34.1778 | 44.7946
1880 | 43.3276 | 34.5677 | 42.0842
1881 | 45.8396 | 32.9999 | 45.9017
1882 | 43.1203 | 33.5008 | 41.7043
1883 | 41.7739 | 32.2573 | 43.1859
1884 | 42.7968 | 34.799 | 43.2974
1885 | 45.0546 | 34.0538 | 45.9469
1886 | 42.3175 | 33.9556 | 41.8869
1887 | 43.9903 | 35.2146 | 44.1307
1888 | 43.8089 | 33.0266 | 46.2446
1889 | 45.1625 | 33.2486 | 43.6129
1890 | 39.7749 | 32.3466 | 44.3245
1891 | 44.3024 | 34.1857 | 43.5771
1892 | 44.5528 | 35.5267 | 43.2146
1893 | 43.5208 | 33.5167 | 41.584
1894 | 43.8841 | 35.9773 | 43.4209
1895 | 43.2057 | 34.283 | 45.5891
1896 | 44.6625 | 34.2043 | 42.4667
1897 | 40.0846 | 35.4164 | 42.9001
1898 | 42.0341 | 35.5814 | 45.1437
1899 | 45.8039 | 35.9427 | 41.27
1900 | 44.0824 | 33.813 | 44.877
1901 | 42.5034 | 36.2179 | 44.4936
1902 | 42.0308 | 33.7952 | 46.7583
1903 | 45.2486 | 34.629 | 39.8956
1904 | 42.986 | 33.3334 | 42.7857
1905 | 43.8574 | 34.1945 | 40.742
1906 | 42.0904 | 35.1682 | 42.713
1907 | 42.1792 | 36.2667 | 43.1865
1908 | 41.9885 | 34.8674 | 42.9391
1909 | 42.2269 | 37.1713 | 41.9141
1910 | 42.6359 | 34.4409 | 42.1444
1911 | 41.4169 | 32.0416 | 41.3264
1912 | 42.4116 | 34.9414 | 43.2449
1913 | 42.9357 | 35.6866 | 42.3203
1914 | 44.5486 | 33.7369 | 45.2061
1915 | 41.7857 | 34.2197 | 39.4176
1916 | 44.3436 | 33.6542 | 43.9804
1917 | 41.0974 | 35.528 | 38.5214
1918 | 42.2518 | 36.4731 | 43.7386
1919 | 45.1332 | 35.4952 | 45.6701
1920 | 43.1842 | 35.3474 | 43.8175
1921 | 41.8625 | 35.7268 | 43.2407
1922 | 44.7499 | 33.4781 | 42.8638
1923 | 42.0312 | 36.1417 | 43.6921
1924 | 42.1986 | 35.1813 | 42.4892
1925 | 41.6485 | 31.4065 | 44.3553
1926 | 42.5325 | 32.9996 | 40.2286
1927 | 43.3164 | 34.0222 | 41.7668
1928 | 43.6805 | 35.0754 | 41.4775
1929 | 44.9595 | 35.7213 | 44.8751
1930 | 46.6206 | 32.9594 | 42.9761
1931 | 41.5977 | 32.5036 | 43.1179
1932 | 45.4819 | 32.9249 | 41.2504
1933 | 44.9723 | 36.6424 | 46.1967
1934 | 42.5406 | 33.406 | 41.399
1935 | 44.219 | 33.421 | 43.5081
1936 | 41.3654 | 33.9294 | 44.2753
1937 | 44.1677 | 34.7066 | 43.723
1938 | 44.1497 | 35.2862 | 41.974
1939 | 44.4474 | 33.8444 | 41.0709
1940 | 43.6587 | 36.3064 | 44.7348
1941 | 43.4381 | 34.8388 | 44.7215
1942 | 43.4247 | 31.2803 | 44.9076
1943 | 44.2648 | 32.5504 | 44.6286
1944 | 44.9541 | 33.8429 | 43.0642
1945 | 43.2549 | 33.5558 | 44.443
1946 | 45.859 | 37.1296 | 43.4111
1947 | 41.3342 | 30.8739 | 42.2469
1948 | 43.5121 | 33.6748 | 42.3573
1949 | 43.3613 | 33.1858 | 40.2498
1950 | 43.6594 | 32.489 | 39.8285
1951 | 42.9928 | 33.1892 | 43.6786
1952 | 40.7406 | 33.3845 | 45.0757
1953 | 42.6306 | 35.3522 | 45.1922
1954 | 42.2899 | 35.3977 | 44.8359
1955 | 41.5732 | 34.2124 | 43.0101
1956 | 46.3897 | 31.6427 | 43.1041
1957 | 42.7934 | 34.4773 | 41.9487
1958 | 41.7285 | 33.0914 | 42.4814
1959 | 41.7063 | 35.0486 | 42.5501
1960 | 46.152 | 35.4003 | 43.6932
1961 | 43.6273 | 33.6796 | 43.9577
1962 | 45.8179 | 34.9358 | 42.5094
1963 | 42.654 | 35.8502 | 42.1732
1964 | 44.3944 | 33.06 | 42.9182
1965 | 40.423 | 32.2225 | 43.1038
1966 | 44.3742 | 36.5844 | 43.8404
1967 | 42.0243 | 34.5844 | 41.3704
1968 | 46.1169 | 35.1676 | 42.3152
1969 | 42.1175 | 33.0185 | 42.3499
1970 | 45.2437 | 33.9973 | 42.276
1971 | 44.126 | 35.4012 | 43.8037
1972 | 44.1746 | 34.245 | 41.6606
1973 | 43.8019 | 34.1956 | 42.8112
1974 | 42.794 | 33.4043 | 44.3822
1975 | 46.0851 | 35.5668 | 43.8236
1976 | 44.435 | 35.7071 | 40.4525
1977 | 42.8335 | 36.9788 | 45.1177
1978 | 43.2411 | 35.6007 | 42.6637
1979 | 43.0049 | 34.7394 | 42.5911
1980 | 44.725 | 33.3268 | 43.8332
1981 | 43.0634 | 35.7163 | 44.797
1982 | 43.0432 | 34.2927 | 44.5833
1983 | 42.1218 | 34.4706 | 43.7886
1984 | 45.2518 | 36.109 | 42.6572
1985 | 43.5208 | 35.3968 | 43.1913
1986 | 41.1332 | 35.2314 | 43.9606
1987 | 42.0518 | 32.7608 | 42.0273
1988 | 45.0558 | 36.3559 | 44.452
1989 | 41.0402 | 34.5287 | 42.2012
1990 | 43.1471 | 34.9923 | 42.4947
1991 | 45.5146 | 36.619 | 43.5998
1992 | 41.1063 | 35.0113 | 41.0567
1993 | 44.6092 | 34.3583 | 45.0307
1994 | 43.9798 | 35.6122 | 45.2983
1995 | 44.9289 | 33.0248 | 43.6962
1996 | 43.7854 | 35.7375 | 41.8837
1997 | 46.3421 | 35.3609 | 44.0628
1998 | 42.005 | 33.4975 | 41.6709
1999 | 45.206 | 32.6881 | 45.0132
2000 | 43.0368 | 34.419 | 43.9179
2001 | 43.9274 | 33.8743 | 43.9457
2002 | 42.0072 | 35.5237 | 43.4813
2003 | 43.0179 | 34.2341 | 44.0992
2004 | 42.0669 | 33.8515 | 41.031
2005 | 42.0366 | 34.3456 | 41.0375
2006 | 42.2176 | 34.3118 | 41.7825
2007 | 46.5 | 32.9726 | 44.2207
2008 | 44.6047 | 32.3458 | 44.1655
2009 | 43.6695 | 32.6588 | 45.433
2010 | 41.5593 | 33.2404 | 43.8581
2011 | 41.4804 | 33.5934 | 44.8239
2012 | 41.7375 | 35.5521 | 41.9637
2013 | 41.1661 | 34.49 | 42.9309
2014 | 41.7273 | 33.008 | 43.4203
2015 | 43.2179 | 34.1348 | 43.1494
2016 | 44.4186 | 34.5427 | 41.6011
2017 | 42.4935 | 36.0446 | 45.8501
2018 | 41.7759 | 37.2549 | 42.6177
2019 | 45.8259 | 35.2553 | 43.3892
2020 | 40.7345 | 35.1213 | 44.2573
2021 | 41.2601 | 33.7701 | 42.7225
2022 | 40.6888 | 36.8057 | 44.7211
2023 | 40.6693 | 34.2151 | 42.1923
2024 | 41.7581 | 32.8993 | 40.514
2025 | 45.7144 | 34.398 | 42.8951
2026 | 43.076 | 31.5146 | 43.3605
2027 | 41.2794 | 30.8011 | 44.8128
2028 | 44.1173 | 33.0181 | 44.5788
2029 | 41.9795 | 35.1377 | 42.3269
2030 | 42.936 | 32.8084 | 44.5749
2031 | 46.538 | 32.6775 | 44.724
2032 | 44.3769 | 33.5777 | 44.6926
2033 | 43.1431 | 34.795 | 42.4375
2034 | 49.1095 | 34.8611 | 43.133
2035 | 42.7358 | 35.7555 | 43.0214
2036 | 38.1726 | 34.297 | 44.0969
2037 | 45.2268 | 33.2351 | 42.7418
2038 | 43.9267 | 34.7729 | 44.0767
2039 | 41.9119 | 32.0602 | 42.8283
2040 | 45.01 | 35.242 | 44.0436
2041 | 47.9307 | 33.5823 | 41.0012
2042 | 42.8243 | 32.6686 | 43.853
2043 | 46.3045 | 35.2274 | 38.7387
2044 | 42.6234 | 36.3817 | 43.3813
2045 | 43.0649 | 34.5428 | 43.9862
2046 | 44.7165 | 34.2214 | 42.4768
2047 | 44.3613 | 32.4104 | 43.767
2048 | 42.8184 | 32.7786 | 42.2525
2049 | 43.7389 | 33.8775 | 44.6598
2050 | 45.914 | 33.4812 | 44.3592
2051 | 44.5222 | 34.2696 | 42.9051
2052 | 44.3981 | 32.9354 | 46.4115
2053 | 41.4778 | 33.4758 | 41.7926
2054 | 42.2422 | 33.9635 | 43.3819
2055 | 43.7403 | 33.3648 | 43.7549
2056 | 44.9472 | 33.0331 | 42.9069
2057 | 42.7271 | 34.0889 | 39.4554
2058 | 44.1913 | 31.8399 | 44.3869
2059 | 43.5179 | 34.2757 | 40.3651
2060 | 42.7894 | 35.1563 | 43.7569
2061 | 40.5965 | 35.6145 | 43.1061
2062 | 41.9343 | 33.4798 | 41.7724
2063 | 43.2416 | 34.5063 | 43.9659
2064 | 44.9143 | 32.7228 | 45.4882
2065 | 41.7786 | 33.9382 | 42.7376
2066 | 44.6997 | 35.5048 | 42.6054
2067 | 43.98 | 36.4268 | 42.0758
2068 | 42.9719 | 35.2165 | 39.7564
2069 | 42.7008 | 33.1922 | 42.5731
2070 | 42.1415 | 33.9228 | 42.8164
2071 | 41.4939 | 34.4129 | 39.7645
2072 | 44.9763 | 32.2989 | 44.4518
2073 | 44.7225 | 33.3565 | 44.2825
2074 | 44.7108 | 32.4305 | 44.8594
2075 | 44.9587 | 35.0484 | 44.6335
2076 | 43.0735 | 32.9123 | 45.3513
2077 | 43.0845 | 34.8913 | 41.5532
2078 | 44.8798 | 34.8358 | 41.0377
2079 | 44.9643 | 34.106 | 47.2955
2080 | 44.4624 | 34.2352 | 40.6082
2081 | 42.1749 | 33.5136 | 42.4597
2082 | 43.6817 | 33.0624 | 36.6241
2083 | 42.3893 | 34.9709 | 41.4999
2084 | 44.886 | 33.105 | 43.8834
2085 | 43.4684 | 35.2818 | 43.7303
2086 | 42.239 | 36.3302 | 42.2796
2087 | 43.2734 | 33.1292 | 44.9079
2088 | 44.0102 | 34.3888 | 44.1506
2089 | 43.9746 | 35.438 | 43.8172
2090 | 40.5538 | 33.1346 | 43.3328
2091 | 44.1207 | 33.4654 | 41.5156
2092 | 42.1509 | 32.0993 | 44.6453
2093 | 44.9016 | 32.9838 | 40.8921
2094 | 41.6772 | 34.6927 | 41.872
2095 | 45.295 | 32.4228 | 45.3108
2096 | 43.7476 | 33.7476 | 43.222
2097 | 42.0562 | 35.4492 | 42.8988
2098 | 44.1835 | 35.0429 | 43.6057
2099 | 45.5837 | 34.5458 | 41.5959
2100 | 43.0122 | 34.0831 | 44.6767
2101 | 42.9179 | 31.6201 | 42.8878
2102 | 44.0695 | 34.6 | 43.1877
2103 | 43.3202 | 32.9879 | 42.3429
2104 | 43.3039 | 34.4266 | 43.0433
2105 | 43.7184 | 36.3507 | 41.796
2106 | 40.1775 | 33.4699 | 43.6362
2107 | 41.164 | 35.096 | 42.4703
2108 | 43.0844 | 34.6618 | 43.0329
2109 | 42.4104 | 30.7655 | 40.4968
2110 | 44.9482 | 35.7525 | 42.0318
2111 | 43.3207 | 32.8285 | 45.0861
2112 | 42.5966 | 34.9974 | 44.8284
2113 | 44.5966 | 34.4236 | 40.6785
2114 | 40.9437 | 34.4798 | 42.937
2115 | 40.749 | 32.7103 | 44.5909
2116 | 44.1466 | 35.4406 | 45.0637
2117 | 45.241 | 35.1419 | 44.2636
2118 | 41.033 | 33.2547 | 42.1504
2119 | 41.9778 | 34.0155 | 40.7545
2120 | 46.3371 | 34.0868 | 41.1262
2121 | 43.9551 | 34.1386 | 43.3637
2122 | 39.919 | 33.2225 | 42.3691
2123 | 44.0097 | 34.2489 | 43.1439
2124 | 42.8003 | 35.1536 | 42.8548
2125 | 40.9042 | 33.2342 | 44.1425
2126 | 42.0135 | 32.7624 | 43.0594
2127 | 42.6082 | 32.788 | 44.0008
2128 | 42.6293 | 34.6625 | 44.5779
2129 | 46.5076 | 37.0906 | 42.078
2130 | 42.9819 | 33.7628 | 40.8546
2131 | 46.6588 | 34.9306 | 44.7537
2132 | 41.2969 | 34.6956 | 42.328
2133 | 46.6315 | 33.5259 | 41.5107
2134 | 43.252 | 34.3533 | 41.51
2135 | 41.9161 | 32.8924 | 42.4111
2136 | 43.5302 | 33.8837 | 41.922
2137 | 44.4811 | 33.7267 | 43.4606
2138 | 44.2414 | 34.7082 | 41.929
2139 | 43.0146 | 36.065 | 42.4729
2140 | 41.0979 | 34.4651 | 41.5087
2141 | 40.2439 | 32.763 | 45.4506
2142 | 43.8112 | 36.1234 | 45.0006
2143 | 41.9372 | 34.5873 | 41.4091
2144 | 41.2506 | 33.8308 | 45.2909
2145 | 40.8589 | 33.2264 | 46.335
2146 | 44.2625 | 34.3253 | 42.5944
2147 | 44.3699 | 35.2992 | 42.0768
2148 | 43.6436 | 31.4742 | 45.0696
2149 | 45.0319 | 34.8129 | 42.0647
2150 | 42.5904 | 35.2018 | 43.9676
2151 | 40.5189 | 32.8941 | 40.713
2152 | 44.9527 | 32.2167 | 40.5258
2153 | 44.9327 | 35.3433 | 43.8779
2154 | 38.2534 | 35.6551 | 44.4367
2155 | 41.8749 | 33.169 | 40.506
2156 | 43.6649 | 31.7802 | 43.3717
2157 | 42.7722 | 35.5329 | 43.5773
2158 | 44.7512 | 34.038 | 42.435
2159 | 41.9283 | 34.8175 | 42.9194
2160 | 42.4005 | 32.2219 | 42.6258
2161 | 44.9425 | 34.2116 | 42.9275
2162 | 45.0834 | 32.1401 | 42.4519
2163 | 44.8117 | 35.5107 | 41.4283
2164 | 45.8715 | 36.8295 | 41.9159
2165 | 44.7078 | 34.1345 | 44.1688
2166 | 42.1061 | 35.8581 | 44.925
2167 | 43.1534 | 33.3853 | 44.4649
2168 | 41.7431 | 33.1058 | 43.6708
2169 | 41.7624 | 34.1744 | 43.5073
2170 | 42.8808 | 35.5356 | 39.8683
2171 | 41.785 | 32.8206 | 43.7531
2172 | 42.9408 | 32.8766 | 44.6353
2173 | 43.5286 | 34.5416 | 41.4137
2174 | 44.0735 | 34.916 | 44.4632
2175 | 42.4333 | 34.1751 | 43.2513
2176 | 41.4643 | 35.7936 | 42.3178
2177 | 43.3433 | 37.1427 | 44.8927
2178 | 44.7044 | 33.7827 | 43.4379
2179 | 46.6113 | 33.0588 | 43.3879
2180 | 42.436 | 33.8517 | 41.0742
2181 | 45.4082 | 34.2147 | 45.9826
2182 | 43.9549 | 33.5073 | 45.7744
2183 | 44.7315 | 34.2516 | 45.3079
2184 | 42.6999 | 33.8796 | 44.4577
2185 | 44.8918 | 33.8807 | 43.4452
2186 | 42.7447 | 36.0558 | 43.5286
2187 | 44.568 | 33.9716 | 43.1706
2188 | 44.5485 | 37.2706 | 42.5937
2189 | 42.6466 | 32.881 | 42.9587
2190 | 45.0346 | 33.0959 | 44.634
2191 | 41.0147 | 32.128 | 43.741
2192 | 44.5801 | 33.8428 | 45.1101
2193 | 40.206 | 32.6135 | 42.0269
2194 | 44.9622 | 34.441 | 40.0713
2195 | 41.6833 | 35.1726 | 44.132
2196 | 44.3798 | 33.7063 | 44.6689
2197 | 45.701 | 34.1794 | 43.5495
2198 | 46.5303 | 34.5796 | 42.3573
2199 | 42.6449 | 35.385 | 44.8549
2200 | 44.0043 | 33.5923 | 46.2295
2201 | 43.7203 | 36.231 | 42.7744
2202 | 42.8945 | 33.3782 | 39.4494
2203 | 40.0591 | 38.3372 | 43.1733
2204 | 41.049 | 35.3533 | 43.5534
2205 | 44.8068 | 34.964 | 45.5959
2206 | 44.2633 | 36.214 | 45.1806
2207 | 41.1249 | 32.6708 | 43.3767
2208 | 44.7777 | 34.0777 | 44.3304
2209 | 42.7442 | 36.2075 | 41.8856
2210 | 45.0864 | 34.5325 | 43.6758
2211 | 44.98 | 35.1395 | 44.4933
2212 | 43.0002 | 36.5536 | 41.8621
2213 | 42.3793 | 35.2665 | 41.5822
2214 | 46.1303 | 33.21 | 44.3005
2215 | 42.0807 | 34.998 | 42.7139
2216 | 43.8264 | 33.1024 | 42.9619
2217 | 45.7941 | 33.7769 | 45.2871
2218 | 43.1677 | 34.1634 | 41.447
2219 | 42.4479 | 35.0122 | 45.072
2220 | 43.2724 | 33.871 | 44.6832
2221 | 44.762 | 32.9211 | 45.2495
2222 | 45.7519 | 34.7246 | 46.2964
2223 | 44.0666 | 33.6807 | 42.2705
2224 | 44.5144 | 34.4039 | 43.3143
2225 | 46.6516 | 33.4958 | 44.7051
2226 | 43.9581 | 33.5976 | 42.5244
2227 | 43.7161 | 34.9826 | 43.7676
2228 | 41.3763 | 33.8583 | 42.1187
2229 | 44.0282 | 33.6744 | 42.8236
2230 | 41.1945 | 33.5792 | 42.3057
2231 | 40.474 | 35.4909 | 39.7121
2232 | 45.3934 | 33.8784 | 43.9449
2233 | 42.1712 | 37.2322 | 39.9314
2234 | 43.8515 | 35.9573 | 44.3337
2235 | 45.4417 | 34.3783 | 44.0985
2236 | 43.042 | 32.8448 | 44.3485
2237 | 42.0859 | 34.4008 | 40.6675
2238 | 44.9669 | 32.5428 | 43.0843
2239 | 45.8632 | 35.1167 | 41.6047
2240 | 41.8893 | 33.7954 | 40.0698
2241 | 42.4241 | 34.628 | 42.3432
2242 | 43.3455 | 34.9917 | 42.4066
2243 | 44.5421 | 33.7314 | 45.0837
2244 | 42.5314 | 33.3296 | 44.1899
2245 | 42.4833 | 33.6135 | 45.572
2246 | 41.2952 | 33.9935 | 43.9114
2247 | 46.5284 | 34.4554 | 42.7273
2248 | 42.6869 | 33.0552 | 45.0645
2249 | 43.5151 | 33.918 | 43.0226
2250 | 44.0931 | 35.6514 | 42.0727
2251 | 45.432 | 31.2551 | 43.0085
2252 | 43.2828 | 34.2666 | 44.7179
2253 | 43.9046 | 34.0078 | 44.0879
2254 | 43.5575 | 33.8326 | 43.2412
2255 | 45.1319 | 36.7286 | 43.4042
2256 | 42.5046 | 34.3137 | 41.6949
2257 | 44.1381 | 34.2022 | 40.8402
2258 | 43.0632 | 34.2027 | 43.4518
2259 | 42.8686 | 34.5901 | 44.577
2260 | 41.6454 | 36.0643 | 44.2522
2261 | 42.3991 | 38.136 | 44.017
2262 | 41.9569 | 34.7205 | 43.6984
2263 | 43.551 | 34.3351 | 43.8302
2264 | 41.5454 | 36.3871 | 42.8181
2265 | 45.0838 | 32.6347 | 44.8905
2266 | 42.6936 | 33.3177 | 43.1856
2267 | 45.7129 | 35.1401 | 43.3113
2268 | 42.2306 | 32.8693 | 42.9758
2269 | 43.8857 | 35.331 | 44.0169
2270 | 45.1526 | 33.9927 | 43.8195
2271 | 44.0525 | 35.5262 | 42.7516
2272 | 43.9801 | 34.6653 | 43.2291
2273 | 43.5821 | 33.9267 | 43.3386
2274 | 42.9044 | 35.3514 | 42.3366
2275 | 43.6296 | 33.6612 | 44.8901
2276 | 42.5936 | 34.1812 | 43.4127
2277 | 45.2122 | 32.6013 | 43.0854
2278 | 41.7252 | 35.3455 | 45.206
2279 | 41.7202 | 32.5139 | 42.8608
2280 | 44.4032 | 34.7993 | 44.8705
2281 | 43.8277 | 32.469 | 43.7314
2282 | 45.291 | 34.3465 | 41.4048
2283 | 42.7454 | 34.5964 | 43.4719
2284 | 40.9948 | 33.6797 | 43.6322
2285 | 42.1329 | 34.258 | 40.6561
2286 | 42.0741 | 34.1139 | 43.6976
2287 | 44.0703 | 34.7938 | 41.6269
2288 | 43.6891 | 34.1305 | 39.6152
2289 | 45.7729 | 35.1106 | 43.3548
2290 | 42.8468 | 35.3355 | 44.3889
2291 | 44.7456 | 32.4722 | 41.4974
2292 | 41.0369 | 35.2598 | 43.3994
2293 | 42.5326 | 33.6675 | 44.0487
2294 | 43.9425 | 35.3925 | 43.2499
2295 | 44.4529 | 33.7416 | 43.0408
2296 | 44.8238 | 33.6979 | 41.5073
2297 | 42.0862 | 34.4612 | 45.3433
2298 | 43.5174 | 33.2372 | 45.4249
2299 | 41.4297 | 34.7895 | 41.52
2300 | 43.12 | 33.951 | 43.2764
2301 | 42.2735 | 32.8635 | 40.9939
2302 | 43.7939 | 36.5218 | 47.5061
2303 | 44.5747 | 33.2345 | 42.4848
2304 | 42.4597 | 32.998 | 42.9873
2305 | 45.8192 | 33.872 | 45.028
2306 | 46.0609 | 36.3164 | 42.3261
2307 | 41.4896 | 34.2916 | 43.8926
2308 | 44.6327 | 35.1948 | 45.2229
2309 | 44.1398 | 35.1451 | 44.8223
2310 | 43.1963 | 34.2634 | 44.1972
2311 | 45.4966 | 33.1148 | 43.7051
2312 | 43.1773 | 33.537 | 42.4747
2313 | 42.2018 | 35.957 | 43.6168
2314 | 43.2203 | 33.9354 | 41.5284
2315 | 43.0617 | 33.7408 | 42.5484
2316 | 43.2679 | 35.1581 | 44.8916
2317 | 40.7211 | 34.3833 | 42.3672
2318 | 42.2274 | 34.6089 | 42.4493
2319 | 44.2679 | 37.192 | 41.4471
2320 | 44.4568 | 32.7483 | 39.5152
2321 | 44.1512 | 34.7568 | 42.2749
2322 | 44.5801 | 33.3707 | 40.7279
2323 | 44.7007 | 34.981 | 43.9803
2324 | 42.9375 | 34.1522 | 44.6778
2325 | 43.8637 | 33.4153 | 40.385
2326 | 43.4349 | 37.8026 | 40.4009
2327 | 41.768 | 34.2035 | 44.0948
2328 | 42.7331 | 36.7955 | 41.8163
2329 | 45.9653 | 35.6625 | 41.6308
2330 | 43.9914 | 36.1407 | 44.026
2331 | 42.9463 | 34.4145 | 45.3438
2332 | 42.2678 | 34.145 | 45.2534
2333 | 42.5762 | 35.4389 | 45.3328
2334 | 42.5444 | 34.5589 | 44.5268
2335 | 40.551 | 33.934 | 42.94
2336 | 43.8194 | 32.8526 | 43.344
2337 | 43.0744 | 35.451 | 40.6836
2338 | 44.7134 | 35.2574 | 41.6863
2339 | 42.7051 | 35.9185 | 43.4201
2340 | 41.3918 | 32.0237 | 42.5137
2341 | 45.0106 | 35.1272 | 43.7999
2342 | 42.7773 | 32.5293 | 42.9845
2343 | 42.8778 | 34.118 | 42.1411
2344 | 43.1507 | 33.8826 | 43.2881
2345 | 43.8083 | 34.4879 | 41.2377
2346 | 41.8523 | 33.8584 | 44.3852
2347 | 44.2997 | 34.0798 | 43.3508
2348 | 42.5285 | 36.1074 | 44.4936
2349 | 46.0893 | 34.7398 | 42.9698
2350 | 42.6754 | 32.7403 | 43.9717
2351 | 44.0127 | 33.1597 | 42.702
2352 | 43.6395 | 36.0286 | 45.4872
2353 | 41.9052 | 32.905 | 40.254
2354 | 40.281 | 35.4683 | 45.152
2355 | 43.4931 | 34.4222 | 45.2714
2356 | 47.1827 | 33.8029 | 44.0169
2357 | 44.374 | 36.0448 | 42.8966
2358 | 40.5513 | 34.6597 | 43.8183
2359 | 43.5861 | 34.1381 | 41.1238
2360 | 45.255 | 33.3576 | 42.5629
2361 | 40.4154 | 33.5075 | 43.1703
2362 | 44.1687 | 33.2822 | 43.0932
2363 | 42.8416 | 34.6375 | 41.1684
2364 | 43.8161 | 34.7487 | 43.1407
2365 | 44.7019 | 31.7489 | 44.6235
2366 | 45.5293 | 36.0587 | 43.479
2367 | 43.7134 | 33.4685 | 44.5025
2368 | 43.17 | 35.0712 | 43.5492
2369 | 45.4635 | 33.1742 | 44.7825
2370 | 40.8937 | 34.2487 | 41.9868
2371 | 43.3738 | 33.2022 | 41.9881
2372 | 42.5229 | 33.0946 | 40.9353
2373 | 44.3378 | 34.2559 | 43.1442
2374 | 43.8531 | 32.6239 | 45.9874
2375 | 44.2823 | 35.3516 | 41.6248
2376 | 40.9232 | 35.0113 | 44.9147
2377 | 42.3903 | 34.4178 | 45.6715
2378 | 40.8747 | 34.0395 | 44.6316
2379 | 43.3094 | 34.631 | 41.9381
2380 | 42.0624 | 34.637 | 43.265
2381 | 41.2156 | 33.8216 | 42.7486
2382 | 43.5436 | 32.5664 | 43.6131
2383 | 44.3152 | 33.7493 | 42.2805
2384 | 43.3535 | 34.8557 | 43.7851
2385 | 42.5274 | 35.4692 | 42.1018
2386 | 43.6629 | 34.5448 | 42.7797
2387 | 43.1202 | 33.6948 | 45.5642
2388 | 43.8092 | 34.0754 | 42.8974
2389 | 42.7385 | 33.9119 | 43.9795
2390 | 41.7079 | 32.4455 | 41.7719
2391 | 44.524 | 33.4718 | 41.7012
2392 | 44.6498 | 36.4399 | 44.6686
2393 | 41.4791 | 34.1983 | 43.9934
2394 | 43.373 | 34.0161 | 43.5245
2395 | 43.9395 | 33.9337 | 43.4463
2396 | 43.1938 | 34.4325 | 43.1361
2397 | 41.509 | 36.7071 | 43.4962
2398 | 45.2857 | 34.745 | 43.9745
2399 | 42.4402 | 34.9389 | 46.0635
2400 | 42.5236 | 34.9826 | 44.4093
2401 | 43.336 | 31.3494 | 42.8882
2402 | 44.1929 | 34.3275 | 42.4155
2403 | 43.4773 | 32.545 | 40.6333
2404 | 44.813 | 34.9549 | 45.9422
2405 | 45.5746 | 33.1588 | 42.713
2406 | 40.8998 | 35.9702 | 41.235
2407 | 43.3386 | 34.4071 | 42.7101
2408 | 43.912 | 34.2789 | 45.8836
2409 | 43.3479 | 34.1317 | 44.79
2410 | 43.754 | 36.5001 | 43.3634
2411 | 44.9832 | 32.8593 | 44.2166
2412 | 45.5106 | 35.9036 | 45.1684
2413 | 43.9974 | 32.7665 | 45.0734
2414 | 42.0661 | 33.9452 | 42.3446
2415 | 41.6671 | 34.9087 | 45.1874
2416 | 45.8105 | 33.6398 | 43.0168
2417 | 45.2366 | 33.5984 | 43.5641
2418 | 40.8065 | 33.4907 | 44.6966
2419 | 43.0156 | 33.3103 | 41.9734
2420 | 43.0043 | 34.7436 | 39.5006
2421 | 44.0371 | 33.4304 | 42.7164
2422 | 43.6867 | 33.1841 | 43.7333
2423 | 43.3815 | 32.9153 | 44.1429
2424 | 41.3682 | 36.2811 | 44.4055
2425 | 40.6593 | 36.8249 | 44.7523
2426 | 43.0688 | 33.9899 | 43.7268
2427 | 44.7438 | 34.1067 | 43.641
2428 | 41.2021 | 35.1716 | 41.1286
2429 | 42.4724 | 32.4465 | 45.2958
2430 | 44.3414 | 33.9177 | 43.6282
2431 | 42.7707 | 33.9472 | 44.653
2432 | 44.3174 | 35.0681 | 43.7779
2433 | 41.812 | 32.1355 | 42.9443
2434 | 42.7147 | 33.8659 | 42.8242
2435 | 42.3125 | 34.6967 | 44.7927
2436 | 42.5097 | 33.9367 | 44.0198
2437 | 41.5829 | 33.7613 | 45.3125
2438 | 43.4783 | 34.2007 | 43.4048
2439 | 44.8909 | 35.9959 | 41.5458
2440 | 43.0371 | 34.4867 | 42.6385
2441 | 42.5579 | 32.7876 | 43.1714
2442 | 43.6338 | 35.9251 | 42.6886
2443 | 42.1274 | 34.1086 | 43.3013
2444 | 43.1316 | 33.9491 | 44.5016
2445 | 44.2922 | 34.9887 | 45.3259
2446 | 43.6611 | 34.1486 | 43.441
2447 | 43.7252 | 35.2008 | 41.4596
2448 | 42.1178 | 34.9684 | 41.0014
2449 | 44.3154 | 33.2304 | 43.4135
2450 | 42.4588 | 35.331 | 42.0745
2451 | 41.9103 | 34.7083 | 43.4041
2452 | 42.3173 | 35.807 | 40.4594
2453 | 41.9704 | 35.1489 | 44.8963
2454 | 42.5519 | 35.3477 | 44.5904
2455 | 43.9064 | 35.1012 | 44.2073
2456 | 41.889 | 37.1428 | 41.4008
2457 | 46.0445 | 33.6797 | 44.5661
2458 | 40.5268 | 34.6917 | 46.1846
2459 | 44.8798 | 35.0777 | 44.0691
2460 | 44.2964 | 33.8521 | 41.2875
2461 | 43.599 | 35.8796 | 41.672
2462 | 40.5138 | 34.3608 | 44.0311
2463 | 45.6136 | 35.0965 | 43.8869
2464 | 42.3716 | 34.8182 | 42.112
2465 | 41.064 | 35.09 | 41.9188
2466 | 41.146 | 34.7856 | 42.1571
2467 | 41.5876 | 34.2697 | 42.2475
2468 | 44.3438 | 34.0139 | 45.1452
2469 | 43.3394 | 34.6436 | 45.8879
2470 | 43.1818 | 36.5617 | 46.2047
2471 | 43.7688 | 35.0885 | 43.0185
2472 | 41.6498 | 32.5099 | 42.6456
2473 | 42.4697 | 34.212 | 43.5602
2474 | 43.3142 | 33.3713 | 41.7814
2475 | 44.0621 | 32.4301 | 46.0542
2476 | 44.4191 | 34.6083 | 42.0288
2477 | 43.4273 | 35.2513 | 44.5375
2478 | 43.4383 | 32.969 | 44.1278
2479 | 41.7099 | 33.4226 | 42.7252
2480 | 41.4382 | 34.8697 | 44.852
2481 | 43.2793 | 33.4916 | 41.69
2482 | 43.1272 | 37.1317 | 43.8904
2483 | 42.9658 | 34.7945 | 42.5529
2484 | 44.2288 | 33.4987 | 44.064
2485 | 44.1984 | 33.9747 | 40.0132
2486 | 43.5146 | 33.6374 | 43.8599
2487 | 43.3102 | 35.5767 | 44.8579
2488 | 42.977 | 36.1969 | 43.4485
2489 | 45.3534 | 32.4586 | 42.1215
2490 | 40.9179 | 36.932 | 43.12
2491 | 43.1654 | 35.9829 | 42.3375
2492 | 45.0696 | 35.3185 | 44.8152
2493 | 44.62 | 35.9956 | 45.0367
2494 | 44.1986 | 34.8449 | 41.4901
2495 | 44.2602 | 34.0768 | 45.0064
2496 | 42.1717 | 33.1977 | 44.3168
2497 | 43.2731 | 34.2665 | 42.6611
2498 | 41.6908 | 35.2219 | 43.3087
2499 | 43.0339 | 35.8955 | 43.2852
2500 | 43.9703 | 34.5425 | 41.4819
2501 | 43.6343 | 33.3425 | 42.13
2502 | 42.498 | 37.2788 | 44.2932
2503 | 45.8738 | 32.8769 | 41.8807
2504 | 43.6304 | 34.1756 | 42.6895
2505 | 42.826 | 33.3139 | 43.9721
2506 | 42.0427 | 36.5754 | 42.0021
2507 | 40.7043 | 33.7962 | 45.6509
2508 | 44.8167 | 33.4927 | 41.6354
2509 | 43.6279 | 32.2057 | 44.0204
2510 | 41.4013 | 34.6168 | 44.7288
2511 | 42.8376 | 32.9655 | 42.7485
2512 | 44.6313 | 32.9866 | 46.1098
2513 | 42.5497 | 33.8167 | 42.7201
2514 | 41.8055 | 32.0655 | 41.309
2515 | 41.0601 | 33.9809 | 42.7498
2516 | 45.137 | 31.7964 | 44.6158
2517 | 43.8158 | 34.5801 | 45.3403
2518 | 44.3348 | 32.9192 | 44.2264
2519 | 41.9092 | 34.1962 | 44.0458
2520 | 43.9311 | 34.4814 | 45.0836
2521 | 44.885 | 34.2402 | 42.6437
2522 | 43.3293 | 35.6449 | 43.9096
2523 | 43.4852 | 33.9352 | 45.039
2524 | 43.542 | 31.6325 | 44.7477
2525 | 43.8575 | 32.5763 | 42.2812
2526 | 42.6708 | 34.7907 | 44.4281
2527 | 43.9954 | 33.3299 | 41.3547
2528 | 40.6554 | 35.5521 | 40.338
2529 | 43.0099 | 34.3166 | 40.4391
2530 | 44.8396 | 33.4131 | 44.0353
2531 | 41.4542 | 32.7257 | 44.2584
2532 | 43.3214 | 36.467 | 45.1434
2533 | 43.8205 | 32.4768 | 42.6553
2534 | 43.4385 | 34.0934 | 39.9105
2535 | 42.7657 | 35.9627 | 44.2092
2536 | 43.4432 | 35.8207 | 44.3736
2537 | 43.7196 | 34.4357 | 39.8017
2538 | 45.7788 | 34.8901 | 41.3721
2539 | 42.7639 | 34.1164 | 41.2799
2540 | 44.6565 | 32.7128 | 44.1364
2541 | 41.5192 | 36.1696 | 42.3889
2542 | 45.2292 | 34.7 | 45.2695
2543 | 42.605 | 35.9155 | 43.403
2544 | 41.9371 | 35.881 | 42.6206
2545 | 43.4121 | 34.361 | 44.2367
2546 | 42.8965 | 32.7079 | 43.6267
2547 | 43.2553 | 32.9448 | 44.7642
2548 | 42.807 | 31.9559 | 41.9091
2549 | 41.789 | 34.7805 | 44.9759
2550 | 42.2422 | 34.9949 | 42.2629
2551 | 44.3256 | 36.2461 | 42.2604
2552 | 42.944 | 34.9189 | 41.5406
2553 | 46.2014 | 34.2719 | 42.4328
2554 | 44.1103 | 32.053 | 43.6418
2555 | 46.6039 | 35.185 | 44.66
2556 | 44.4975 | 35.3557 | 45.1977
2557 | 43.2825 | 36.077 | 44.5689
2558 | 39.6757 | 35.1415 | 44.835
2559 | 44.5991 | 34.6939 | 41.5148
2560 | 42.1583 | 33.4772 | 41.3527
2561 | 42.4622 | 34.1872 | 43.9542
2562 | 42.6405 | 33.5745 | 43.6658
2563 | 43.2032 | 35.2192 | 44.4513
2564 | 41.6725 | 34.748 | 46.134
2565 | 45.5348 | 35.5067 | 41.5222
2566 | 42.8449 | 34.9046 | 41.4426
2567 | 42.0997 | 36.2869 | 43.2587
2568 | 43.8425 | 35.2467 | 43.9557
2569 | 42.7079 | 35.101 | 40.9327
2570 | 44.2342 | 34.7204 | 43.315
2571 | 42.7787 | 35.6618 | 44.8148
2572 | 44.9423 | 37.3713 | 44.4927
2573 | 39.9003 | 33.4331 | 43.0238
2574 | 43.8293 | 34.4326 | 41.5128
2575 | 44.6005 | 34.7421 | 40.8131
2576 | 44.3669 | 33.6177 | 43.432
2577 | 45.3593 | 35.1301 | 41.6361
2578 | 42.168 | 33.6858 | 43.4365
2579 | 40.8495 | 35.09 | 42.9793
2580 | 42.2987 | 36.0686 | 42.1788
2581 | 43.3357 | 35.147 | 40.0855
2582 | 44.3375 | 32.5849 | 41.9609
2583 | 43.4584 | 35.6014 | 42.6745
2584 | 42.562 | 34.6644 | 42.4243
2585 | 41.9605 | 33.3267 | 46.5171
2586 | 45.7978 | 33.8335 | 44.8806
2587 | 42.4114 | 34.6343 | 43.8754
2588 | 43.2639 | 35.5769 | 42.3466
2589 | 44.5648 | 36.2974 | 42.8538
2590 | 44.3499 | 35.5647 | 40.7691
2591 | 43.4587 | 33.4492 | 42.3455
2592 | 42.8732 | 36.3554 | 41.3615
2593 | 44.2594 | 33.8067 | 45.1482
2594 | 44.6846 | 34.0059 | 44.6627
2595 | 45.3198 | 34.9495 | 39.7036
2596 | 41.5883 | 33.6878 | 44.4403
2597 | 44.1414 | 34.204 | 42.3206
2598 | 44.5814 | 33.8598 | 44.5619
2599 | 41.0288 | 32.9533 | 42.3626
2600 | 43.7014 | 33.0912 | 41.7046
2601 | 46.4327 | 35.5067 | 44.976
2602 | 42.4312 | 32.8882 | 43.3041
2603 | 44.1653 | 35.4685 | 42.2056
2604 | 45.5022 | 32.8666 | 39.6461
2605 | 47.3191 | 34.4121 | 42.1981
2606 | 44.2192 | 33.625 | 43.9945
2607 | 45.1735 | 34.2466 | 42.8536
2608 | 42.2681 | 37.0825 | 42.5437
2609 | 44.2048 | 35.0342 | 40.5029
2610 | 45.2475 | 35.4189 | 44.0795
2611 | 43.3294 | 34.5569 | 42.0719
2612 | 45.2439 | 35.0264 | 41.0902
2613 | 43.0213 | 36.0601 | 44.4804
2614 | 45.0027 | 34.008 | 43.4952
2615 | 44.1636 | 34.7938 | 44.2679
2616 | 41.7588 | 34.2382 | 45.2098
2617 | 43.0678 | 35.498 | 43.9106
2618 | 45.8831 | 35.0682 | 44.2543
2619 | 43.0168 | 33.3224 | 45.3517
2620 | 44.6182 | 35.8684 | 45.6214
2621 | 42.2815 | 32.0702 | 44.6166
2622 | 43.711 | 31.291 | 42.7891
2623 | 42.2331 | 34.2411 | 44.0519
2624 | 43.9952 | 34.7927 | 46.5007
2625 | 44.9237 | 34.6796 | 44.302
2626 | 43.3233 | 34.2624 | 41.437
2627 | 42.3332 | 33.7091 | 44.4208
2628 | 44.9782 | 33.8089 | 44.1183
2629 | 43.8831 | 33.7859 | 41.5926
2630 | 42.9723 | 36.3293 | 43.797
2631 | 43.5128 | 34.6045 | 42.722
2632 | 44.1243 | 35.7337 | 39.7333
2633 | 44.7722 | 33.0675 | 42.9335
2634 | 46.5883 | 34.4559 | 42.5037
2635 | 42.5823 | 34.6754 | 44.4092
2636 | 43.8715 | 36.0683 | 46.0943
2637 | 44.7966 | 36.2627 | 45.9448
2638 | 41.0019 | 33.3447 | 42.6253
2639 | 40.8439 | 34.8094 | 42.4043
2640 | 44.8914 | 35.5033 | 42.1245
2641 | 41.2209 | 33.2489 | 44.0548
2642 | 41.9103 | 32.4119 | 43.1141
2643 | 44.6758 | 33.7806 | 43.6836
2644 | 45.9417 | 35.5097 | 42.893
2645 | 43.1873 | 34.1411 | 40.5402
2646 | 41.9848 | 36.3273 | 44.8657
2647 | 41.6709 | 34.5669 | 44.856
2648 | 40.9383 | 33.7372 | 42.6221
2649 | 45.2454 | 36.6363 | 42.3446
2650 | 46.3023 | 35.2304 | 44.9075
2651 | 46.3407 | 33.7219 | 43.9765
2652 | 41.4724 | 31.7774 | 41.9953
2653 | 41.491 | 35.2492 | 43.948
2654 | 42.2314 | 34.2658 | 44.0926
2655 | 43.6252 | 33.8607 | 42.8321
2656 | 43.234 | 34.1942 | 42.9466
2657 | 45.855 | 35.5153 | 42.6175
2658 | 41.1545 | 35.4516 | 44.4438
2659 | 41.6254 | 36.5376 | 44.549
2660 | 45.287 | 34.1373 | 41.649
2661 | 43.2395 | 32.9834 | 41.1789
2662 | 42.6193 | 33.787 | 42.6994
2663 | 43.4251 | 34.9971 | 42.3309
2664 | 44.7578 | 35.1022 | 43.8964
2665 | 39.8694 | 33.9872 | 40.2225
2666 | 42.8258 | 33.6435 | 42.3437
2667 | 42.5278 | 32.7397 | 44.4692
2668 | 44.7249 | 35.2562 | 42.0284
2669 | 42.29 | 33.9072 | 43.5153
2670 | 43.9688 | 34.6417 | 42.2692
2671 | 45.7755 | 33.1097 | 41.4543
2672 | 44.961 | 34.3226 | 43.5022
2673 | 44.0625 | 34.4705 | 43.5087
2674 | 41.2505 | 31.1151 | 42.8501
2675 | 42.268 | 33.2685 | 43.0345
2676 | 40.5457 | 33.8871 | 43.084
2677 | 43.2016 | 31.9453 | 42.2672
2678 | 42.2381 | 32.8996 | 42.517
2679 | 42.7329 | 32.687 | 44.1487
2680 | 43.4375 | 35.1328 | 43.6223
2681 | 44.2302 | 33.6928 | 44.2013
2682 | 45.4563 | 34.1062 | 44.5721
2683 | 42.5858 | 35.405 | 44.2112
2684 | 42.2114 | 33.9638 | 43.3532
2685 | 40.9531 | 32.2084 | 42.4092
2686 | 41.9133 | 34.3354 | 43.7933
2687 | 44.1337 | 32.9138 | 43.0642
2688 | 41.2132 | 34.9882 | 41.6679
2689 | 44.0445 | 33.4759 | 43.563
2690 | 44.6393 | 35.4543 | 42.9326
2691 | 41.6229 | 34.7907 | 40.2251
2692 | 40.282 | 35.6938 | 43.0722
2693 | 42.8914 | 35.1263 | 40.4411
2694 | 43.6742 | 35.1234 | 44.2404
2695 | 43.2907 | 34.5661 | 43.7196
2696 | 44.5365 | 34.6178 | 41.3259
2697 | 42.279 | 32.4075 | 43.6801
2698 | 42.8099 | 32.0616 | 45.1029
2699 | 44.7405 | 32.8613 | 42.6154
2700 | 44.0187 | 33.7164 | 42.7998
2701 | 45.7739 | 33.6791 | 44.6736
2702 | 41.7235 | 35.6698 | 41.6124
2703 | 44.2651 | 37.3365 | 45.6264
2704 | 45.3086 | 32.7781 | 43.5086
2705 | 43.5935 | 31.8913 | 43.0768
2706 | 44.9728 | 33.6103 | 45.0357
2707 | 43.9117 | 35.894 | 42.2667
2708 | 41.6643 | 34.639 | 45.2333
2709 | 41.3404 | 33.5738 | 43.4003
2710 | 43.8405 | 35.3641 | 41.7208
2711 | 42.9434 | 34.613 | 42.3662
2712 | 42.8205 | 33.1072 | 42.9023
2713 | 44.4894 | 32.7338 | 42.8761
2714 | 42.6308 | 34.7303 | 44.0057
2715 | 43.6877 | 32.5425 | 43.6678
2716 | 42.8978 | 36.4694 | 43.6258
2717 | 44.6244 | 32.0783 | 42.5242
2718 | 42.1424 | 35.0042 | 43.6993
2719 | 45.8931 | 36.459 | 43.8909
2720 | 44.817 | 35.2899 | 44.1963
2721 | 42.5154 | 32.1735 | 45.1496
2722 | 41.4039 | 33.8424 | 43.3506
2723 | 45.5385 | 33.9767 | 42.7814
2724 | 44.5005 | 34.6033 | 43.8001
2725 | 42.7355 | 34.4084 | 42.704
2726 | 41.9091 | 36.9308 | 43.3992
2727 | 44.6674 | 33.8312 | 41.8129
2728 | 41.5202 | 31.4682 | 43.9002
2729 | 43.0807 | 34.0585 | 41.7623
2730 | 44.2844 | 32.9609 | 41.2442
2731 | 45.8248 | 32.5609 | 40.5746
2732 | 44.0507 | 34.0056 | 40.8792
2733 | 44.9838 | 33.1305 | 42.915
2734 | 45.2162 | 35.0413 | 42.7813
2735 | 43.1507 | 34.7978 | 44.5215
2736 | 43.3126 | 33.9636 | 41.4547
2737 | 43.3428 | 33.7213 | 45.0288
2738 | 46.3317 | 31.0919 | 45.0243
2739 | 42.0825 | 35.0168 | 45.7643
2740 | 41.3713 | 34.207 | 44.4647
2741 | 43.8464 | 34.0716 | 42.9987
2742 | 43.8981 | 34.7835 | 42.0532
2743 | 44.7193 | 33.8445 | 45.9111
2744 | 46.4789 | 32.274 | 43.4914
2745 | 41.3471 | 36.3841 | 42.6582
2746 | 44.5365 | 34.8298 | 44.35
2747 | 41.1632 | 33.8233 | 41.5605
2748 | 42.5568 | 34.6045 | 42.9875
2749 | 44.2357 | 32.4593 | 43.8596
2750 | 44.361 | 33.9654 | 40.564
2751 | 45.2881 | 35.6631 | 43.3098
2752 | 41.2899 | 33.0298 | 42.8855
2753 | 42.8864 | 34.66 | 43.8116
2754 | 43.3764 | 36.1007 | 45.5991
2755 | 41.479 | 36.0979 | 45.8616
2756 | 42.7267 | 33.8648 | 43.4612
2757 | 43.936 | 33.402 | 43.3305
2758 | 44.7689 | 33.1925 | 41.9361
2759 | 46.0544 | 36.3213 | 42.6126
2760 | 41.6814 | 32.2669 | 41.5007
2761 | 42.9461 | 34.1183 | 44.2185
2762 | 43.9739 | 35.3594 | 42.5451
2763 | 44.9355 | 32.3667 | 40.1639
2764 | 40.159 | 32.8215 | 42.3875
2765 | 44.134 | 34.5828 | 43.2063
2766 | 40.133 | 33.4974 | 45.0652
2767 | 42.7462 | 33.8754 | 42.1134
2768 | 41.3938 | 36.2418 | 45.1349
2769 | 45.1877 | 35.6647 | 43.6841
2770 | 43.1616 | 35.4119 | 44.0032
2771 | 42.1068 | 33.9762 | 43.1799
2772 | 41.1948 | 34.1724 | 39.0961
2773 | 42.8265 | 34.2458 | 44.6518
2774 | 42.9862 | 35.8556 | 43.9882
2775 | 41.4791 | 33.9306 | 42.4206
2776 | 43.3377 | 35.5528 | 43.2099
2777 | 43.5913 | 34.9316 | 42.8315
2778 | 41.7944 | 37.3254 | 43.2128
2779 | 43.5462 | 34.252 | 44.8801
2780 | 44.6572 | 34.6678 | 44.4103
2781 | 43.396 | 37.0745 | 43.309
2782 | 44.5805 | 35.8109 | 43.2028
2783 | 41.7807 | 36.0099 | 43.6027
2784 | 42.8381 | 33.7041 | 46.3406
2785 | 43.7869 | 33.6631 | 40.6228
2786 | 43.4891 | 34.199 | 43.2588
2787 | 40.9099 | 32.5152 | 42.7999
2788 | 43.2883 | 32.8697 | 40.6993
2789 | 43.7556 | 35.3917 | 43.1169
2790 | 44.8917 | 34.5678 | 44.0502
2791 | 42.7369 | 33.64 | 41.7924
2792 | 42.5304 | 31.7735 | 44.1979
2793 | 43.9379 | 34.6838 | 42.8032
2794 | 42.7482 | 36.1289 | 41.0101
2795 | 46.1536 | 35.5872 | 42.8611
2796 | 44.537 | 34.6924 | 41.698
2797 | 42.2587 | 32.1205 | 44.3663
2798 | 41.6932 | 33.6393 | 43.1755
2799 | 41.8272 | 35.8686 | 44.7409
2800 | 41.9829 | 33.8559 | 45.5893
2801 | 44.2087 | 33.1316 | 43.9177
2802 | 41.2851 | 34.2441 | 43.688
2803 | 45.0327 | 37.311 | 44.6058
2804 | 42.406 | 32.3593 | 41.3326
2805 | 43.0911 | 33.1893 | 40.6043
2806 | 42.9855 | 32.9312 | 44.6742
2807 | 40.3296 | 33.9734 | 44.9359
2808 | 41.9728 | 34.2399 | 44.1253
2809 | 44.3937 | 34.001 | 43.6231
2810 | 41.9937 | 36.2653 | 41.3367
2811 | 43.5968 | 34.4932 | 44.235
2812 | 44.0202 | 36.8944 | 45.3321
2813 | 43.8733 | 33.0871 | 44.378
2814 | 41.5856 | 34.3798 | 46.5619
2815 | 44.2168 | 33.8368 | 43.5463
2816 | 44.394 | 33.3501 | 44.0611
2817 | 42.7146 | 35.3628 | 44.1816
2818 | 42.7811 | 34.1419 | 41.2308
2819 | 41.8765 | 33.4916 | 43.2611
2820 | 44.4419 | 34.1047 | 44.532
2821 | 41.4481 | 32.1552 | 45.7074
2822 | 45.3379 | 33.1993 | 42.7869
2823 | 44.0988 | 34.0418 | 43.3109
2824 | 41.8728 | 35.3722 | 45.8804
2825 | 45.8894 | 34.6533 | 43.5311
2826 | 44.5374 | 35.2099 | 42.6643
2827 | 43.2133 | 34.5673 | 42.0667
2828 | 43.0058 | 34.8699 | 39.6999
2829 | 41.5718 | 33.3036 | 43.1564
2830 | 43.8161 | 35.8924 | 42.6393
2831 | 44.0469 | 34.0623 | 43.7778
2832 | 43.3095 | 33.1827 | 42.6179
2833 | 45.2516 | 34.3279 | 42.6669
2834 | 44.8643 | 34.6588 | 42.1381
2835 | 42.7614 | 35.3011 | 42.6958
2836 | 41.3528 | 34.6415 | 44.3046
2837 | 42.1443 | 34.6616 | 45.1233
2838 | 42.8469 | 35.2103 | 43.1208
2839 | 44.1471 | 35.5234 | 41.7593
2840 | 43.4743 | 33.1821 | 44.8444
2841 | 42.8989 | 32.5318 | 44.3271
2842 | 43.8135 | 35.9077 | 42.2757
2843 | 44.8374 | 35.8121 | 44.4075
2844 | 46.1818 | 35.2267 | 43.3836
2845 | 39.8986 | 33.6555 | 41.5235
2846 | 47.0439 | 35.1058 | 42.4385
2847 | 41.3713 | 32.9787 | 44.5884
2848 | 43.8725 | 33.564 | 46.0658
2849 | 44.7836 | 34.9812 | 43.9955
2850 | 43.341 | 33.445 | 42.3669
2851 | 43.3562 | 33.0297 | 42.7307
2852 | 41.3957 | 33.7556 | 44.6631
2853 | 44.2282 | 35.8442 | 41.7276
2854 | 42.7027 | 35.4319 | 44.1362
2855 | 43.5583 | 34.4764 | 43.5186
2856 | 44.1545 | 35.8259 | 44.5546
2857 | 43.4622 | 37.9239 | 43.1637
2858 | 44.4492 | 33.0904 | 42.148
2859 | 43.2902 | 34.7006 | 42.5342
2860 | 39.9526 | 33.8927 | 43.4338
2861 | 47.4317 | 36.2206 | 42.0393
2862 | 43.1214 | 32.129 | 42.3832
2863 | 45.5047 | 34.9677 | 42.9854
2864 | 41.3773 | 35.4096 | 45.283
2865 | 41.4123 | 33.7232 | 44.0194
2866 | 43.118 | 33.106 | 44.5414
2867 | 41.4944 | 36.3874 | 43.2183
2868 | 39.4754 | 34.0645 | 43.6553
2869 | 43.5051 | 35.2819 | 42.6502
2870 | 44.7103 | 34.7222 | 42.2753
2871 | 42.5644 | 32.0703 | 41.7962
2872 | 44.3465 | 34.3329 | 42.3712
2873 | 41.8274 | 35.1106 | 43.6019
2874 | 43.3653 | 32.5457 | 44.4922
2875 | 42.7884 | 34.3454 | 42.5996
2876 | 42.594 | 34.9116 | 42.4307
2877 | 42.9967 | 34.1617 | 44.1674
2878 | 43.507 | 34.844 | 44.6895
2879 | 42.8432 | 33.3683 | 45.4134
2880 | 42.0439 | 35.3412 | 43.877
2881 | 43.1441 | 34.4431 | 43.6172
2882 | 40.8134 | 35.1891 | 43.4089
2883 | 44.9533 | 33.8135 | 45.5455
2884 | 44.5015 | 34.6133 | 45.7075
2885 | 40.9633 | 33.2861 | 43.8016
2886 | 43.4908 | 32.9747 | 44.1244
2887 | 40.5749 | 35.8601 | 40.9782
2888 | 44.7067 | 36.6911 | 43.2378
2889 | 42.9724 | 35.3839 | 42.4933
2890 | 44.8676 | 34.2386 | 41.9697
2891 | 43.4399 | 32.7115 | 43.4846
2892 | 44.0593 | 34.9451 | 42.4856
2893 | 40.8387 | 33.069 | 41.6714
2894 | 42.6914 | 33.5691 | 44.8621
2895 | 43.1275 | 34.5355 | 45.3005
2896 | 44.7998 | 33.4988 | 42.6113
2897 | 41.9843 | 35.3713 | 41.2733
2898 | 41.4669 | 33.2482 | 43.7628
2899 | 43.6146 | 33.1064 | 42.3481
2900 | 44.8713 | 33.4421 | 44.967
2901 | 41.6386 | 32.7217 | 41.856
2902 | 43.5922 | 32.0472 | 43.5938
2903 | 42.5528 | 32.8437 | 45.7516
2904 | 44.2897 | 36.7478 | 48.0615
2905 | 42.8659 | 33.6618 | 44.3964
2906 | 42.2254 | 35.1885 | 43.777
2907 | 43.3754 | 34.2549 | 39.8388
2908 | 43.7982 | 36.0147 | 42.3543
2909 | 43.0366 | 35.5458 | 44.5043
2910 | 43.8459 | 34.608 | 46.0806
2911 | 39.4922 | 33.4034 | 42.6639
2912 | 43.3787 | 34.1453 | 42.9476
2913 | 44.2475 | 32.1517 | 41.2926
2914 | 45.3285 | 34.2738 | 43.8514
2915 | 42.4845 | 33.7612 | 43.0857
2916 | 43.5973 | 31.1553 | 44.6436
2917 | 44.1763 | 33.0428 | 45.0725
2918 | 43.8415 | 32.0679 | 43.5663
2919 | 42.2007 | 33.6097 | 44.5538
2920 | 45.0656 | 34.6399 | 44.457
2921 | 42.9356 | 34.9399 | 44.2406
2922 | 42.4777 | 33.7374 | 42.3347
2923 | 41.7331 | 33.7074 | 43.4884
2924 | 40.9755 | 35.4667 | 42.7597
2925 | 42.7837 | 35.841 | 44.191
2926 | 41.8878 | 32.5654 | 42.8224
2927 | 44.5237 | 32.6903 | 40.9869
2928 | 44.5597 | 34.5249 | 44.2481
2929 | 40.9902 | 34.3953 | 43.4939
2930 | 41.0613 | 33.5678 | 43.8605
2931 | 41.1561 | 34.5959 | 43.0356
2932 | 41.6149 | 38.4013 | 45.2301
2933 | 44.0208 | 36.4511 | 44.456
2934 | 42.5354 | 34.8792 | 45.692
2935 | 45.0816 | 34.3647 | 42.8541
2936 | 43.2242 | 34.8629 | 40.8784
2937 | 45.2162 | 35.4495 | 43.8709
2938 | 45.1455 | 34.6822 | 42.3297
2939 | 41.7449 | 33.2943 | 44.8889
2940 | 44.7325 | 33.69 | 41.9684
2941 | 40.5665 | 34.2687 | 43.5213
2942 | 48.2634 | 33.9345 | 42.0157
2943 | 46.0615 | 34.1417 | 44.0195
2944 | 42.8147 | 34.2508 | 43.0757
2945 | 45.0449 | 35.1646 | 43.1623
2946 | 42.9211 | 34.6639 | 41.4771
2947 | 44.6845 | 35.0465 | 40.5461
2948 | 44.5841 | 34.7472 | 44.6371
2949 | 43.4621 | 34.2903 | 43.8143
2950 | 41.4361 | 36.3165 | 43.034
2951 | 44.8327 | 36.688 | 42.8416
2952 | 44.2473 | 34.7623 | 42.4864
2953 | 42.739 | 34.8498 | 42.7307
2954 | 43.2317 | 34.3605 | 43.5727
2955 | 42.8593 | 34.5265 | 41.7258
2956 | 42.2621 | 34.3081 | 44.5916
2957 | 45.4991 | 33.4029 | 42.8283
2958 | 44.9965 | 34.5484 | 42.2442
2959 | 42.2891 | 37.4356 | 45.8019
2960 | 42.6839 | 34.0517 | 42.7185
2961 | 42.5214 | 34.6374 | 45.7045
2962 | 43.8833 | 34.7381 | 44.8912
2963 | 41.0458 | 34.9987 | 44.4292
2964 | 45.1373 | 35.6362 | 46.4153
2965 | 40.4141 | 34.9416 | 43.8344
2966 | 40.1415 | 34.9257 | 42.113
2967 | 41.088 | 32.8322 | 45.0166
2968 | 41.9748 | 34.0395 | 41.3297
2969 | 40.8164 | 32.5802 | 42.2945
2970 | 42.5664 | 33.3437 | 40.6306
2971 | 46.9474 | 36.8168 | 44.0153
2972 | 41.3739 | 37.2133 | 43.3089
2973 | 41.5145 | 34.0241 | 42.1304
2974 | 41.091 | 33.0941 | 43.0334
2975 | 44.9435 | 34.5534 | 45.7255
2976 | 43.2531 | 33.4758 | 41.5399
2977 | 41.9816 | 35.0372 | 44.5363
2978 | 42.2652 | 33.2807 | 42.0895
2979 | 42.849 | 35.8882 | 40.8863
2980 | 42.667 | 33.8622 | 42.3709
2981 | 43.9706 | 34.5355 | 41.5295
2982 | 41.3255 | 34.6605 | 43.1065
2983 | 41.6973 | 36.1233 | 44.5193
2984 | 44.2545 | 33.3357 | 40.3945
2985 | 43.335 | 34.539 | 45.7743
2986 | 44.6815 | 33.5034 | 43.3401
2987 | 41.1478 | 31.8531 | 44.8007
2988 | 43.3966 | 36.2192 | 43.3007
2989 | 43.7308 | 35.2062 | 44.9865
2990 | 41.5943 | 34.7603 | 44.1672
2991 | 43.7914 | 32.3047 | 42.2611
2992 | 44.1579 | 35.7414 | 42.4877
2993 | 44.5665 | 35.8112 | 45.9272
2994 | 41.0451 | 33.6522 | 41.7435
2995 | 42.0345 | 34.5295 | 42.9109
2996 | 43.3959 | 35.6957 | 43.6021
2997 | 44.2554 | 33.9604 | 44.3364
2998 | 42.071 | 35.0748 | 44.1832
2999 | 43.2962 | 33.2304 | 45.8805
3000 | 45.1647 | 33.5496 | 42.1051
3001 | 44.5761 | 36.4203 | 44.3689
3002 | 43.6242 | 38.0156 | 43.9476
3003 | 43.4292 | 33.3402 | 41.6461
3004 | 41.2367 | 33.3301 | 43.0151
3005 | 43.4203 | 34.9465 | 42.8201
3006 | 45.4575 | 34.9457 | 45.2065
3007 | 42.1074 | 34.8878 | 44.7582
3008 | 41.8378 | 33.6836 | 45.9525
3009 | 43.6093 | 33.3817 | 45.5609
3010 | 43.5005 | 35.5066 | 42.4087
3011 | 42.9493 | 34.1565 | 45.4859
3012 | 44.8223 | 32.7164 | 44.6524
3013 | 40.5453 | 34.8986 | 42.5248
3014 | 41.4757 | 37.0636 | 44.1821
3015 | 44.7149 | 35.0984 | 41.6003
3016 | 39.7325 | 34.4544 | 45.8543
3017 | 44.2886 | 33.5953 | 44.844
3018 | 44.8848 | 34.9327 | 41.2307
3019 | 45.8501 | 35.5482 | 42.7941
3020 | 44.0098 | 34.2673 | 43.7054
3021 | 44.0476 | 34.6464 | 43.7509
3022 | 43.4938 | 34.6693 | 44.0532
3023 | 44.3249 | 33.5452 | 45.6149
3024 | 41.3058 | 34.5007 | 44.6785
3025 | 43.6555 | 32.4453 | 42.5939
3026 | 43.3515 | 32.8876 | 44.2276
3027 | 41.7414 | 34.2846 | 42.1818
3028 | 47.6188 | 33.6067 | 40.2402
3029 | 40.9603 | 34.8546 | 41.911
3030 | 44.4168 | 31.709 | 42.9774
3031 | 42.3622 | 35.1933 | 44.2258
3032 | 40.1041 | 33.596 | 46.126
3033 | 46.2764 | 32.3205 | 44.4065
3034 | 42.0923 | 34.3281 | 44.2332
3035 | 40.6697 | 35.1771 | 40.9434
3036 | 45.5341 | 37.4147 | 42.6444
3037 | 40.969 | 33.6777 | 44.2773
3038 | 44.0811 | 33.2736 | 42.2207
3039 | 41.8076 | 36.4452 | 42.5673
3040 | 41.6589 | 31.7836 | 41.8013
3041 | 45.3668 | 33.9953 | 44.0411
3042 | 41.8601 | 34.9346 | 44.5283
3043 | 42.3927 | 33.851 | 42.9363
3044 | 41.9663 | 34.6394 | 43.1216
3045 | 41.681 | 36.367 | 44.1938
3046 | 43.0513 | 35.1249 | 43.0933
3047 | 44.2739 | 35.5296 | 43.2701
3048 | 41.9487 | 35.0275 | 43.5648
3049 | 40.9332 | 34.8239 | 45.5163
3050 | 41.8779 | 35.9234 | 44.9866
3051 | 40.4574 | 33.6772 | 42.1404
3052 | 41.3775 | 33.9565 | 42.5721
3053 | 45.1205 | 34.6327 | 42.7103
3054 | 41.8648 | 32.5989 | 44.1183
3055 | 43.159 | 32.9591 | 40.8443
3056 | 44.9758 | 33.397 | 43.4531
3057 | 43.7092 | 33.8581 | 44.2998
3058 | 43.1255 | 35.0006 | 44.9228
3059 | 42.708 | 33.6178 | 44.044
3060 | 44.3807 | 33.5964 | 43.8509
3061 | 40.302 | 34.1021 | 43.1554
3062 | 43.0579 | 32.7405 | 43.0409
3063 | 45.7316 | 35.8731 | 43.3895
3064 | 42.4679 | 35.2022 | 40.9979
3065 | 41.2645 | 34.2648 | 43.7562
3066 | 42.8565 | 32.1827 | 42.9498
3067 | 45.4136 | 34.1984 | 43.7001
3068 | 41.3859 | 32.7968 | 43.6012
3069 | 43.9303 | 34.1119 | 41.9726
3070 | 44.4459 | 32.7755 | 40.6661
3071 | 41.4423 | 37.2923 | 44.4418
3072 | 43.4399 | 34.2148 | 43.7393
3073 | 43.138 | 34.8168 | 42.9692
3074 | 43.4476 | 35.3112 | 43.8871
3075 | 42.8554 | 32.1632 | 42.6634
3076 | 44.0785 | 34.9318 | 43.1428
3077 | 42.4843 | 33.5539 | 43.2583
3078 | 43.4321 | 35.4641 | 44.7089
3079 | 41.7042 | 32.3974 | 42.0733
3080 | 44.364 | 34.6285 | 44.1876
3081 | 46.4429 | 33.8804 | 41.2151
3082 | 43.5839 | 33.8276 | 42.9605
3083 | 42.4053 | 35.1307 | 43.1356
3084 | 42.2785 | 31.1249 | 42.9026
3085 | 41.5544 | 34.6391 | 43.6998
3086 | 44.4023 | 34.7701 | 42.4743
3087 | 44.1808 | 33.3298 | 44.9091
3088 | 43.3038 | 34.5061 | 42.24
3089 | 45.9785 | 34.9108 | 43.9342
3090 | 43.1927 | 33.6645 | 45.8234
3091 | 40.7482 | 32.4169 | 42.6751
3092 | 43.4688 | 35.209 | 43.1828
3093 | 44.3541 | 35.3783 | 42.6481
3094 | 42.9843 | 34.8244 | 43.7817
3095 | 43.7028 | 35.0047 | 41.3119
3096 | 44.4319 | 34.1434 | 44.6058
3097 | 43.5431 | 36.0078 | 43.6313
3098 | 44.843 | 34.8113 | 42.3852
3099 | 42.4814 | 34.044 | 43.2232
3100 | 41.332 | 32.1106 | 45.1334
3101 | 41.8959 | 33.1942 | 40.9269
3102 | 44.2951 | 32.5471 | 47.7995
3103 | 40.8515 | 34.6131 | 42.7554
3104 | 44.3243 | 33.7047 | 43.9013
3105 | 43.7788 | 32.3446 | 43.8484
3106 | 41.0567 | 34.3896 | 44.6197
3107 | 45.4277 | 35.5116 | 42.2333
3108 | 46.348 | 33.7555 | 44.4774
3109 | 43.3712 | 33.4552 | 44.7265
3110 | 40.6868 | 34.5348 | 45.8695
3111 | 42.6203 | 36.8712 | 42.924
3112 | 43.4442 | 35.1466 | 44.0671
3113 | 40.6318 | 34.1208 | 43.941
3114 | 42.3611 | 37.6855 | 44.5838
3115 | 41.1217 | 34.3111 | 41.0462
3116 | 44.8763 | 34.3464 | 42.5624
3117 | 44.2452 | 33.5791 | 44.3473
3118 | 44.6626 | 34.4034 | 44.7001
3119 | 44.4084 | 33.3256 | 43.2256
3120 | 42.8945 | 33.9468 | 44.6715
3121 | 44.7877 | 34.0706 | 42.6323
3122 | 42.6848 | 33.544 | 46.1283
3123 | 44.3393 | 35.4478 | 45.5412
3124 | 44.7047 | 33.3349 | 42.6874
3125 | 45.3246 | 33.7357 | 43.3803
3126 | 42.0878 | 33.1519 | 44.0749
3127 | 41.1656 | 33.4623 | 41.7167
3128 | 46.1931 | 34.8477 | 42.1922
3129 | 43.1091 | 34.3578 | 45.6482
3130 | 42.2201 | 35.5021 | 42.033
3131 | 43.2747 | 33.5569 | 44.2648
3132 | 45.5094 | 34.3232 | 42.747
3133 | 43.3428 | 35.4587 | 42.8702
3134 | 42.732 | 33.3815 | 44.3369
3135 | 41.6435 | 34.8064 | 40.1598
3136 | 43.0048 | 32.7618 | 44.7755
3137 | 45.2153 | 33.3644 | 46.2785
3138 | 44.0497 | 34.2255 | 42.3953
3139 | 45.2506 | 32.8916 | 43.0956
3140 | 45.7748 | 33.6916 | 43.2835
3141 | 41.2822 | 33.741 | 44.7836
3142 | 43.7783 | 32.3381 | 43.5129
3143 | 44.5549 | 37.1339 | 44.9142
3144 | 40.7242 | 32.4938 | 40.1345
3145 | 40.4035 | 34.0386 | 43.556
3146 | 41.3964 | 33.8915 | 42.5967
3147 | 43.692 | 35.551 | 45.2502
3148 | 41.1415 | 36.7751 | 40.4424
3149 | 44.0652 | 36.0209 | 44.4966
3150 | 43.0526 | 34.478 | 42.2515
3151 | 41.2671 | 34.5101 | 43.2742
3152 | 43.6234 | 38.1215 | 43.5852
3153 | 42.5279 | 34.2564 | 46.7419
3154 | 44.4774 | 32.8334 | 43.8389
3155 | 42.8001 | 36.8788 | 42.1139
3156 | 40.2872 | 35.0372 | 42.8981
3157 | 42.6758 | 31.8889 | 43.3186
3158 | 44.3134 | 33.9256 | 41.9463
3159 | 42.7136 | 34.9141 | 42.5374
3160 | 43.1473 | 33.5309 | 42.9503
3161 | 42.4066 | 36.1384 | 41.7057
3162 | 41.935 | 36.5193 | 42.9313
3163 | 43.3538 | 35.5543 | 45.2315
3164 | 41.1543 | 32.9639 | 44.4066
3165 | 43.2362 | 34.8192 | 43.1103
3166 | 46.0954 | 34.2516 | 42.4831
3167 | 41.4003 | 35.1888 | 43.596
3168 | 41.9347 | 34.2465 | 44.2707
3169 | 43.8315 | 34.7303 | 44.4884
3170 | 42.9714 | 35.8631 | 42.1337
3171 | 42.2775 | 35.487 | 41.6721
3172 | 41.9539 | 34.255 | 41.4603
3173 | 43.8529 | 33.7484 | 42.1515
3174 | 41.0275 | 35.0865 | 44.1829
3175 | 42.7209 | 36.0614 | 41.1405
3176 | 42.7352 | 35.2192 | 43.2803
3177 | 43.5595 | 34.7984 | 40.1817
3178 | 44.8096 | 32.9893 | 42.7343
3179 | 42.4402 | 33.6901 | 44.2349
3180 | 44.8337 | 34.4128 | 43.7019
3181 | 43.032 | 36.0465 | 41.3316
3182 | 41.5249 | 33.6659 | 45.115
3183 | 41.6093 | 34.9281 | 43.7079
3184 | 44.9237 | 34.8774 | 43.5034
3185 | 42.4526 | 34.3343 | 44.0854
3186 | 43.4671 | 33.5134 | 43.4948
3187 | 40.4886 | 33.291 | 42.2907
3188 | 43.5125 | 34.3595 | 43.3927
3189 | 42.8152 | 33.419 | 43.2021
3190 | 45.1714 | 34.3609 | 43.8123
3191 | 44.4901 | 34.2447 | 45.1727
3192 | 42.9996 | 33.5936 | 43.3823
3193 | 43.0459 | 33.8082 | 43.6155
3194 | 40.5952 | 35.0897 | 42.5347
3195 | 42.2043 | 34.3212 | 45.8173
3196 | 42.9455 | 33.3501 | 42.3123
3197 | 45.2634 | 35.3223 | 45.595
3198 | 41.9441 | 33.1223 | 43.9164
3199 | 41.2675 | 34.005 | 44.2238
3200 | 43.3618 | 33.6197 | 41.4062
3201 | 45.4944 | 34.4562 | 42.4734
3202 | 44.0152 | 34.2917 | 44.8912
3203 | 45.0804 | 33.1156 | 43.2925
3204 | 41.6305 | 35.7934 | 44.2856
3205 | 44.0218 | 32.0872 | 43.577
3206 | 42.9141 | 35.4162 | 44.2594
3207 | 42.4516 | 34.8733 | 42.285
3208 | 43.2422 | 33.5966 | 42.6445
3209 | 44.0925 | 35.0588 | 43.8491
3210 | 43.5687 | 35.3447 | 42.2072
3211 | 42.7011 | 32.7728 | 44.7993
3212 | 42.3076 | 33.5689 | 43.2878
3213 | 44.5488 | 34.4692 | 42.1992
3214 | 42.3015 | 33.9724 | 41.8379
3215 | 42.3784 | 33.1556 | 42.706
3216 | 46.0165 | 35.611 | 45.1996
3217 | 43.7162 | 34.7853 | 44.6831
3218 | 43.9308 | 34.2936 | 39.5203
3219 | 43.5201 | 33.0332 | 43.5504
3220 | 42.9912 | 32.4961 | 41.8121
3221 | 44.6056 | 33.891 | 41.8919
3222 | 43.2187 | 34.1752 | 44.7779
3223 | 42.9194 | 35.5412 | 42.5873
3224 | 44.7877 | 34.9124 | 42.7454
3225 | 42.483 | 35.8459 | 42.5044
3226 | 40.7232 | 34.1317 | 42.6183
3227 | 41.3287 | 35.9373 | 43.5227
3228 | 42.5398 | 32.9384 | 42.5148
3229 | 44.8781 | 32.3447 | 43.0452
3230 | 43.4466 | 34.3098 | 43.7374
3231 | 41.2482 | 34.8607 | 41.3745
3232 | 41.213 | 33.2705 | 44.4118
3233 | 44.2192 | 34.6189 | 43.6395
3234 | 40.9736 | 33.4887 | 45.2615
3235 | 42.321 | 36.1201 | 39.1492
3236 | 42.8902 | 35.5567 | 44.0884
3237 | 44.0223 | 33.4231 | 43.1655
3238 | 42.8863 | 34.5132 | 43.2565
3239 | 46.0281 | 33.5867 | 45.6369
3240 | 43.6521 | 34.9051 | 43.8218
3241 | 43.7887 | 34.5873 | 43.9179
3242 | 41.2392 | 32.8324 | 43.3262
3243 | 41.503 | 35.248 | 44.4462
3244 | 41.5976 | 33.1433 | 43.7707
3245 | 42.0072 | 33.5179 | 44.1853
3246 | 44.5875 | 35.9662 | 43.8871
3247 | 47.1263 | 35.0373 | 40.7749
3248 | 42.3685 | 33.7978 | 42.2868
3249 | 44.0646 | 35.1736 | 42.3394
3250 | 45.0029 | 35.8756 | 41.4902
3251 | 41.5443 | 35.1967 | 40.2141
3252 | 47.019 | 35.9764 | 43.9744
3253 | 42.5137 | 33.798 | 44.9252
3254 | 42.1387 | 35.4364 | 44.4239
3255 | 44.0934 | 33.3413 | 45.6893
3256 | 41.4406 | 34.4523 | 43.9109
3257 | 43.4704 | 35.1238 | 40.607
3258 | 42.0225 | 35.2509 | 44.4437
3259 | 43.6356 | 37.3723 | 42.9146
3260 | 42.518 | 32.6176 | 44.2577
3261 | 42.4865 | 36.506 | 42.7099
3262 | 41.7409 | 36.7636 | 42.1189
3263 | 44.3701 | 34.4988 | 43.4779
3264 | 44.1289 | 31.9262 | 42.4131
3265 | 44.6786 | 35.9152 | 45.604
3266 | 45.8408 | 32.692 | 43.1419
3267 | 43.228 | 33.7905 | 41.4262
3268 | 44.1902 | 35.3091 | 44.9221
3269 | 45.5121 | 36.4735 | 42.5518
3270 | 42.4961 | 35.5159 | 43.0481
3271 | 45.1819 | 33.443 | 43.4703
3272 | 42.6188 | 35.2249 | 45.1118
3273 | 43.8481 | 35.0491 | 42.4706
3274 | 45.0999 | 35.2489 | 43.3423
3275 | 42.1317 | 35.2296 | 42.8508
3276 | 41.8211 | 34.4469 | 43.7924
3277 | 40.6099 | 32.8113 | 40.2489
3278 | 41.1007 | 34.5891 | 43.813
3279 | 40.2972 | 34.5634 | 41.8322
3280 | 42.887 | 33.6622 | 43.054
3281 | 40.7129 | 33.9683 | 44.865
3282 | 42.0447 | 32.5188 | 45.5356
3283 | 44.2883 | 32.0227 | 43.9552
3284 | 46.1081 | 33.483 | 43.4226
3285 | 44.6654 | 35.3363 | 41.1697
3286 | 45.4288 | 36.3483 | 43.3678
3287 | 44.3778 | 33.8756 | 44.2778
3288 | 42.8618 | 33.9898 | 44.1326
3289 | 42.5514 | 35.436 | 43.8364
3290 | 40.6969 | 33.6201 | 42.6237
3291 | 45.2279 | 32.7982 | 43.2973
3292 | 40.8489 | 34.0702 | 42.4989
3293 | 43.2369 | 34.6392 | 44.828
3294 | 45.2491 | 32.4702 | 42.6141
3295 | 42.4081 | 35.1467 | 42.6425
3296 | 46.2941 | 34.5711 | 45.3712
3297 | 41.7455 | 33.726 | 43.2402
3298 | 43.1083 | 34.799 | 41.3442
3299 | 42.9882 | 34.7108 | 40.5247
3300 | 43.0545 | 32.4871 | 45.5806
3301 | 42.2871 | 35.6769 | 42.0005
3302 | 44.5365 | 32.8684 | 46.0817
3303 | 42.4193 | 34.021 | 42.0523
3304 | 40.2455 | 32.746 | 45.6311
3305 | 45.7446 | 35.2591 | 46.4881
3306 | 43.3184 | 33.9289 | 39.7722
3307 | 43.9325 | 35.2394 | 43.9198
3308 | 43.6442 | 36.1699 | 41.235
3309 | 42.9937 | 32.9945 | 41.9992
3310 | 42.5736 | 34.347 | 45.2404
3311 | 45.2017 | 33.2375 | 43.0616
3312 | 44.1095 | 29.965 | 43.4008
3313 | 41.9417 | 34.4757 | 45.7373
3314 | 42.2276 | 34.3778 | 45.6547
3315 | 39.5963 | 35.5401 | 43.4306
3316 | 43.515 | 33.4496 | 41.7094
3317 | 41.0521 | 34.1015 | 44.3204
3318 | 44.8397 | 35.3565 | 44.598
3319 | 41.1941 | 35.9704 | 42.4062
3320 | 42.0778 | 35.2117 | 41.3013
3321 | 43.6305 | 33.8133 | 42.4503
3322 | 46.0494 | 33.4507 | 44.2229
3323 | 43.6798 | 35.0187 | 44.4876
3324 | 42.3885 | 32.0612 | 44.679
3325 | 41.0677 | 33.6046 | 45.3749
3326 | 41.7913 | 35.5687 | 44.8279
3327 | 41.2091 | 34.5892 | 43.7282
3328 | 42.6822 | 35.462 | 43.1604
3329 | 44.3633 | 34.8642 | 40.6504
3330 | 40.8678 | 32.4423 | 42.5775
3331 | 41.9926 | 34.5198 | 41.2321
3332 | 42.6819 | 34.7196 | 44.429
3333 | 43.9844 | 35.0332 | 44.2248
3334 | 45.4637 | 34.2926 | 42.2215
3335 | 43.4693 | 34.3981 | 43.1091
3336 | 43.0625 | 35.4796 | 45.2887
3337 | 40.1914 | 34.4748 | 42.0396
3338 | 43.2309 | 33.6574 | 43.0102
3339 | 42.6243 | 35.2819 | 43.525
3340 | 43.6259 | 35.1653 | 43.7487
3341 | 44.3278 | 35.6228 | 41.2623
3342 | 42.2319 | 35.2565 | 45.46
3343 | 43.0901 | 33.9517 | 43.0687
3344 | 43.3707 | 36.3111 | 41.8938
3345 | 43.6059 | 32.784 | 42.1093
3346 | 40.9864 | 33.8254 | 42.3825
3347 | 45.0725 | 32.8899 | 43.1823
3348 | 43.7376 | 34.3363 | 46.3813
3349 | 43.4357 | 34.4878 | 42.7919
3350 | 42.7102 | 34.5159 | 43.4928
3351 | 46.2143 | 33.927 | 42.4491
3352 | 44.8294 | 36.9152 | 44.6288
3353 | 41.3261 | 33.2247 | 41.1922
3354 | 44.5132 | 30.8933 | 44.7333
3355 | 42.6844 | 34.0956 | 45.0706
3356 | 41.9881 | 36.3666 | 42.0926
3357 | 44.512 | 36.0859 | 41.6684
3358 | 42.3974 | 34.1974 | 41.2454
3359 | 42.7931 | 34.6683 | 44.2006
3360 | 42.4589 | 34.2379 | 43.6968
3361 | 43.3793 | 31.1379 | 43.6631
3362 | 44.0196 | 34.7252 | 41.5731
3363 | 43.4173 | 32.5231 | 44.1995
3364 | 44.4396 | 35.0804 | 42.6826
3365 | 44.7423 | 36.9906 | 45.8926
3366 | 38.6326 | 33.7079 | 46.5798
3367 | 43.3353 | 34.4202 | 42.8641
3368 | 45.3515 | 33.9345 | 42.4879
3369 | 43.4105 | 35.8923 | 41.8676
3370 | 40.937 | 34.5235 | 42.3998
3371 | 43.0594 | 33.2752 | 42.392
3372 | 41.1734 | 35.0309 | 44.2858
3373 | 41.0522 | 32.9207 | 44.4379
3374 | 42.9334 | 34.2348 | 43.6854
3375 | 42.449 | 35.0737 | 44.1697
3376 | 44.5285 | 36.4459 | 42.3793
3377 | 43.9064 | 31.6952 | 44.8104
3378 | 43.9724 | 34.9658 | 43.5921
3379 | 44.1007 | 33.8574 | 44.0783
3380 | 43.0005 | 33.4609 | 43.0022
3381 | 43.0553 | 31.9506 | 42.4287
3382 | 46.3933 | 34.209 | 41.4365
3383 | 42.2541 | 32.2552 | 43.086
3384 | 45.6595 | 34.2508 | 43.3981
3385 | 43.075 | 34.2121 | 43.2319
3386 | 40.3728 | 33.3517 | 41.3263
3387 | 46.792 | 33.5571 | 45.4471
3388 | 44.0108 | 34.4072 | 41.0667
3389 | 40.2763 | 35.5783 | 43.694
3390 | 40.8724 | 33.9249 | 44.628
3391 | 41.4192 | 31.8105 | 44.3715
3392 | 42.4835 | 33.7483 | 46.6982
3393 | 43.1238 | 35.0815 | 41.7986
3394 | 41.0789 | 33.511 | 45.3403
3395 | 42.7937 | 32.972 | 38.9188
3396 | 42.0068 | 34.5993 | 41.2504
3397 | 45.1876 | 36.7063 | 40.7455
3398 | 42.9171 | 33.5475 | 42.2253
3399 | 41.2186 | 36.7055 | 40.0742
3400 | 43.399 | 35.5401 | 43.1596
3401 | 43.3312 | 36.1725 | 41.9621
3402 | 45.1071 | 33.2294 | 40.6192
3403 | 41.782 | 32.8297 | 43.6669
3404 | 43.0053 | 32.8636 | 45.7369
3405 | 45.2553 | 34.8433 | 42.9109
3406 | 42.421 | 35.8401 | 42.9915
3407 | 43.6292 | 33.6032 | 43.5112
3408 | 41.6653 | 34.071 | 44.9807
3409 | 46.4896 | 37.1225 | 46.1409
3410 | 43.7653 | 36.449 | 42.4187
3411 | 41.8766 | 35.0201 | 44.0217
3412 | 44.089 | 34.3652 | 44.276
3413 | 42.4258 | 32.4667 | 42.2264
3414 | 43.9402 | 36.1558 | 43.8047
3415 | 43.4796 | 35.4485 | 42.2464
3416 | 46.0423 | 36.5324 | 44.7173
3417 | 43.3818 | 35.123 | 44.4253
3418 | 42.0753 | 33.5613 | 40.2634
3419 | 43.6665 | 33.8951 | 41.9586
3420 | 40.6667 | 33.9324 | 43.7034
3421 | 42.5738 | 34.8071 | 42.7781
3422 | 44.2158 | 35.6456 | 43.4709
3423 | 44.8127 | 33.8764 | 42.4057
3424 | 44.9608 | 33.0616 | 41.6182
3425 | 44.3795 | 35.4182 | 42.9719
3426 | 40.0631 | 35.243 | 42.8891
3427 | 44.1716 | 36.1908 | 42.8615
3428 | 41.9243 | 34.5177 | 43.8555
3429 | 45.0055 | 35.0353 | 42.2127
3430 | 44.4436 | 35.128 | 44.2647
3431 | 45.6065 | 36.2918 | 43.1444
3432 | 43.7231 | 33.0131 | 42.6714
3433 | 43.4067 | 33.0952 | 40.5465
3434 | 41.1345 | 33.9832 | 43.6648
3435 | 44.032 | 33.3662 | 42.8684
3436 | 42.4125 | 34.36 | 42.9699
3437 | 40.9406 | 34.9867 | 41.1239
3438 | 43.2953 | 35.0481 | 42.2283
3439 | 44.2218 | 33.3766 | 42.7244
3440 | 45.1675 | 35.5343 | 42.8632
3441 | 42.3592 | 33.2942 | 42.6161
3442 | 41.4372 | 33.6501 | 44.8703
3443 | 45.0073 | 34.3892 | 42.5241
3444 | 42.9012 | 35.3232 | 43.2652
3445 | 43.7343 | 35.2842 | 41.7037
3446 | 45.2515 | 31.384 | 41.2824
3447 | 42.2183 | 33.5366 | 43.1176
3448 | 43.249 | 33.4637 | 42.7773
3449 | 46.6642 | 35.0282 | 42.652
3450 | 42.9722 | 32.5876 | 42.8412
3451 | 44.7232 | 34.4133 | 45.5756
3452 | 45.4523 | 33.9345 | 43.4682
3453 | 40.9579 | 33.8865 | 41.886
3454 | 42.1638 | 35.3186 | 42.7855
3455 | 43.8886 | 34.3894 | 45.2668
3456 | 44.785 | 36.3226 | 43.7975
3457 | 43.3347 | 32.5621 | 42.7633
3458 | 42.0132 | 34.6486 | 43.8744
3459 | 41.9434 | 33.5375 | 44.9429
3460 | 43.5239 | 33.5001 | 41.8535
3461 | 44.0591 | 34.118 | 43.7646
3462 | 46.6769 | 32.2344 | 42.6093
3463 | 43.5547 | 36.0497 | 44.3056
3464 | 45.2638 | 34.2532 | 45.3247
3465 | 42.4292 | 34.2547 | 41.5567
3466 | 43.2406 | 36.3512 | 43.8857
3467 | 46.6856 | 33.8258 | 42.078
3468 | 42.6798 | 34.1534 | 41.8501
3469 | 42.7498 | 33.8789 | 43.7143
3470 | 42.0576 | 33.249 | 44.632
3471 | 41.7745 | 32.9719 | 40.154
3472 | 43.326 | 34.3458 | 42.615
3473 | 40.948 | 33.5846 | 42.968
3474 | 43.6057 | 35.2795 | 42.9932
3475 | 43.9497 | 34.76 | 44.0334
3476 | 39.2555 | 35.2019 | 40.9841
3477 | 43.1065 | 32.9445 | 43.4098
3478 | 42.7263 | 35.5381 | 43.7391
3479 | 44.5555 | 35.8893 | 41.7273
3480 | 43.193 | 34.5176 | 40.8963
3481 | 41.8754 | 32.5728 | 42.9402
3482 | 42.3584 | 33.6377 | 43.5402
3483 | 43.6892 | 34.2042 | 43.1186
3484 | 44.0824 | 34.4784 | 43.1505
3485 | 44.8429 | 35.5952 | 41.669
3486 | 44.9173 | 34.4525 | 43.9716
3487 | 44.1723 | 35.0227 | 43.0277
3488 | 45.1193 | 36.297 | 45.1755
3489 | 45.0851 | 32.6281 | 44.1029
3490 | 40.5733 | 33.4935 | 43.533
3491 | 40.1359 | 34.1609 | 46.3408
3492 | 44.4354 | 36.6144 | 44.5277
3493 | 45.855 | 33.5005 | 43.8825
3494 | 44.8859 | 34.4998 | 43.8363
3495 | 45.9281 | 34.8681 | 44.5443
3496 | 41.7133 | 35.1474 | 42.1722
3497 | 45.0773 | 34.2447 | 42.5861
3498 | 43.0248 | 33.1945 | 45.6078
3499 | 42.6711 | 33.3402 | 45.9462
3500 | 40.8655 | 33.6614 | 43.7481
3501 | 42.9175 | 36.3043 | 43.9753
3502 | 45.8407 | 35.9276 | 45.0882
3503 | 40.6405 | 33.5321 | 41.2389
3504 | 43.6972 | 32.2992 | 43.0787
3505 | 46.1432 | 35.3591 | 43.0417
3506 | 42.7895 | 34.8914 | 43.0061
3507 | 43.3896 | 34.8773 | 43.2522
3508 | 43.2185 | 33.4516 | 44.0425
3509 | 40.8636 | 34.3404 | 41.9287
3510 | 44.438 | 32.9241 | 41.5529
3511 | 44.7531 | 34.0098 | 46.1102
3512 | 42.9562 | 36.5474 | 42.2305
3513 | 42.5762 | 32.5921 | 43.5597
3514 | 42.7145 | 36.7066 | 43.4177
3515 | 43.3676 | 32.9629 | 45.0848
3516 | 43.1273 | 34.9304 | 43.7428
3517 | 42.6658 | 34.7431 | 42.0061
3518 | 43.0461 | 34.645 | 43.072
3519 | 44.1395 | 34.1024 | 42.5781
3520 | 45.0648 | 34.846 | 44.0377
3521 | 42.5405 | 37.0115 | 42.6771
3522 | 42.9606 | 33.0367 | 43.229
3523 | 41.7581 | 33.5382 | 43.5408
3524 | 41.1386 | 33.2784 | 43.3882
3525 | 47.2176 | 33.6186 | 42.7228
3526 | 44.2401 | 34.3716 | 43.5567
3527 | 42.644 | 33.9791 | 41.7776
3528 | 42.6479 | 32.9119 | 43.1841
3529 | 42.873 | 33.8965 | 44.3476
3530 | 41.1176 | 32.6184 | 43.9051
3531 | 42.5697 | 34.2754 | 41.7016
3532 | 43.2062 | 34.4249 | 42.0726
3533 | 43.1433 | 32.3216 | 42.2164
3534 | 43.3347 | 33.1169 | 43.6831
3535 | 46.1293 | 32.0315 | 42.9195
3536 | 45.7078 | 34.9436 | 41.3907
3537 | 44.7505 | 34.4928 | 41.7115
3538 | 43.8327 | 36.228 | 42.3831
3539 | 46.1582 | 36.8537 | 41.8735
3540 | 45.2154 | 35.3359 | 44.798
3541 | 44.4138 | 36.2591 | 42.1578
3542 | 44.6508 | 33.4779 | 39.4254
3543 | 42.6605 | 34.7443 | 40.5321
3544 | 44.0992 | 33.5518 | 42.9831
3545 | 42.9799 | 34.0757 | 44.1008
3546 | 44.7069 | 34.6629 | 40.367
3547 | 41.2379 | 34.2129 | 39.7874
3548 | 42.5734 | 35.6362 | 42.315
3549 | 44.8374 | 33.4487 | 44.1619
3550 | 47.8612 | 32.9461 | 43.6014
3551 | 44.4706 | 32.8463 | 45.6015
3552 | 43.9067 | 31.7971 | 41.0486
3553 | 41.0418 | 33.7937 | 41.8974
3554 | 46.4859 | 35.9671 | 42.7389
3555 | 42.792 | 34.4029 | 46.3105
3556 | 42.1107 | 36.6238 | 45.0318
3557 | 41.9603 | 31.7598 | 41.7075
3558 | 41.8029 | 32.5522 | 44.3653
3559 | 39.4005 | 34.2179 | 43.965
3560 | 46.2596 | 33.7872 | 42.3857
3561 | 40.6336 | 32.1607 | 45.0349
3562 | 40.9887 | 34.0976 | 42.4565
3563 | 42.1699 | 33.7293 | 46.6489
3564 | 44.8218 | 34.9343 | 43.2676
3565 | 40.7772 | 33.5559 | 42.7904
3566 | 41.6702 | 33.253 | 42.3699
3567 | 46.4768 | 33.2272 | 45.8029
3568 | 43.5528 | 34.2921 | 43.4291
3569 | 42.7572 | 34.4073 | 41.7131
3570 | 45.3538 | 34.449 | 44.4715
3571 | 42.2176 | 35.6696 | 42.1292
3572 | 42.4597 | 33.9978 | 46.1627
3573 | 42.7433 | 34.1952 | 42.0924
3574 | 43.5866 | 34.7581 | 45.07
3575 | 40.3521 | 34.7805 | 42.906
3576 | 43.2739 | 36.401 | 43.2611
3577 | 43.141 | 34.0626 | 44.3972
3578 | 43.2746 | 33.7904 | 43.4392
3579 | 44.0794 | 35.0779 | 42.4584
3580 | 44.0935 | 33.5003 | 44.8986
3581 | 40.3619 | 34.0072 | 44.013
3582 | 44.7608 | 34.3063 | 42.4239
3583 | 43.0413 | 32.6679 | 42.2986
3584 | 43.9523 | 36.9853 | 44.4876
3585 | 42.6673 | 32.6212 | 45.7998
3586 | 43.5713 | 34.9202 | 42.2042
3587 | 43.6603 | 34.1586 | 43.3381
3588 | 42.8674 | 36.4694 | 42.2418
3589 | 43.1282 | 33.3803 | 42.8282
3590 | 44.1995 | 33.0094 | 44.6121
3591 | 45.0827 | 33.5158 | 41.2819
3592 | 42.2235 | 35.3532 | 42.9308
3593 | 45.0826 | 35.3225 | 45.5981
3594 | 42.737 | 35.3493 | 42.6544
3595 | 45.1006 | 35.6641 | 43.2007
3596 | 43.5184 | 34.0283 | 45.0384
3597 | 41.5725 | 34.5675 | 43.9613
3598 | 43.1702 | 34.8535 | 43.2329
3599 | 43.4752 | 34.3218 | 44.1084
3600 | 44.2798 | 33.2684 | 41.0084
3601 | 42.2595 | 34.8465 | 41.6146
3602 | 44.3592 | 34.5144 | 42.3858
3603 | 43.4179 | 35.2963 | 43.3695
3604 | 43.7937 | 33.845 | 44.6218
3605 | 42.9888 | 33.9588 | 43.6678
3606 | 43.4439 | 34.5376 | 41.8251
3607 | 46.9731 | 36.4207 | 45.7628
3608 | 44.3501 | 35.9209 | 41.551
3609 | 44.4403 | 34.9276 | 40.6736
3610 | 43.1379 | 33.2416 | 42.2421
3611 | 43.1594 | 33.4237 | 39.8263
3612 | 42.2566 | 35.2192 | 42.4629
3613 | 43.344 | 34.9133 | 42.2504
3614 | 43.0911 | 33.0468 | 41.6628
3615 | 43.1492 | 35.109 | 40.7364
3616 | 41.3459 | 34.5509 | 43.1735
3617 | 43.2226 | 34.5733 | 42.3681
3618 | 42.3802 | 33.2471 | 43.8325
3619 | 42.998 | 34.1606 | 42.1367
3620 | 43.0739 | 34.5092 | 40.6374
3621 | 43.3792 | 35.4693 | 42.2985
3622 | 45.9949 | 33.4604 | 42.9509
3623 | 40.597 | 36.5789 | 43.6322
3624 | 40.2962 | 32.508 | 42.814
3625 | 40.4571 | 34.6074 | 44.0344
3626 | 46.3652 | 31.9826 | 42.4321
3627 | 42.0581 | 34.3257 | 39.2662
3628 | 42.43 | 34.79 | 44.2523
3629 | 41.2655 | 32.155 | 44.8589
3630 | 45.1301 | 32.5198 | 43.3142
3631 | 42.9817 | 33.9701 | 43.7218
3632 | 42.0185 | 34.8812 | 42.0769
3633 | 37.8793 | 34.2549 | 45.6288
3634 | 41.7564 | 33.2125 | 44.8971
3635 | 43.1249 | 36.0477 | 44.9306
3636 | 41.6895 | 33.9507 | 43.8686
3637 | 41.5769 | 32.781 | 42.8219
3638 | 43.8117 | 34.614 | 44.7324
3639 | 44.335 | 35.198 | 44.5201
3640 | 43.7835 | 34.8626 | 43.0904
3641 | 44.6094 | 34.9968 | 43.1358
3642 | 43.9076 | 35.6317 | 45.0404
3643 | 43.7824 | 34.6725 | 43.3539
3644 | 42.3961 | 34.5272 | 41.4683
3645 | 42.7281 | 35.1068 | 41.6235
3646 | 43.7735 | 34.2869 | 40.9707
3647 | 43.573 | 33.9721 | 45.2163
3648 | 40.0858 | 33.7149 | 46.0961
3649 | 42.0438 | 33.8504 | 43.4171
3650 | 40.6813 | 33.7417 | 42.4621
3651 | 45.0371 | 35.2078 | 43.3546
3652 | 41.4895 | 35.6328 | 45.4756
3653 | 44.4053 | 35.6248 | 42.5113
3654 | 45.0122 | 32.8583 | 46.0559
3655 | 44.5129 | 33.2799 | 43.4716
3656 | 40.9652 | 35.4863 | 41.6223
3657 | 42.6346 | 34.9911 | 43.0618
3658 | 44.3911 | 34.3655 | 43.7083
3659 | 43.1133 | 35.3621 | 40.5975
3660 | 45.481 | 34.6452 | 44.3538
3661 | 43.5107 | 34.6748 | 42.093
3662 | 43.7566 | 35.0352 | 41.8753
3663 | 40.6968 | 36.002 | 42.0993
3664 | 43.5389 | 36.6805 | 44.5082
3665 | 43.9918 | 33.8404 | 43.6339
3666 | 44.5553 | 35.3587 | 42.0377
3667 | 42.8643 | 33.9372 | 40.8766
3668 | 42.0396 | 34.0963 | 41.9293
3669 | 43.0998 | 36.8633 | 42.5803
3670 | 41.42 | 35.9537 | 42.6675
3671 | 43.8918 | 34.8114 | 45.8835
3672 | 43.6062 | 34.7742 | 44.8654
3673 | 41.7221 | 33.6109 | 43.3037
3674 | 43.6776 | 34.5901 | 44.6812
3675 | 43.4088 | 34.8271 | 43.1756
3676 | 42.5698 | 31.6817 | 43.7135
3677 | 39.1864 | 34.2971 | 44.0245
3678 | 43.7603 | 34.3778 | 40.9018
3679 | 44.6944 | 35.6082 | 41.0292
3680 | 45.0578 | 34.2536 | 45.5846
3681 | 45.3102 | 32.8952 | 40.7014
3682 | 43.571 | 34.9166 | 44.5254
3683 | 42.6495 | 34.727 | 42.6452
3684 | 43.0378 | 34.8504 | 42.8741
3685 | 41.4157 | 33.7025 | 45.1961
3686 | 44.7043 | 35.1662 | 42.9192
3687 | 42.122 | 37.7506 | 44.8309
3688 | 44.3431 | 34.8187 | 42.0342
3689 | 45.5786 | 34.2323 | 45.4054
3690 | 40.4225 | 34.2251 | 40.819
3691 | 44.941 | 33.0603 | 43.5624
3692 | 42.8161 | 35.4637 | 44.3686
3693 | 43.9871 | 33.4534 | 43.5786
3694 | 42.1864 | 33.7309 | 40.7444
3695 | 45.5828 | 35.4775 | 44.0284
3696 | 45.0192 | 34.915 | 43.3809
3697 | 42.5709 | 36.5747 | 43.2295
3698 | 44.445 | 34.1448 | 45.7354
3699 | 46.2699 | 33.7857 | 43.6263
3700 | 44.4407 | 31.2298 | 43.0806
3701 | 43.0079 | 34.1323 | 42.037
3702 | 45.4892 | 35.0571 | 44.5991
3703 | 43.7804 | 34.6711 | 41.7135
3704 | 43.8638 | 33.8398 | 40.7746
3705 | 42.6665 | 35.0211 | 43.949
3706 | 42.8854 | 36.8671 | 42.7606
3707 | 44.8524 | 34.2691 | 42.9128
3708 | 42.881 | 33.7546 | 44.9444
3709 | 42.4658 | 37.5587 | 44.8617
3710 | 43.1172 | 33.2811 | 44.413
3711 | 40.1721 | 34.8575 | 44.5689
3712 | 44.2494 | 32.1809 | 44.3562
3713 | 41.9405 | 33.5903 | 42.525
3714 | 42.1045 | 35.0098 | 42.3741
3715 | 46.6127 | 34.1528 | 43.1228
3716 | 45.9177 | 35.933 | 43.8249
3717 | 42.2161 | 33.763 | 42.1841
3718 | 43.3104 | 35.1491 | 46.8385
3719 | 42.2681 | 34.9809 | 42.9447
3720 | 44.0091 | 34.1856 | 39.9644
3721 | 43.6965 | 34.699 | 41.0667
3722 | 44.7174 | 32.4947 | 42.7195
3723 | 42.2491 | 34.858 | 42.1017
3724 | 41.9154 | 33.319 | 44.2845
3725 | 42.8405 | 34.0034 | 45.5032
3726 | 41.7349 | 34.7143 | 44.4098
3727 | 44.2131 | 36.2645 | 44.8537
3728 | 42.521 | 35.1791 | 42.5882
3729 | 44.1572 | 32.7619 | 44.3643
3730 | 42.9847 | 33.5193 | 43.7437
3731 | 46.3064 | 34.2627 | 44.1875
3732 | 41.6636 | 33.804 | 44.6921
3733 | 42.3064 | 33.5956 | 43.1318
3734 | 40.7544 | 33.3522 | 43.7321
3735 | 41.7632 | 34.7371 | 45.7429
3736 | 43.043 | 34.3784 | 43.8087
3737 | 43.0682 | 34.1522 | 41.5039
3738 | 43.4357 | 37.2088 | 43.4312
3739 | 46.2146 | 35.183 | 41.0624
3740 | 43.8587 | 32.2503 | 42.7612
3741 | 44.9958 | 35.5326 | 41.6334
3742 | 42.5747 | 35.2176 | 41.9434
3743 | 41.5588 | 33.6707 | 44.1946
3744 | 42.2245 | 33.7317 | 41.5413
3745 | 42.6268 | 34.4464 | 43.3491
3746 | 43.7624 | 35.6733 | 43.7714
3747 | 45.0863 | 35.2441 | 45.8796
3748 | 44.3383 | 35.3061 | 42.8775
3749 | 45.2355 | 33.6645 | 44.3544
3750 | 43.0309 | 31.4345 | 44.7447
3751 | 42.0617 | 36.6099 | 39.705
3752 | 41.1941 | 32.9512 | 43.0034
3753 | 45.9221 | 35.1647 | 46.9062
3754 | 42.137 | 35.4892 | 41.6532
3755 | 41.0645 | 34.9259 | 44.9529
3756 | 42.5281 | 36.007 | 43.2364
3757 | 43.7752 | 33.3851 | 43.6455
3758 | 40.7052 | 34.7057 | 44.1059
3759 | 38.5295 | 33.6011 | 42.5741
3760 | 43.9153 | 34.5687 | 42.2611
3761 | 45.3385 | 34.9693 | 41.2471
3762 | 43.6707 | 36.2055 | 43.5922
3763 | 44.7789 | 34.3494 | 44.0627
3764 | 43.7907 | 36.3764 | 44.5277
3765 | 41.6423 | 33.808 | 44.1366
3766 | 43.6553 | 34.432 | 43.7961
3767 | 44.3706 | 33.3735 | 42.0282
3768 | 43.7251 | 34.5693 | 40.7839
3769 | 41.6769 | 33.0388 | 42.8226
3770 | 45.6271 | 34.9874 | 43.5282
3771 | 43.9265 | 33.773 | 43.1201
3772 | 43.8594 | 33.8716 | 46.8641
3773 | 43.5007 | 34.7307 | 42.5772
3774 | 44.0998 | 35.571 | 41.0835
3775 | 44.0604 | 34.8617 | 42.5175
3776 | 45.45 | 35.5687 | 42.4166
3777 | 41.857 | 33.7785 | 40.6008
3778 | 41.4696 | 36.2577 | 41.2852
3779 | 42.1622 | 32.9396 | 45.985
3780 | 43.5466 | 35.1294 | 42.1831
3781 | 44.74 | 34.191 | 42.6905
3782 | 41.7446 | 35.9536 | 44.0816
3783 | 43.8787 | 33.6637 | 46.9241
3784 | 45.1997 | 33.6874 | 43.4261
3785 | 42.1947 | 34.8848 | 42.6818
3786 | 42.7056 | 34.1646 | 45.6487
3787 | 43.5483 | 33.2703 | 43.5654
3788 | 42.2609 | 36.2999 | 45.0879
3789 | 42.9795 | 31.2785 | 42.048
3790 | 43.7597 | 33.3166 | 41.989
3791 | 42.5594 | 34.8464 | 44.8387
3792 | 40.6589 | 34.9275 | 45.4284
3793 | 41.1091 | 35.5985 | 43.8795
3794 | 41.8737 | 33.388 | 43.3654
3795 | 45.3015 | 33.6086 | 43.1234
3796 | 39.0476 | 36.0126 | 44.9463
3797 | 45.1471 | 34.8714 | 43.8632
3798 | 43.9208 | 33.7356 | 42.4603
3799 | 43.7667 | 33.5313 | 44.3973
3800 | 44.353 | 33.8753 | 42.5584
3801 | 41.2463 | 32.1812 | 42.3093
3802 | 44.5619 | 34.5424 | 43.2151
3803 | 43.756 | 36.201 | 42.3315
3804 | 45.946 | 36.158 | 41.4763
3805 | 42.6188 | 33.0547 | 46.2588
3806 | 43.6051 | 36.2387 | 45.8664
3807 | 43.6363 | 33.3223 | 43.8453
3808 | 40.6239 | 34.7459 | 43.6532
3809 | 39.9832 | 33.4156 | 44.0238
3810 | 45.3564 | 33.6938 | 42.3146
3811 | 44.8418 | 36.0004 | 41.9988
3812 | 43.9865 | 34.0804 | 44.0251
3813 | 43.0065 | 34.7232 | 43.1004
3814 | 42.7852 | 33.1909 | 43.966
3815 | 46.1294 | 33.2768 | 42.2529
3816 | 41.99 | 35.9707 | 44.3625
3817 | 41.7929 | 35.0491 | 41.6459
3818 | 43.586 | 37.414 | 42.9871
3819 | 44.5652 | 32.1168 | 42.6949
3820 | 43.3129 | 35.3129 | 42.9314
3821 | 43.8247 | 33.8072 | 40.5075
3822 | 43.6671 | 34.4029 | 43.3061
3823 | 42.5331 | 34.879 | 40.5228
3824 | 44.0832 | 33.8076 | 45.4304
3825 | 43.1106 | 37.444 | 43.9616
3826 | 42.6182 | 33.8281 | 43.3577
3827 | 44.0306 | 34.7194 | 42.1355
3828 | 43.9804 | 31.6788 | 44.3571
3829 | 45.253 | 34.0456 | 43.9056
3830 | 44.7913 | 35.1387 | 42.2517
3831 | 45.7363 | 33.1689 | 43.3678
3832 | 45.1645 | 34.1241 | 46.4217
3833 | 43.1393 | 34.7016 | 44.7845
3834 | 44.9349 | 30.9717 | 42.9451
3835 | 41.6752 | 33.2166 | 43.0098
3836 | 46.8728 | 33.3114 | 42.5336
3837 | 45.37 | 34.291 | 41.9242
3838 | 40.1542 | 36.0111 | 43.0625
3839 | 42.5391 | 34.4919 | 42.6151
3840 | 41.9643 | 36.3095 | 41.8876
3841 | 42.5616 | 34.3872 | 42.7698
3842 | 41.9862 | 33.1803 | 44.8045
3843 | 44.0354 | 35.934 | 44.421
3844 | 42.9134 | 33.4154 | 42.4189
3845 | 43.8956 | 34.4887 | 43.301
3846 | 42.4241 | 34.5927 | 42.6803
3847 | 41.768 | 35.3364 | 43.8512
3848 | 44.3756 | 33.405 | 46.773
3849 | 43.4164 | 34.0989 | 42.2381
3850 | 40.3084 | 33.8418 | 43.3034
3851 | 44.2344 | 35.2114 | 41.8156
3852 | 43.5407 | 34.8411 | 43.1544
3853 | 42.8626 | 34.4134 | 40.8959
3854 | 41.7331 | 31.0594 | 43.3871
3855 | 44.6577 | 34.8356 | 43.7951
3856 | 42.392 | 35.1258 | 44.8211
3857 | 42.9689 | 33.5167 | 42.0691
3858 | 42.8036 | 34.264 | 44.6223
3859 | 44.5082 | 32.3365 | 43.4627
3860 | 41.0284 | 34.7019 | 40.3905
3861 | 44.0902 | 33.8489 | 42.6517
3862 | 40.436 | 36.2813 | 41.7992
3863 | 45.295 | 34.0065 | 41.0902
3864 | 42.4831 | 35.7291 | 46.7338
3865 | 40.1264 | 32.4639 | 44.4913
3866 | 45.4847 | 35.236 | 41.5303
3867 | 43.1107 | 35.2889 | 44.1363
3868 | 43.1607 | 33.2928 | 44.7384
3869 | 43.8138 | 35.1617 | 41.11
3870 | 43.3521 | 33.6633 | 43.5766
3871 | 42.6157 | 31.12 | 44.0886
3872 | 41.4122 | 33.1067 | 43.0909
3873 | 43.4791 | 34.9417 | 42.7031
3874 | 42.7435 | 35.2476 | 44.6456
3875 | 42.65 | 33.7307 | 41.4531
3876 | 44.4519 | 34.6038 | 44.9183
3877 | 42.6718 | 34.2585 | 44.0048
3878 | 41.5963 | 33.224 | 44.7169
3879 | 44.9415 | 34.1699 | 45.0361
3880 | 41.6161 | 34.8178 | 42.8444
3881 | 45.0043 | 33.4988 | 45.881
3882 | 43.6787 | 34.3507 | 43.5149
3883 | 42.2563 | 33.4933 | 43.7244
3884 | 42.6866 | 34.7101 | 42.3267
3885 | 44.9109 | 34.7264 | 44.3559
3886 | 42.9066 | 35.4073 | 46.3444
3887 | 41.8212 | 33.9706 | 43.9107
3888 | 44.7988 | 34.5028 | 44.2211
3889 | 40.5615 | 33.266 | 43.008
3890 | 41.9647 | 35.5018 | 44.8509
3891 | 43.5109 | 37.1747 | 41.7216
3892 | 42.4476 | 32.9589 | 43.6614
3893 | 42.7471 | 36.6557 | 42.4136
3894 | 45.065 | 32.5493 | 43.7251
3895 | 42.4712 | 35.9271 | 44.4953
3896 | 44.7395 | 35.8184 | 42.2804
3897 | 42.4763 | 33.2414 | 44.8571
3898 | 45.2153 | 35.8173 | 41.3346
3899 | 39.5858 | 35.7765 | 42.3582
3900 | 43.8676 | 36.2299 | 45.1683
3901 | 44.8461 | 33.3683 | 43.0136
3902 | 42.8937 | 34.0156 | 42.0329
3903 | 42.7591 | 33.5995 | 41.6985
3904 | 40.6 | 37.0106 | 43.7536
3905 | 41.5801 | 31.8842 | 43.6715
3906 | 41.7326 | 33.4221 | 43.3479
3907 | 44.2699 | 35.6841 | 46.0339
3908 | 46.5656 | 33.1791 | 43.9617
3909 | 44.6292 | 35.1579 | 44.1277
3910 | 42.8964 | 33.6758 | 43.0272
3911 | 41.7291 | 32.1441 | 43.1892
3912 | 40.9731 | 35.2077 | 45.1743
3913 | 42.5815 | 32.4095 | 44.2476
3914 | 42.8178 | 33.2653 | 42.5292
3915 | 42.6457 | 34.918 | 42.1667
3916 | 42.8528 | 34.2413 | 43.8281
3917 | 42.9691 | 35.5839 | 42.0748
3918 | 44.7824 | 33.9596 | 42.2783
3919 | 44.2791 | 34.465 | 43.0789
3920 | 42.2441 | 32.0498 | 39.7419
3921 | 41.5738 | 33.9861 | 42.1665
3922 | 44.4101 | 33.2748 | 41.9186
3923 | 42.0199 | 36.2102 | 44.3981
3924 | 43.1446 | 34.9332 | 42.9324
3925 | 41.761 | 32.1982 | 42.6599
3926 | 46.0126 | 33.6561 | 42.656
3927 | 42.8268 | 33.1125 | 44.4005
3928 | 44.4257 | 34.4162 | 46.1847
3929 | 43.5027 | 36.9584 | 42.9521
3930 | 44.2855 | 33.8387 | 46.3726
3931 | 42.0397 | 33.2898 | 45.0103
3932 | 42.8123 | 34.3822 | 43.2354
3933 | 44.3879 | 33.0046 | 42.6295
3934 | 41.946 | 32.0344 | 46.3889
3935 | 45.534 | 35.5334 | 44.8456
3936 | 43.1777 | 35.4488 | 45.3684
3937 | 44.5379 | 36.6558 | 43.1678
3938 | 45.0225 | 35.1319 | 41.9833
3939 | 44.6362 | 34.6198 | 40.9445
3940 | 43.0084 | 35.2618 | 44.2216
3941 | 44.0979 | 32.3312 | 43.3373
3942 | 44.266 | 33.3492 | 43.5669
3943 | 44.6072 | 33.1279 | 40.3444
3944 | 40.5129 | 34.4714 | 41.909
3945 | 43.6126 | 34.6121 | 40.8143
3946 | 43.7431 | 33.5129 | 41.9602
3947 | 43.7533 | 34.4639 | 42.8597
3948 | 43.6333 | 35.4857 | 42.886
3949 | 41.5196 | 35.0715 | 42.2937
3950 | 43.9628 | 31.8738 | 45.3592
3951 | 39.935 | 33.2452 | 43.7341
3952 | 44.3319 | 34.5216 | 43.4457
3953 | 44.9179 | 33.8242 | 41.3864
3954 | 40.0108 | 36.5362 | 40.1626
3955 | 41.8758 | 34.2676 | 43.8595
3956 | 41.4907 | 33.6573 | 41.4044
3957 | 46.185 | 33.7144 | 42.176
3958 | 42.404 | 34.2144 | 44.5419
3959 | 41.4808 | 33.4244 | 43.4534
3960 | 45.8054 | 33.8742 | 43.1562
3961 | 41.2947 | 33.6816 | 42.9846
3962 | 42.6382 | 33.1804 | 41.0526
3963 | 45.2798 | 34.2024 | 42.543
3964 | 42.8301 | 34.6323 | 42.7906
3965 | 46.5942 | 34.9094 | 44.196
3966 | 42.8309 | 35.2019 | 44.1669
3967 | 42.9533 | 35.0061 | 46.6946
3968 | 43.3239 | 33.6932 | 42.9544
3969 | 43.5683 | 33.9424 | 40.7309
3970 | 43.747 | 33.7121 | 45.3422
3971 | 45.6691 | 34.1822 | 43.1786
3972 | 43.1585 | 34.1294 | 44.9931
3973 | 42.6309 | 34.4229 | 43.9239
3974 | 42.9284 | 35.2295 | 42.5438
3975 | 44.1297 | 34.5575 | 42.981
3976 | 44.6751 | 33.6952 | 44.3118
3977 | 43.1844 | 34.4516 | 40.699
3978 | 43.492 | 34.0229 | 43.3653
3979 | 43.8199 | 33.6981 | 44.8232
3980 | 43.679 | 35.4017 | 41.9191
3981 | 43.2974 | 36.6101 | 43.1122
3982 | 44.2178 | 35.6189 | 45.1285
3983 | 44.7665 | 35.3836 | 45.2614
3984 | 45.3189 | 33.174 | 43.9774
3985 | 44.0328 | 32.912 | 41.3419
3986 | 46.0416 | 36.0468 | 44.362
3987 | 44.3628 | 34.6299 | 46.4167
3988 | 41.4525 | 35.5907 | 42.7622
3989 | 41.7016 | 37.9656 | 44.3946
3990 | 44.8756 | 34.6897 | 43.2997
3991 | 41.7699 | 34.5875 | 42.7062
3992 | 38.6231 | 34.8307 | 42.0989
3993 | 41.6088 | 34.8725 | 43.2693
3994 | 43.2306 | 34.1577 | 42.6971
3995 | 40.198 | 34.8412 | 41.8642
3996 | 42.9154 | 34.1449 | 43.5942
3997 | 43.6613 | 32.8747 | 44.6446
3998 | 45.0155 | 34.9295 | 41.4914
3999 | 42.2023 | 33.8336 | 44.5283
4000 | 43.8437 | 32.0669 | 43.4808
4001 | 43.925 | 35.1764 | 45.6487
4002 | 43.9835 | 33.8957 | 41.2466
4003 | 41.7098 | 34.9534 | 42.1937
4004 | 45.3697 | 32.2815 | 44.9477
4005 | 44.0317 | 35.3894 | 45.1878
4006 | 44.2934 | 34.9362 | 45.2453
4007 | 42.0824 | 34.0526 | 42.8284
4008 | 43.7841 | 34.5406 | 42.7396
4009 | 41.397 | 34.7413 | 41.8464
4010 | 42.9214 | 33.8331 | 44.2582
4011 | 42.7362 | 32.9018 | 42.9371
4012 | 42.0706 | 33.7589 | 43.9754
4013 | 44.0166 | 34.389 | 43.397
4014 | 44.2502 | 34.4733 | 44.0425
4015 | 43.6714 | 33.8773 | 42.0885
4016 | 41.2976 | 34.3656 | 40.3087
4017 | 43.0088 | 36.1896 | 41.7542
4018 | 40.5308 | 35.1111 | 42.4811
4019 | 46.2048 | 32.6452 | 41.6896
4020 | 44.656 | 34.9081 | 41.9023
4021 | 45.7056 | 33.3723 | 43.5135
4022 | 45.6166 | 34.8602 | 42.8121
4023 | 45.3977 | 36.2676 | 44.8545
4024 | 45.7106 | 35.4513 | 43.7651
4025 | 43.0218 | 37.6202 | 43.8516
4026 | 41.9016 | 34.3744 | 45.2038
4027 | 45.4609 | 33.2879 | 45.5586
4028 | 46.1097 | 35.509 | 42.0216
4029 | 44.2961 | 36.7448 | 45.2653
4030 | 44.2601 | 34.2652 | 41.2998
4031 | 43.7923 | 35.2095 | 45.2536
4032 | 41.6434 | 33.5222 | 42.8206
4033 | 43.8812 | 31.9062 | 42.6975
4034 | 45.073 | 34.7486 | 42.2414
4035 | 42.4744 | 34.7115 | 42.1928
4036 | 42.9734 | 32.2687 | 41.4297
4037 | 41.8858 | 32.6861 | 41.0111
4038 | 44.01 | 34.1809 | 42.1029
4039 | 42.2674 | 33.8026 | 41.8777
4040 | 42.9431 | 33.3627 | 41.1204
4041 | 43.549 | 35.0059 | 41.8565
4042 | 43.7889 | 33.5811 | 39.7424
4043 | 44.9353 | 34.5861 | 42.5441
4044 | 41.7493 | 33.4693 | 41.9091
4045 | 41.1791 | 35.9642 | 44.1858
4046 | 44.2368 | 33.9308 | 42.8513
4047 | 47.1975 | 34.007 | 43.4441
4048 | 40.7017 | 35.3588 | 42.2069
4049 | 42.2891 | 34.6507 | 41.5177
4050 | 46.249 | 34.6247 | 45.0262
4051 | 43.8489 | 33.8778 | 41.6942
4052 | 41.3934 | 33.8387 | 42.6494
4053 | 43.2861 | 31.9333 | 44.7583
4054 | 44.5931 | 34.2733 | 45.5791
4055 | 43.1583 | 34.2601 | 41.194
4056 | 44.6336 | 36.0625 | 41.5106
4057 | 43.2835 | 35.3481 | 40.8707
4058 | 42.1324 | 33.7244 | 43.1252
4059 | 42.5028 | 34.6244 | 42.7757
4060 | 42.3094 | 31.6388 | 43.6142
4061 | 43.1722 | 34.2827 | 44.2046
4062 | 43.0143 | 34.7315 | 43.5121
4063 | 41.5408 | 32.4196 | 43.9445
4064 | 43.2028 | 33.6795 | 42.3451
4065 | 43.9383 | 35.6373 | 41.8944
4066 | 40.7292 | 35.8548 | 44.3434
4067 | 42.2718 | 34.7989 | 41.8966
4068 | 46.5127 | 34.7237 | 44.6648
4069 | 44.3666 | 33.3557 | 43.5735
4070 | 42.7598 | 35.9455 | 46.449
4071 | 43.1008 | 32.6775 | 45.8783
4072 | 44.5531 | 35.0331 | 43.2643
4073 | 43.9758 | 34.0676 | 43.7661
4074 | 42.3594 | 34.6446 | 45.7934
4075 | 45.0001 | 34.8433 | 43.81
4076 | 44.3794 | 31.9511 | 41.6767
4077 | 41.6542 | 32.8658 | 44.0264
4078 | 44.3102 | 33.6676 | 43.7768
4079 | 43.3064 | 34.8643 | 40.6662
4080 | 42.7796 | 35.0155 | 43.0969
4081 | 40.4125 | 36.1901 | 43.9897
4082 | 42.7862 | 33.2363 | 44.4073
4083 | 41.309 | 33.2258 | 42.281
4084 | 45.786 | 33.9212 | 44.7503
4085 | 44.2036 | 35.6583 | 44.3532
4086 | 43.5163 | 35.3077 | 40.8898
4087 | 42.8009 | 34.9116 | 42.6753
4088 | 43.7667 | 33.9609 | 42.5899
4089 | 43.252 | 34.5319 | 41.2469
4090 | 43.1862 | 33.4028 | 41.6634
4091 | 44.9481 | 35.3466 | 41.3554
4092 | 43.1829 | 32.6106 | 43.4701
4093 | 40.9736 | 34.885 | 42.4274
4094 | 43.0577 | 35.8618 | 43.5714
4095 | 45.3078 | 34.7804 | 44.1815
4096 | 41.1974 | 33.9892 | 45.8172
4097 | 45.6764 | 33.8387 | 45.1105
4098 | 41.7611 | 34.0944 | 41.4737
4099 | 43.4605 | 33.5169 | 45.0192
4100 | 44.5594 | 35.5935 | 43.2081
4101 | 42.5363 | 32.0472 | 43.5884
4102 | 43.41 | 32.1222 | 43.1876
4103 | 42.2547 | 35.3009 | 41.1717
4104 | 39.4788 | 33.023 | 41.7495
4105 | 41.4604 | 34.1431 | 45.1983
4106 | 42.7116 | 34.6741 | 41.8479
4107 | 41.7872 | 35.5783 | 44.0148
4108 | 40.332 | 33.7513 | 40.5894
4109 | 41.8917 | 33.3854 | 41.6022
4110 | 41.6901 | 33.4835 | 44.9238
4111 | 40.6226 | 34.6536 | 42.1675
4112 | 42.7428 | 34.7159 | 42.2175
4113 | 45.0633 | 33.7622 | 45.8046
4114 | 43.4119 | 33.8126 | 39.8001
4115 | 46.7084 | 35.0943 | 43.0574
4116 | 44.3187 | 34.7337 | 42.3372
4117 | 44.4845 | 31.8357 | 43.8261
4118 | 45.0385 | 33.8052 | 43.2257
4119 | 43.4715 | 33.7553 | 43.9507
4120 | 43.3649 | 32.8758 | 45.5851
4121 | 44.4029 | 32.143 | 44.6575
4122 | 44.1005 | 32.0703 | 43.7313
4123 | 42.6101 | 34.597 | 41.067
4124 | 40.932 | 32.8806 | 43.4812
4125 | 42.9318 | 35.6766 | 42.8509
4126 | 42.3393 | 33.9097 | 41.7547
4127 | 42.0467 | 34.8185 | 40.7665
4128 | 43.3269 | 34.9296 | 44.9068
4129 | 44.8343 | 35.1238 | 44.0293
4130 | 42.3112 | 34.4151 | 44.5088
4131 | 44.2701 | 33.104 | 42.9184
4132 | 41.738 | 37.8249 | 43.0392
4133 | 43.2218 | 34.5417 | 41.3171
4134 | 43.218 | 32.4379 | 41.8912
4135 | 42.0666 | 32.891 | 42.6787
4136 | 45.896 | 34.5895 | 43.0249
4137 | 44.5644 | 33.1103 | 40.2813
4138 | 44.3723 | 33.8539 | 43.1953
4139 | 43.3142 | 31.6861 | 45.111
4140 | 44.6753 | 35.1932 | 39.9326
4141 | 42.7863 | 34.6023 | 42.5614
4142 | 41.2826 | 32.5974 | 44.5019
4143 | 43.2367 | 36.1196 | 43.5
4144 | 43.7126 | 33.3771 | 45.587
4145 | 43.2384 | 34.9164 | 45.3203
4146 | 41.3276 | 34.5505 | 42.5169
4147 | 41.0528 | 36.2138 | 44.9374
4148 | 46.2852 | 35.399 | 43.0327
4149 | 46.0145 | 34.5604 | 42.3851
4150 | 44.0583 | 35.6256 | 44.5813
4151 | 42.939 | 34.6265 | 41.8734
4152 | 42.1846 | 31.6391 | 44.9202
4153 | 43.0404 | 35.0752 | 45.3141
4154 | 44.9869 | 32.6009 | 43.1977
4155 | 42.9909 | 35.1525 | 44.4786
4156 | 44.6249 | 33.0656 | 40.7518
4157 | 39.735 | 34.6106 | 43.2382
4158 | 44.802 | 32.0012 | 45.0893
4159 | 44.1891 | 33.1 | 42.7436
4160 | 41.4408 | 34.9817 | 42.769
4161 | 42.8085 | 36.7678 | 42.3107
4162 | 42.0754 | 35.4114 | 44.6046
4163 | 44.1099 | 34.0303 | 44.6719
4164 | 44.3432 | 33.9202 | 43.0507
4165 | 42.0659 | 33.6784 | 42.6406
4166 | 44.8766 | 34.0863 | 43.5602
4167 | 41.411 | 32.4594 | 45.9071
4168 | 41.1595 | 35.9169 | 45.3283
4169 | 44.7546 | 32.6739 | 43.326
4170 | 45.6337 | 36.8251 | 42.799
4171 | 42.1153 | 34.1927 | 41.0979
4172 | 42.8707 | 35.3103 | 41.4421
4173 | 43.458 | 33.8233 | 41.3252
4174 | 44.2016 | 35.9782 | 43.2212
4175 | 41.9143 | 34.9272 | 45.9334
4176 | 42.6947 | 35.9759 | 42.7327
4177 | 43.2895 | 34.8842 | 42.7756
4178 | 44.7379 | 34.8919 | 44.2396
4179 | 43.9317 | 35.4036 | 41.7919
4180 | 45.2211 | 34.6684 | 44.9403
4181 | 43.7872 | 34.5499 | 43.5669
4182 | 41.6455 | 34.9561 | 43.5274
4183 | 44.3516 | 33.4042 | 43.9817
4184 | 41.9469 | 35.3711 | 41.4485
4185 | 44.0041 | 31.6786 | 41.7542
4186 | 40.6019 | 32.665 | 41.6444
4187 | 43.9061 | 36.0538 | 45.1748
4188 | 41.9216 | 35.0723 | 44.1122
4189 | 45.2243 | 34.1128 | 44.4532
4190 | 45.6874 | 36.045 | 45.1066
4191 | 45.1702 | 33.5983 | 43.5346
4192 | 43.0193 | 35.232 | 39.7583
4193 | 43.669 | 34.4151 | 44.6486
4194 | 43.307 | 32.4908 | 44.6133
4195 | 43.2379 | 34.974 | 41.1059
4196 | 43.2972 | 35.4491 | 43.5423
4197 | 43.17 | 33.8849 | 43.8715
4198 | 44.8544 | 34.1352 | 42.1177
4199 | 43.1421 | 33.6339 | 41.6373
4200 | 41.8231 | 34.3053 | 42.1421
4201 | 42.5442 | 33.3446 | 42.8372
4202 | 46.8191 | 35.4311 | 41.9227
4203 | 42.1541 | 34.6305 | 43.7241
4204 | 42.1505 | 32.3095 | 42.7924
4205 | 43.9371 | 34.273 | 41.8574
4206 | 41.0536 | 34.8496 | 41.3573
4207 | 44.849 | 34.6428 | 44.633
4208 | 42.1791 | 34.6641 | 43.1578
4209 | 45.0389 | 35.2762 | 44.4022
4210 | 43.174 | 33.9306 | 44.6041
4211 | 46.1907 | 34.8593 | 44.9698
4212 | 42.8625 | 34.396 | 45.6212
4213 | 42.7971 | 35.6249 | 42.5808
4214 | 42.5392 | 32.5755 | 40.7386
4215 | 43.5 | 33.5897 | 44.0085
4216 | 41.6258 | 34.4515 | 39.6919
4217 | 41.3917 | 35.1645 | 45.296
4218 | 40.8093 | 33.0314 | 41.6602
4219 | 41.2652 | 33.0166 | 41.7251
4220 | 41.449 | 35.238 | 40.5343
4221 | 44.0411 | 33.3213 | 45.8526
4222 | 40.7865 | 32.84 | 44.9276
4223 | 42.0572 | 33.5902 | 45.5287
4224 | 44.7964 | 34.0435 | 42.4633
4225 | 42.5653 | 35.4757 | 44.7574
4226 | 41.9676 | 34.0097 | 43.3866
4227 | 45.7796 | 35.1085 | 41.2225
4228 | 44.4836 | 33.4629 | 42.6592
4229 | 40.8619 | 35.185 | 41.8269
4230 | 45.8362 | 35.6033 | 41.9696
4231 | 42.3983 | 34.6505 | 42.5364
4232 | 39.4022 | 33.4899 | 42.0321
4233 | 43.6814 | 33.38 | 43.059
4234 | 41.6843 | 34.9268 | 45.1948
4235 | 44.2597 | 35.6704 | 43.0775
4236 | 45.2322 | 35.8282 | 42.3571
4237 | 41.4272 | 34.2302 | 42.4381
4238 | 42.9596 | 33.6956 | 42.5606
4239 | 42.9725 | 33.2138 | 42.5465
4240 | 43.9653 | 35.329 | 44.3277
4241 | 43.4437 | 33.6558 | 44.5647
4242 | 42.3963 | 31.7627 | 42.5877
4243 | 44.9881 | 34.2298 | 43.0465
4244 | 44.786 | 35.4265 | 44.4879
4245 | 44.5902 | 35.4633 | 43.6251
4246 | 44.0946 | 34.6407 | 42.7659
4247 | 40.5403 | 34.6639 | 40.5467
4248 | 44.804 | 34.5518 | 43.2312
4249 | 45.5473 | 36.5106 | 43.4112
4250 | 43.8075 | 33.5309 | 43.0741
4251 | 42.3618 | 34.2751 | 45.5161
4252 | 46.4347 | 35.0908 | 42.0588
4253 | 45.4108 | 34.9184 | 45.3718
4254 | 41.3697 | 34.8314 | 41.7767
4255 | 42.4564 | 34.3376 | 42.2406
4256 | 44.4092 | 34.3899 | 44.3083
4257 | 44.1606 | 33.2155 | 42.8504
4258 | 43.1455 | 33.6104 | 41.9623
4259 | 42.8179 | 34.1468 | 44.114
4260 | 42.8351 | 36.3601 | 43.735
4261 | 41.1615 | 34.4319 | 43.4934
4262 | 42.3035 | 34.4205 | 42.2941
4263 | 42.6746 | 33.1885 | 41.3128
4264 | 43.0521 | 35.5373 | 45.3923
4265 | 40.7022 | 33.5898 | 45.1908
4266 | 40.0303 | 35.2382 | 46.1995
4267 | 42.6317 | 34.1221 | 43.271
4268 | 43.275 | 35.3492 | 39.9203
4269 | 44.33 | 33.8147 | 42.4666
4270 | 43.544 | 34.3562 | 43.4157
4271 | 41.9557 | 34.006 | 42.6602
4272 | 42.8465 | 33.2922 | 40.3624
4273 | 44.8842 | 33.9621 | 44.0497
4274 | 41.8059 | 34.3543 | 42.4408
4275 | 42.0289 | 33.6728 | 42.0444
4276 | 44.3335 | 34.1044 | 47.7496
4277 | 44.426 | 32.0595 | 42.016
4278 | 39.9335 | 36.7799 | 41.378
4279 | 46.1617 | 34.0218 | 44.4209
4280 | 42.9128 | 35.4019 | 43.9043
4281 | 43.4922 | 33.2666 | 44.6667
4282 | 42.3315 | 36.0088 | 43.6559
4283 | 44.0328 | 33.627 | 43.5748
4284 | 43.3496 | 35.1586 | 45.4923
4285 | 44.0146 | 36.5219 | 45.1599
4286 | 43.5036 | 34.9594 | 42.7749
4287 | 44.0679 | 33.8867 | 43.2921
4288 | 45.2986 | 34.128 | 42.3983
4289 | 44.9592 | 35.8652 | 44.2404
4290 | 44.5523 | 34.5769 | 41.9025
4291 | 43.1529 | 37.164 | 42.6536
4292 | 41.7028 | 34.4112 | 43.497
4293 | 46.9517 | 37.0439 | 43.4813
4294 | 41.7489 | 34.1302 | 42.5317
4295 | 41.4475 | 34.0445 | 43.1816
4296 | 44.4019 | 34.4678 | 41.9876
4297 | 39.7818 | 33.2647 | 46.2912
4298 | 45.215 | 34.2151 | 42.492
4299 | 45.0083 | 35.5226 | 42.4051
4300 | 40.1553 | 33.7702 | 43.2213
4301 | 43.107 | 35.3549 | 43.1346
4302 | 43.0003 | 34.7671 | 44.1634
4303 | 41.2794 | 34.2038 | 44.2316
4304 | 41.9602 | 35.1388 | 41.2524
4305 | 44.8084 | 35.2126 | 43.3922
4306 | 41.3187 | 32.4533 | 43.442
4307 | 43.524 | 35.6242 | 44.7051
4308 | 43.7443 | 32.4163 | 44.0721
4309 | 44.2142 | 31.4338 | 44.3913
4310 | 42.8497 | 34.2605 | 42.5022
4311 | 44.6105 | 34.1809 | 44.5138
4312 | 43.1532 | 33.3462 | 43.2253
4313 | 43.8489 | 35.781 | 42.2045
4314 | 39.5241 | 34.9257 | 43.4941
4315 | 43.1764 | 33.3985 | 43.8079
4316 | 44.822 | 31.9895 | 45.0869
4317 | 40.8987 | 32.7917 | 45.6141
4318 | 44.9347 | 37.0917 | 42.3178
4319 | 44.0832 | 32.557 | 45.9453
4320 | 44.2408 | 34.2861 | 46.2685
4321 | 43.4401 | 37.1998 | 42.1581
4322 | 44.4622 | 34.1563 | 44.9238
4323 | 43.8211 | 32.5363 | 44.5687
4324 | 43.761 | 34.9161 | 41.2478
4325 | 40.512 | 34.8169 | 44.0211
4326 | 43.5953 | 35.986 | 44.8574
4327 | 42.2496 | 33.8067 | 43.085
4328 | 43.2097 | 34.3895 | 41.2669
4329 | 42.1607 | 34.6202 | 45.7944
4330 | 43.1669 | 34.7567 | 43.9045
4331 | 43.9009 | 35.7394 | 43.6751
4332 | 42.4461 | 36.8391 | 44.4224
4333 | 42.3869 | 34.7818 | 39.5907
4334 | 41.421 | 33.0847 | 43.3127
4335 | 42.8401 | 35.0243 | 43.2875
4336 | 42.5973 | 34.3209 | 42.5236
4337 | 41.5593 | 32.9579 | 41.9299
4338 | 42.6157 | 32.9314 | 45.3912
4339 | 44.8892 | 36.5866 | 41.9047
4340 | 46.3948 | 36.3872 | 41.0274
4341 | 41.6264 | 33.8785 | 43.928
4342 | 43.0065 | 32.9321 | 44.4484
4343 | 46.978 | 36.4894 | 45.7204
4344 | 43.6532 | 33.5908 | 43.6284
4345 | 43.7299 | 34.0446 | 40.7792
4346 | 42.1874 | 35.8386 | 42.5976
4347 | 44.3168 | 33.9758 | 45.3881
4348 | 44.3572 | 35.1829 | 44.889
4349 | 42.4412 | 32.7879 | 41.8209
4350 | 44.4028 | 34.4727 | 42.4615
4351 | 43.0036 | 34.1083 | 44.3065
4352 | 43.737 | 33.1916 | 45.108
4353 | 46.0622 | 33.7239 | 42.0963
4354 | 43.6045 | 35.3335 | 39.4196
4355 | 41.2002 | 35.2589 | 42.4064
4356 | 43.8616 | 35.3751 | 42.3153
4357 | 43.5365 | 33.9454 | 44.3037
4358 | 42.8923 | 35.1555 | 43.2456
4359 | 41.9859 | 32.6963 | 44.2508
4360 | 41.892 | 34.5061 | 41.8912
4361 | 43.145 | 33.7609 | 44.5371
4362 | 43.5457 | 35.0487 | 42.4463
4363 | 41.8351 | 36.2145 | 42.1586
4364 | 43.6519 | 35.6897 | 43.8082
4365 | 43.5813 | 33.3171 | 43.1847
4366 | 42.1934 | 34.7747 | 45.5508
4367 | 41.7545 | 34.6709 | 43.7156
4368 | 41.704 | 34.1176 | 45.8688
4369 | 42.1755 | 33.9533 | 43.4688
4370 | 42.1687 | 32.0976 | 42.9956
4371 | 43.7378 | 34.8467 | 42.2863
4372 | 43.8329 | 35.4763 | 42.9314
4373 | 43.5347 | 35.5594 | 43.0949
4374 | 41.9734 | 34.8296 | 43.9885
4375 | 42.1264 | 33.713 | 43.9107
4376 | 42.8413 | 32.7947 | 42.9919
4377 | 42.4093 | 34.64 | 42.3665
4378 | 45.3681 | 35.3497 | 44.6899
4379 | 42.5429 | 34.1668 | 41.419
4380 | 44.553 | 35.9429 | 42.4351
4381 | 43.8246 | 33.169 | 43.0561
4382 | 42.846 | 33.8843 | 43.6354
4383 | 44.2279 | 34.5398 | 43.1623
4384 | 42.6927 | 31.4955 | 43.7934
4385 | 43.1568 | 34.1095 | 41.9561
4386 | 43.1189 | 35.6138 | 42.2748
4387 | 45.7236 | 32.846 | 42.5223
4388 | 43.6669 | 35.1681 | 43.3746
4389 | 44.5411 | 33.4047 | 43.1094
4390 | 43.7237 | 35.2824 | 43.3176
4391 | 43.6185 | 34.9538 | 43.936
4392 | 41.7924 | 32.9265 | 44.729
4393 | 44.3695 | 32.9602 | 42.3147
4394 | 43.7697 | 35.2565 | 44.8054
4395 | 46.2192 | 32.7764 | 44.6065
4396 | 45.659 | 33.4517 | 43.3415
4397 | 44.6691 | 35.1965 | 41.8059
4398 | 44.8264 | 33.0848 | 44.0693
4399 | 43.5443 | 33.5315 | 42.7599
4400 | 45.0165 | 30.5151 | 45.7937
4401 | 43.7763 | 34.5719 | 41.4266
4402 | 43.9835 | 35.062 | 44.4193
4403 | 44.4407 | 36.9566 | 41.3092
4404 | 42.5994 | 35.3599 | 43.0435
4405 | 44.6254 | 33.8199 | 41.994
4406 | 39.567 | 34.2404 | 42.9441
4407 | 44.5508 | 34.3348 | 43.1507
4408 | 45.8946 | 33.5169 | 43.8569
4409 | 42.5281 | 35.9089 | 41.5994
4410 | 46.155 | 33.2086 | 42.2116
4411 | 39.6442 | 33.836 | 45.7819
4412 | 40.1623 | 33.9825 | 43.1584
4413 | 42.6022 | 34.0713 | 42.8401
4414 | 43.7584 | 32.5861 | 41.2451
4415 | 43.0482 | 35.3497 | 41.7076
4416 | 43.7277 | 31.2366 | 42.9621
4417 | 41.7409 | 35.3486 | 43.8324
4418 | 40.2896 | 33.5692 | 42.9717
4419 | 42.4976 | 33.1758 | 42.0704
4420 | 44.5394 | 35.284 | 43.5923
4421 | 43.886 | 33.7684 | 41.6897
4422 | 43.5497 | 32.9342 | 43.7159
4423 | 42.3153 | 34.0954 | 41.234
4424 | 44.3068 | 34.3097 | 41.112
4425 | 40.2819 | 34.7771 | 42.2436
4426 | 44.4401 | 34.5702 | 42.4081
4427 | 44.0052 | 35.9109 | 45.0413
4428 | 45.5107 | 33.6771 | 40.5362
4429 | 46.4695 | 32.5135 | 43.6822
4430 | 41.3798 | 34.7272 | 40.8483
4431 | 43.9785 | 33.5694 | 41.8109
4432 | 40.8988 | 32.9591 | 42.6126
4433 | 42.273 | 32.6051 | 44.5428
4434 | 46.0051 | 35.2261 | 45.4343
4435 | 42.0299 | 35.5017 | 44.5667
4436 | 44.6425 | 35.7155 | 42.942
4437 | 45.3875 | 33.323 | 44.3861
4438 | 45.5871 | 32.5632 | 44.9527
4439 | 43.3336 | 32.8765 | 43.2534
4440 | 42.4667 | 33.1605 | 43.6813
4441 | 46.5492 | 37.7489 | 44.9835
4442 | 43.6979 | 33.0662 | 42.5172
4443 | 43.6553 | 35.3182 | 43.2034
4444 | 41.6573 | 33.8424 | 43.2913
4445 | 43.5127 | 36.0939 | 42.6108
4446 | 44.5169 | 33.8152 | 40.8197
4447 | 42.3606 | 33.8639 | 41.7086
4448 | 45.2567 | 35.6486 | 41.9402
4449 | 42.3001 | 33.1177 | 43.3654
4450 | 44.1305 | 33.8199 | 42.2224
4451 | 42.7574 | 34.1627 | 43.6147
4452 | 42.3632 | 34.5353 | 43.696
4453 | 42.84 | 34.9755 | 45.4765
4454 | 42.5112 | 35.3121 | 40.5676
4455 | 42.9587 | 33.9351 | 44.7584
4456 | 43.8259 | 33.3004 | 43.2916
4457 | 42.8896 | 33.9384 | 43.1369
4458 | 42.9855 | 32.234 | 46.237
4459 | 42.7998 | 34.4013 | 41.2457
4460 | 42.9389 | 34.9442 | 45.9344
4461 | 43.1569 | 34.2109 | 42.6046
4462 | 43.2532 | 35.6635 | 46.1999
4463 | 44.3518 | 34.4055 | 44.235
4464 | 42.5356 | 33.0266 | 42.8395
4465 | 44.7865 | 32.8668 | 42.5207
4466 | 44.8674 | 35.684 | 44.1152
4467 | 45.6242 | 34.1149 | 44.1071
4468 | 42.7116 | 33.5489 | 43.9192
4469 | 41.9878 | 33.87 | 45.4872
4470 | 44.7028 | 34.2341 | 42.759
4471 | 44.2346 | 34.4373 | 41.1912
4472 | 43.6242 | 32.9943 | 42.344
4473 | 44.4049 | 34.8475 | 43.216
4474 | 42.041 | 35.0718 | 42.8543
4475 | 41.1301 | 34.2984 | 41.6657
4476 | 43.2001 | 32.1998 | 39.7981
4477 | 41.1243 | 33.4447 | 40.286
4478 | 42.4496 | 33.3686 | 41.9886
4479 | 43.4292 | 34.967 | 42.3197
4480 | 40.5497 | 34.6133 | 42.5599
4481 | 45.7512 | 35.3889 | 45.8731
4482 | 46.3655 | 35.9336 | 44.6415
4483 | 42.9316 | 35.1448 | 43.7683
4484 | 43.7609 | 33.7974 | 43.2395
4485 | 44.7157 | 34.7238 | 41.7059
4486 | 45.5323 | 34.54 | 42.9975
4487 | 43.4167 | 33.0814 | 45.7027
4488 | 43.9772 | 36.0854 | 43.1077
4489 | 42.7104 | 34.7464 | 42.3855
4490 | 43.9286 | 33.118 | 40.4972
4491 | 42.4907 | 33.8976 | 40.9423
4492 | 43.5772 | 35.8826 | 43.0813
4493 | 40.6778 | 34.4725 | 44.2274
4494 | 45.3617 | 33.9075 | 42.8524
4495 | 40.3044 | 35.5062 | 41.861
4496 | 40.8764 | 36.4622 | 44.8941
4497 | 42.1171 | 35.672 | 42.1338
4498 | 43.0447 | 34.7599 | 41.8593
4499 | 44.7453 | 36.7433 | 44.2214
4500 | 43.913 | 33.6681 | 44.7887
4501 | 43.5491 | 32.9978 | 43.1147
4502 | 43.4608 | 32.486 | 42.8393
4503 | 41.061 | 36.7056 | 44.3087
4504 | 44.1734 | 34.8595 | 40.9138
4505 | 40.7024 | 34.6993 | 43.8269
4506 | 44.5756 | 34.9616 | 43.4512
4507 | 44.9134 | 33.0045 | 43.5017
4508 | 40.5374 | 33.9988 | 42.402
4509 | 42.9296 | 34.3071 | 44.9183
4510 | 41.4143 | 33.9869 | 41.6312
4511 | 43.598 | 33.8 | 43.4387
4512 | 40.9708 | 34.19 | 43.3275
4513 | 44.2091 | 34.5882 | 41.8434
4514 | 40.0276 | 33.5669 | 42.6029
4515 | 45.023 | 35.4818 | 44.5158
4516 | 40.8087 | 33.522 | 42.846
4517 | 43.8935 | 36.3159 | 40.3713
4518 | 42.6422 | 34.2219 | 45.5801
4519 | 42.4965 | 34.2568 | 41.9605
4520 | 43.6849 | 33.7896 | 44.6935
4521 | 40.9632 | 33.7751 | 41.9701
4522 | 43.4055 | 33.5266 | 41.8274
4523 | 43.562 | 35.8185 | 42.6935
4524 | 43.8869 | 34.2421 | 42.5352
4525 | 42.9987 | 36.784 | 43.4797
4526 | 41.7547 | 33.9656 | 44.352
4527 | 45.6097 | 32.7101 | 42.3577
4528 | 43.1813 | 34.9942 | 44.1563
4529 | 44.8622 | 33.1598 | 41.5926
4530 | 43.5412 | 35.0991 | 43.1366
4531 | 43.9238 | 32.9821 | 40.1102
4532 | 46.253 | 34.4987 | 43.4445
4533 | 40.4565 | 33.6797 | 43.7572
4534 | 41.9907 | 33.7231 | 43.3654
4535 | 46.0286 | 33.4022 | 41.8818
4536 | 43.815 | 33.2166 | 43.5143
4537 | 42.8726 | 35.6485 | 41.7657
4538 | 41.3309 | 35.1958 | 40.7667
4539 | 43.6803 | 35.9406 | 43.0974
4540 | 47.1157 | 33.9858 | 44.0616
4541 | 46.1292 | 33.9179 | 44.83
4542 | 44.8283 | 36.163 | 46.2168
4543 | 41.3646 | 35.7508 | 44.5666
4544 | 43.059 | 34.116 | 44.3901
4545 | 42.4092 | 34.1713 | 43.0209
4546 | 41.6384 | 33.6329 | 42.3745
4547 | 41.839 | 35.3245 | 43.0549
4548 | 45.2758 | 35.4803 | 44.0724
4549 | 40.9284 | 34.8874 | 42.9612
4550 | 44.2019 | 34.2278 | 46.2849
4551 | 41.9386 | 33.6666 | 44.8485
4552 | 43.0201 | 36.6412 | 45.4358
4553 | 42.0326 | 32.837 | 44.3426
4554 | 42.3722 | 35.5954 | 42.8682
4555 | 44.4624 | 35.5953 | 41.1483
4556 | 41.2966 | 35.1563 | 45.2848
4557 | 44.6512 | 33.4299 | 42.5312
4558 | 44.1124 | 34.3857 | 42.24
4559 | 39.5809 | 34.5266 | 43.6166
4560 | 41.9517 | 32.7396 | 43.2854
4561 | 43.6997 | 34.2351 | 43.8169
4562 | 41.1404 | 35.9475 | 42.1077
4563 | 41.8185 | 33.1309 | 44.6693
4564 | 43.351 | 33.1922 | 43.7272
4565 | 40.9613 | 33.3785 | 41.1405
4566 | 42.836 | 33.2218 | 44.8187
4567 | 42.1439 | 34.7966 | 42.9899
4568 | 42.9325 | 32.2068 | 40.6653
4569 | 41.9696 | 31.945 | 43.2752
4570 | 42.4511 | 33.6857 | 39.8874
4571 | 41.898 | 33.0237 | 40.962
4572 | 46.1814 | 33.2728 | 41.4879
4573 | 43.5373 | 33.3876 | 44.2674
4574 | 43.5289 | 33.4116 | 43.529
4575 | 46.3793 | 33.5401 | 42.6027
4576 | 41.0946 | 36.5794 | 40.7003
4577 | 42.5835 | 33.1439 | 43.1323
4578 | 44.7921 | 34.1818 | 42.6734
4579 | 42.06 | 34.6632 | 45.0404
4580 | 43.336 | 35.6512 | 43.1358
4581 | 41.2349 | 35.6647 | 42.1122
4582 | 44.8406 | 33.4185 | 43.7382
4583 | 42.2334 | 33.3222 | 42.1863
4584 | 44.3718 | 38.0373 | 43.5432
4585 | 43.0851 | 33.385 | 45.8994
4586 | 45.7858 | 35.1809 | 45.3397
4587 | 45.4588 | 34.3043 | 43.1695
4588 | 42.1331 | 35.9978 | 45.4196
4589 | 44.0246 | 34.1504 | 43.8399
4590 | 43.6649 | 35.3016 | 42.2467
4591 | 42.1491 | 32.4189 | 42.215
4592 | 47.9715 | 33.5072 | 43.9953
4593 | 44.319 | 35.4156 | 42.6077
4594 | 41.6695 | 34.1928 | 44.299
4595 | 43.6875 | 34.7231 | 41.8633
4596 | 43.9143 | 35.7027 | 43.8268
4597 | 42.1023 | 32.1919 | 42.4942
4598 | 43.7969 | 32.7237 | 44.7538
4599 | 44.5339 | 34.0552 | 44.9325
4600 | 44.0825 | 35.575 | 45.0003
4601 | 41.5813 | 33.8752 | 42.807
4602 | 45.4881 | 35.7813 | 42.9289
4603 | 45.3282 | 32.8203 | 43.6621
4604 | 43.8996 | 35.598 | 42.5998
4605 | 44.5788 | 33.6148 | 45.5059
4606 | 45.2723 | 35.1917 | 42.073
4607 | 44.2337 | 34.1081 | 42.8592
4608 | 44.6464 | 31.4052 | 43.1863
4609 | 45.3107 | 35.0287 | 43.0044
4610 | 44.595 | 34.1885 | 40.821
4611 | 44.8205 | 34.9377 | 42.0567
4612 | 43.811 | 36.1976 | 43.7072
4613 | 42.5586 | 35.4639 | 43.0893
4614 | 44.9639 | 35.0985 | 42.003
4615 | 43.8531 | 33.2435 | 40.9805
4616 | 45.0071 | 33.8694 | 43.7683
4617 | 44.4048 | 34.833 | 44.089
4618 | 43.7416 | 35.6157 | 46.1235
4619 | 40.7703 | 35.4217 | 42.4474
4620 | 43.7862 | 32.9717 | 45.0704
4621 | 47.4263 | 35.2942 | 43.4103
4622 | 44.3235 | 35.922 | 42.8911
4623 | 43.7671 | 31.9529 | 44.1737
4624 | 43.1902 | 34.8605 | 41.9741
4625 | 45.6182 | 35.8835 | 44.0392
4626 | 44.0997 | 37.1858 | 41.343
4627 | 39.2799 | 35.4407 | 44.3173
4628 | 42.3797 | 32.1741 | 44.6601
4629 | 43.1036 | 33.1808 | 43.0825
4630 | 43.9529 | 37.0263 | 43.1258
4631 | 46.7251 | 33.2552 | 43.6423
4632 | 44.5814 | 34.2966 | 42.9041
4633 | 42.3714 | 32.7102 | 44.4744
4634 | 45.4865 | 35.7404 | 44.8193
4635 | 42.8315 | 35.4094 | 42.9779
4636 | 42.1757 | 32.2622 | 45.7205
4637 | 41.8431 | 32.4022 | 43.8284
4638 | 45.6621 | 37.0209 | 42.3289
4639 | 42.9675 | 33.0693 | 41.737
4640 | 42.3234 | 34.4836 | 42.5124
4641 | 41.9064 | 34.6349 | 41.8497
4642 | 43.7106 | 33.8504 | 43.928
4643 | 40.386 | 34.7689 | 42.7552
4644 | 45.0037 | 34.5296 | 42.8882
4645 | 42.8635 | 33.2916 | 45.0315
4646 | 43.3691 | 35.282 | 44.6598
4647 | 43.5347 | 35.0795 | 43.2756
4648 | 41.1005 | 33.8686 | 44.0512
4649 | 40.9824 | 33.6428 | 42.274
4650 | 44.1073 | 33.6414 | 43.2382
4651 | 42.6808 | 33.8178 | 42.6416
4652 | 43.3347 | 34.3736 | 45.092
4653 | 43.1021 | 34.7763 | 42.1988
4654 | 42.8183 | 33.5084 | 42.5862
4655 | 46.0977 | 33.125 | 43.6598
4656 | 40.9022 | 34.2139 | 41.0335
4657 | 43.8297 | 35.34 | 45.9162
4658 | 42.1564 | 32.6993 | 42.7384
4659 | 42.2032 | 34.9742 | 40.9612
4660 | 43.0032 | 34.5931 | 42.0086
4661 | 43.9065 | 34.2948 | 42.9999
4662 | 45.0667 | 33.8893 | 40.6184
4663 | 43.0774 | 34.1149 | 45.0441
4664 | 41.3897 | 35.6707 | 42.5639
4665 | 44.5737 | 36.5023 | 39.7324
4666 | 40.5255 | 34.3812 | 41.6051
4667 | 43.4736 | 34.1807 | 45.4274
4668 | 43.188 | 35.808 | 47.0305
4669 | 42.9733 | 34.8066 | 44.2339
4670 | 46.5006 | 33.3184 | 44.2393
4671 | 42.7796 | 34.1612 | 42.4767
4672 | 43.2587 | 34.7221 | 42.395
4673 | 44.6912 | 35.7807 | 42.9748
4674 | 43.9695 | 34.4996 | 45.264
4675 | 38.6347 | 35.7664 | 43.1879
4676 | 45.2678 | 35.6204 | 44.2517
4677 | 41.6846 | 35.2651 | 42.6556
4678 | 43.5885 | 33.7768 | 45.8517
4679 | 43.4055 | 36.2199 | 44.8872
4680 | 41.5722 | 35.1229 | 45.8891
4681 | 42.2895 | 33.575 | 41.2043
4682 | 45.0528 | 34.3725 | 41.8319
4683 | 43.3485 | 33.9237 | 42.7731
4684 | 44.0417 | 33.7162 | 43.5787
4685 | 44.2108 | 35.5443 | 47.4941
4686 | 42.1756 | 34.992 | 41.593
4687 | 44.3187 | 33.1724 | 42.8084
4688 | 43.1487 | 32.8279 | 45.5146
4689 | 42.4353 | 34.4189 | 42.9673
4690 | 41.6066 | 35.3336 | 42.0889
4691 | 41.0206 | 35.0756 | 43.9932
4692 | 42.8277 | 35.2355 | 45.8304
4693 | 42.6413 | 34.0273 | 42.9918
4694 | 44.1323 | 33.549 | 43.2355
4695 | 45.2357 | 32.7152 | 45.3758
4696 | 43.5274 | 35.6573 | 44.0768
4697 | 42.3527 | 35.9076 | 43.5473
4698 | 43.7345 | 33.515 | 42.2112
4699 | 44.1348 | 32.7491 | 42.5161
4700 | 44.516 | 34.8269 | 42.6077
4701 | 42.065 | 34.0453 | 41.4134
4702 | 42.863 | 36.2382 | 43.4299
4703 | 44.0697 | 33.7905 | 44.7594
4704 | 41.848 | 33.3008 | 42.3093
4705 | 44.2227 | 35.0644 | 43.8355
4706 | 43.6632 | 32.8546 | 40.9702
4707 | 41.9564 | 35.2607 | 45.3038
4708 | 43.8373 | 33.3995 | 42.8118
4709 | 41.1153 | 33.4023 | 42.995
4710 | 41.6293 | 33.4852 | 44.9226
4711 | 42.3802 | 37.1884 | 40.3602
4712 | 42.2191 | 34.2718 | 42.9871
4713 | 41.3236 | 34.3685 | 44.1327
4714 | 43.0758 | 35.2652 | 39.0373
4715 | 43.3045 | 35.6619 | 42.5298
4716 | 44.5567 | 33.8047 | 41.4568
4717 | 42.1808 | 36.0439 | 42.5645
4718 | 44.7602 | 34.6085 | 42.088
4719 | 41.815 | 30.9464 | 42.6463
4720 | 43.4961 | 32.6816 | 43.8306
4721 | 43.6413 | 31.3971 | 44.5569
4722 | 45.0199 | 34.4125 | 42.4492
4723 | 40.286 | 33.3433 | 45.0095
4724 | 46.8329 | 33.4108 | 42.5488
4725 | 42.4231 | 33.0043 | 43.6636
4726 | 43.6505 | 34.475 | 44.0408
4727 | 41.6493 | 33.5932 | 42.3828
4728 | 43.5727 | 33.9456 | 43.2583
4729 | 42.7284 | 35.4366 | 46.0722
4730 | 43.9229 | 34.6238 | 46.4641
4731 | 42.3707 | 34.6718 | 42.2763
4732 | 42.9456 | 32.9808 | 45.9926
4733 | 44.287 | 34.2984 | 42.8821
4734 | 45.1127 | 34.1551 | 41.8924
4735 | 45.8084 | 33.0492 | 43.3228
4736 | 44.1422 | 33.5177 | 42.1619
4737 | 42.934 | 34.8598 | 44.8315
4738 | 42.5714 | 35.9688 | 44.6195
4739 | 42.5345 | 33.3865 | 42.012
4740 | 43.8225 | 35.4497 | 45.4111
4741 | 41.3624 | 34.0058 | 44.411
4742 | 42.2508 | 32.7818 | 44.0963
4743 | 45.0648 | 33.9545 | 43.5711
4744 | 44.1404 | 34.1925 | 42.7449
4745 | 42.773 | 36.2189 | 42.6326
4746 | 42.7875 | 34.0025 | 45.1789
4747 | 44.9199 | 35.6512 | 41.4953
4748 | 44.134 | 36.272 | 44.2864
4749 | 41.9514 | 35.5591 | 42.7736
4750 | 41.2988 | 34.9773 | 45.8442
4751 | 44.5207 | 31.9956 | 43.0176
4752 | 45.5923 | 32.5916 | 45.0082
4753 | 43.9649 | 33.4716 | 43.619
4754 | 42.8969 | 34.5406 | 41.9776
4755 | 42.889 | 35.6705 | 43.597
4756 | 42.9519 | 36.5378 | 43.051
4757 | 43.3838 | 35.429 | 41.071
4758 | 46.5794 | 35.4681 | 43.0989
4759 | 41.8623 | 34.5312 | 43.6668
4760 | 43.21 | 33.6981 | 42.577
4761 | 42.5433 | 35.0355 | 42.9465
4762 | 41.493 | 32.0632 | 43.4767
4763 | 43.9875 | 34.4942 | 43.2315
4764 | 43.6355 | 35.2133 | 43.1193
4765 | 42.5758 | 33.9024 | 43.1468
4766 | 42.6142 | 34.8183 | 43.1648
4767 | 42.5792 | 32.8391 | 42.2294
4768 | 41.278 | 33.3321 | 41.3922
4769 | 41.7775 | 34.9331 | 43.5595
4770 | 41.5224 | 34.625 | 42.7563
4771 | 43.9025 | 35.727 | 42.028
4772 | 43.7553 | 33.5619 | 42.5326
4773 | 40.7918 | 35.4421 | 41.6522
4774 | 44.9139 | 33.7646 | 41.9127
4775 | 43.5122 | 34.683 | 45.4267
4776 | 43.7669 | 33.5116 | 43.6377
4777 | 42.4298 | 34.6208 | 44.0566
4778 | 44.7524 | 35.4017 | 42.3264
4779 | 42.3815 | 33.6033 | 42.0102
4780 | 41.1592 | 32.268 | 42.1893
4781 | 43.5255 | 33.8632 | 42.2045
4782 | 42.796 | 34.155 | 44.4612
4783 | 43.0495 | 35.2395 | 42.5468
4784 | 42.9778 | 35.4619 | 42.1793
4785 | 44.8675 | 38.687 | 41.1676
4786 | 43.5363 | 34.4698 | 43.1622
4787 | 43.9663 | 35.2319 | 45.0234
4788 | 42.1737 | 34.5965 | 42.9904
4789 | 44.7488 | 35.1729 | 42.0259
4790 | 42.9733 | 34.499 | 43.4289
4791 | 41.9619 | 33.2245 | 42.3308
4792 | 45.4755 | 37.5094 | 43.4244
4793 | 43.8688 | 34.9542 | 45.7262
4794 | 42.9954 | 34.2166 | 44.2784
4795 | 43.3512 | 31.9668 | 41.1195
4796 | 41.9535 | 34.5702 | 45.2623
4797 | 42.76 | 32.7424 | 42.9392
4798 | 42.9415 | 31.5941 | 45.2866
4799 | 41.9024 | 35.2498 | 44.6382
4800 | 43.0041 | 34.3724 | 40.2782
4801 | 43.1508 | 33.1412 | 46.1093
4802 | 43.0476 | 33.8329 | 42.929
4803 | 41.7896 | 36.6699 | 43.8458
4804 | 43.668 | 35.5465 | 42.8014
4805 | 43.6534 | 31.5582 | 44.8539
4806 | 41.3248 | 33.184 | 43.6402
4807 | 39.6885 | 34.7918 | 43.8125
4808 | 40.195 | 33.0722 | 40.9928
4809 | 42.9338 | 34.2795 | 45.2998
4810 | 43.0545 | 36.1922 | 46.8994
4811 | 42.0075 | 32.094 | 43.2862
4812 | 41.6843 | 33.6081 | 42.5556
4813 | 43.4129 | 35.0681 | 45.0889
4814 | 42.8994 | 33.3621 | 42.4786
4815 | 40.8494 | 35.4003 | 43.4546
4816 | 46.3724 | 35.9848 | 43.3095
4817 | 42.6542 | 32.4898 | 44.4275
4818 | 43.3674 | 34.239 | 41.1704
4819 | 45.5425 | 31.5722 | 43.2542
4820 | 42.3672 | 35.5641 | 41.5289
4821 | 43.2322 | 32.8398 | 45.3486
4822 | 45.1412 | 34.895 | 43.1506
4823 | 47.543 | 34.871 | 43.2892
4824 | 44.4774 | 35.5651 | 43.1307
4825 | 43.734 | 33.9976 | 42.1768
4826 | 43.0828 | 34.3987 | 40.2569
4827 | 45.5513 | 35.33 | 44.1834
4828 | 43.1206 | 33.7839 | 44.9727
4829 | 43.6341 | 32.5734 | 43.2838
4830 | 42.3112 | 33.1095 | 44.2878
4831 | 43.3137 | 31.9684 | 42.9065
4832 | 42.8605 | 35.7233 | 42.9399
4833 | 42.8395 | 33.1858 | 44.0232
4834 | 43.5192 | 34.6247 | 43.4838
4835 | 44.3442 | 34.7191 | 43.0527
4836 | 44.3454 | 34.914 | 41.8276
4837 | 45.0038 | 32.8051 | 43.4973
4838 | 44.3219 | 31.9661 | 44.3126
4839 | 44.1935 | 34.1402 | 45.2633
4840 | 41.4044 | 33.0123 | 43.2217
4841 | 45.0593 | 34.2479 | 41.4344
4842 | 42.3198 | 34.7514 | 45.539
4843 | 42.0835 | 32.8224 | 42.3803
4844 | 44.9541 | 35.4785 | 43.0627
4845 | 41.8974 | 33.602 | 42.0527
4846 | 42.6649 | 35.6068 | 39.9844
4847 | 42.0091 | 34.6642 | 42.8918
4848 | 41.7856 | 34.1121 | 45.5734
4849 | 42.8673 | 33.8483 | 40.6441
4850 | 42.3972 | 36.1543 | 43.813
4851 | 41.8311 | 35.1421 | 43.7395
4852 | 43.8172 | 32.9371 | 44.1603
4853 | 44.5919 | 34.7404 | 43.4598
4854 | 43.9058 | 34.6088 | 46.1497
4855 | 44.7633 | 32.3934 | 44.6752
4856 | 43.2187 | 35.4109 | 43.8638
4857 | 40.2216 | 32.6821 | 43.4659
4858 | 42.6719 | 33.7244 | 43.5339
4859 | 43.7696 | 34.8329 | 43.4783
4860 | 44.8116 | 34.4814 | 43.8043
4861 | 42.0279 | 34.7721 | 42.7125
4862 | 43.9958 | 36.3278 | 45.1379
4863 | 44.6115 | 34.663 | 44.6847
4864 | 44.9302 | 35.3102 | 39.7433
4865 | 42.8456 | 35.2607 | 39.0071
4866 | 42.981 | 34.215 | 44.5751
4867 | 44.2601 | 35.5263 | 42.3704
4868 | 43.3177 | 35.0625 | 44.1263
4869 | 44.1208 | 35.4569 | 43.3496
4870 | 42.1361 | 32.3599 | 42.7231
4871 | 43.063 | 32.9068 | 45.6649
4872 | 43.2409 | 34.2696 | 44.0075
4873 | 46.7894 | 34.616 | 43.8945
4874 | 43.4051 | 34.8095 | 42.1725
4875 | 45.2626 | 36.0542 | 44.8081
4876 | 44.821 | 34.1698 | 42.5285
4877 | 45.3558 | 34.4545 | 42.8927
4878 | 43.7821 | 35.991 | 43.527
4879 | 43.541 | 35.4096 | 39.9353
4880 | 43.4965 | 36.0648 | 45.5264
4881 | 42.9372 | 35.8844 | 42.9844
4882 | 41.2837 | 34.1732 | 41.8601
4883 | 44.589 | 34.3923 | 40.6867
4884 | 41.8283 | 36.8342 | 42.8792
4885 | 44.2638 | 36.7298 | 41.7588
4886 | 41.4511 | 34.0985 | 42.109
4887 | 44.625 | 33.4266 | 44.1269
4888 | 44.0741 | 34.7466 | 40.5452
4889 | 44.1692 | 34.617 | 43.7266
4890 | 39.6598 | 34.806 | 42.4837
4891 | 40.028 | 35.4091 | 45.6781
4892 | 42.307 | 33.9781 | 46.4526
4893 | 42.9674 | 35.0331 | 43.1018
4894 | 41.3293 | 32.4039 | 42.2455
4895 | 47.4743 | 35.6653 | 46.8946
4896 | 42.6633 | 34.3706 | 43.3834
4897 | 40.5403 | 34.6871 | 44.5942
4898 | 43.2494 | 34.6281 | 43.2834
4899 | 41.6589 | 36.3714 | 43.2534
4900 | 42.1343 | 35.6021 | 43.996
4901 | 42.1126 | 35.6181 | 44.9065
4902 | 45.3108 | 34.5471 | 44.0072
4903 | 43.918 | 31.8427 | 44.0372
4904 | 43.0386 | 35.3974 | 42.1233
4905 | 43.884 | 33.5799 | 43.3236
4906 | 41.3674 | 32.469 | 40.3603
4907 | 43.0906 | 34.2262 | 41.1773
4908 | 45.4085 | 31.9326 | 42.092
4909 | 43.5034 | 34.2207 | 42.3743
4910 | 44.5142 | 34.1217 | 41.5196
4911 | 43.2064 | 35.6488 | 45.2807
4912 | 42.2642 | 33.1933 | 43.408
4913 | 41.5545 | 35.4211 | 44.265
4914 | 43.169 | 33.8306 | 44.5869
4915 | 45.9176 | 34.2648 | 41.851
4916 | 42.7835 | 36.7433 | 44.7661
4917 | 41.9639 | 35.0782 | 40.0973
4918 | 44.3782 | 34.1272 | 43.3433
4919 | 43.9623 | 34.0815 | 41.7822
4920 | 45.3117 | 34.3672 | 44.5349
4921 | 43.8975 | 35.7726 | 43.4245
4922 | 42.8412 | 33.0716 | 41.9025
4923 | 41.8505 | 32.6084 | 42.8336
4924 | 41.8322 | 34.9471 | 43.2938
4925 | 42.9724 | 33.3023 | 43.7352
4926 | 43.1283 | 35.2642 | 44.1398
4927 | 45.5131 | 34.9784 | 44.0123
4928 | 45.9637 | 34.463 | 43.6167
4929 | 42.1887 | 34.4305 | 45.2861
4930 | 44.7509 | 31.1534 | 44.9189
4931 | 42.3584 | 36.4378 | 44.8039
4932 | 44.907 | 34.9884 | 41.8341
4933 | 45.6834 | 34.7648 | 41.2641
4934 | 43.3541 | 33.2221 | 43.6997
4935 | 41.3065 | 35.4999 | 44.4978
4936 | 44.8045 | 35.5728 | 40.89
4937 | 41.5374 | 34.3409 | 44.6424
4938 | 41.2316 | 32.9278 | 44.2709
4939 | 42.6454 | 36.058 | 43.9316
4940 | 44.2806 | 32.3006 | 40.9431
4941 | 42.3812 | 35.4665 | 42.4455
4942 | 42.2507 | 35.55 | 43.6435
4943 | 43.2648 | 33.3067 | 44.3395
4944 | 43.3055 | 33.6123 | 43.9554
4945 | 43.7438 | 35.4178 | 44.9523
4946 | 43.982 | 35.7927 | 44.3605
4947 | 43.6239 | 33.3488 | 45.2305
4948 | 42.8083 | 35.631 | 46.3847
4949 | 44.5659 | 33.8526 | 41.716
4950 | 43.2948 | 35.0258 | 42.3187
4951 | 42.7489 | 34.3121 | 45.3195
4952 | 43.0044 | 35.3376 | 42.7325
4953 | 42.9044 | 33.0887 | 42.4748
4954 | 42.7574 | 35.5666 | 43.1684
4955 | 42.8779 | 35.2069 | 42.5675
4956 | 42.1409 | 32.0214 | 43.9006
4957 | 40.6887 | 35.1614 | 40.5633
4958 | 45.3953 | 35.75 | 42.0499
4959 | 44.4134 | 35.1331 | 41.942
4960 | 44.2659 | 34.7797 | 40.9601
4961 | 45.6354 | 34.3202 | 42.5583
4962 | 45.9379 | 34.4569 | 44.0329
4963 | 43.8974 | 32.3094 | 41.7126
4964 | 45.9487 | 35.1525 | 42.697
4965 | 44.6794 | 34.4114 | 44.5358
4966 | 43.8717 | 32.6886 | 40.5565
4967 | 41.8993 | 36.1137 | 43.4773
4968 | 43.4244 | 32.9635 | 42.7734
4969 | 41.8688 | 36.4887 | 45.0634
4970 | 45.5321 | 35.535 | 42.8272
4971 | 44.6585 | 32.5918 | 45.6204
4972 | 42.4483 | 32.5865 | 42.6727
4973 | 43.6747 | 34.8028 | 43.4557
4974 | 44.023 | 34.6855 | 45.9064
4975 | 43.5486 | 36.1239 | 48.6073
4976 | 41.9018 | 33.871 | 41.5971
4977 | 44.6939 | 35.6334 | 44.4991
4978 | 42.5791 | 35.2549 | 42.1233
4979 | 44.352 | 33.5895 | 41.1508
4980 | 45.2133 | 37.2025 | 41.6412
4981 | 44.5313 | 35.5408 | 43.9715
4982 | 45.1107 | 35.3648 | 43.3278
4983 | 43.0969 | 35.1514 | 43.2455
4984 | 43.16 | 33.5549 | 45.1887
4985 | 41.9043 | 32.3204 | 42.5359
4986 | 41.2479 | 32.8635 | 45.2564
4987 | 45.9584 | 32.7771 | 43.2529
4988 | 41.0008 | 33.5209 | 42.2002
4989 | 43.9584 | 32.6251 | 39.8162
4990 | 41.4514 | 32.6028 | 42.1414
4991 | 46.1248 | 34.8329 | 42.3733
4992 | 44.3343 | 34.002 | 40.6761
4993 | 43.5743 | 32.6123 | 44.3178
4994 | 41.9963 | 36.9439 | 41.7799
4995 | 45.1884 | 34.9485 | 41.4694
4996 | 42.1495 | 33.0654 | 44.5737
4997 | 45.0341 | 34.1244 | 46.8748
4998 | 40.581 | 35.0536 | 44.8447
4999 | 43.7199 | 33.3121 | 42.9089
5000 | 43.186 | 34.5838 | 43.668
MIN (SPREAD) | 37.8793 | 29.885 | 36.6241
MAX (SPREAD) | 49.1095 | 38.687 | 49.4257
SAMPLE SIZE (n) | 5000 | 5000 | 5000
MIN (HISTOGRAM PLOT) | 32.8793 | 24.885 | 31.6241
MAX (HISTOGRAM PLOT)) | 54.1095 | 43.687 | 54.4257
32.88
54.11

## WP
SUMMARY STATISTICS
| Sample Size (n) : | 5000
CENTRAL TENDENCIES
Mean | 43.3023 | Median | 43.2914
StErr | 0.021497
SPREAD
StDev: | 1.52
Max: | 49.1095 | Q(.75): | 44.3356
Min: | 37.8793 | Q(.25): | 42.2539
Range: | 11.2302 | IQ Range: | 2.0817
SHAPE
| Skewness | 0.0054447
| Kurtosis | -0.06159
QUARTILES, PERCENTILES, INTERVAL
| 90% Interval |  | 95% Interval
Q(.05): | 40.8437 | Q(.025): | 40.3543
Q(.95): | 45.856 | Q(.975): | 46.3065
Alpha (a): | 0.05 | Q(a/2): | 40.3543
% Interval: | 0.95 | Q(1-a/2): | 46.3065
PROBABILITIES
| REMAINING DURATION | 43.2658 | MONTHS
|  | OVERALL PROJECT SCHEDULE IMPACT UNCERTAINTY: | 23.33%
|  | PROBABILITY OF COMPLETING PER SCHEDULE : | 49.3%
|  | TIMELY COMPLETION PROBABILITY: | 12.22%
|  | ESTIMATED EARLY COMPLETION DATE : | 2020-10-25
|  | ESTIMATED LATEST COMPLETION DATE : | 2020-11-25
HISTOGRAM PLOT
Min: | 32.8793
Max: | 54.1095
N: | 5000
Bins | Count | Scaled | Cum
32.8793 | 0 | 0 | 0%
33.41 | 0 | 0 | 0%
33.9408 | 0 | 0 | 0%
34.4715 | 0 | 0 | 0%
35.0023 | 0 | 0 | 0%
35.533 | 0 | 0 | 0%
36.0638 | 0 | 0 | 0%
36.5946 | 0 | 0 | 0%
37.1253 | 0 | 0 | 0%
37.6561 | 0 | 0 | 0%
38.1868 | 3 | 0.0011305 | 0.06%
38.7176 | 10 | 0.0037682 | 0.26%
39.2483 | 5 | 0.0018841 | 0.36%
39.7791 | 24 | 0.0090437 | 0.84%
40.3098 | 76 | 0.028638 | 2.36%
40.8406 | 132 | 0.04974 | 5%
41.3714 | 268 | 0.10099 | 10.36%
41.9021 | 378 | 0.14244 | 17.92%
42.4329 | 534 | 0.20122 | 28.6%
42.9636 | 639 | 0.24079 | 41.38%
43.4944 | 669 | 0.25209 | 54.76%
44.0251 | 682 | 0.25699 | 68.4%
44.5559 | 537 | 0.20235 | 79.14%
45.0867 | 457 | 0.17221 | 88.28%
45.6174 | 252 | 0.094959 | 93.32%
46.1482 | 164 | 0.061799 | 96.6%
46.6789 | 113 | 0.042581 | 98.86%
47.2097 | 41 | 0.01545 | 99.68%
47.7404 | 10 | 0.0037682 | 99.88%
48.2712 | 4 | 0.0015073 | 99.96%
48.8019 | 1 | 0.00037682 | 99.98%
49.3327 | 1 | 0.00037682 | 100%
49.8635 | 0 | 0 | 100%
50.3942 | 0 | 0 | 100%
50.925 | 0 | 0 | 100%
51.4557 | 0 | 0 | 100%
51.9865 | 0 | 0 | 100%
52.5172 | 0 | 0 | 100%
53.048 | 0 | 0 | 100%
53.5787 | 0 | 0 | 100%
54.1095 | 0 | 0 | 100%
CONFIDENCE LEVEL
Q | Confidence level | Variance | Contingencies
0.05 | 40.8437 | -5.598% | -2.4221 | 43.2658
0.1 | 41.3456 | -4.438% | -1.9202 | 43.2658
0.15 | 41.7165 | -3.581% | -1.5493 | 43.2658
0.2 | 42.0071 | -2.909% | -1.2587 | 43.2658
0.25 | 42.2539 | -2.339% | -1.0119 | 43.2658
0.3 | 42.4999 | -1.77% | -0.76586 | 43.2658
0.35 | 42.71 | -1.285% | -0.55579 | 43.2658
0.4 | 42.9109 | -0.8203% | -0.3549 | 43.2658
0.45 | 43.0909 | -0.4042% | -0.1749 | 43.2658
0.5 | 43.2914 | 0.05916% | 0.025598 | 43.2658
0.55 | 43.5038 | 0.5501% | 0.23801 | 43.2658
0.6 | 43.6964 | 0.9953% | 0.43064 | 43.2658
0.65 | 43.8932 | 1.45% | 0.62747 | 43.2658
0.7 | 44.0945 | 1.915% | 0.82874 | 43.2658
0.75 | 44.3356 | 2.473% | 1.0699 | 43.2658
0.8 | 44.597 | 3.077% | 1.3313 | 43.2658
0.85 | 44.8835 | 3.739% | 1.6178 | 43.2658
0.9 | 45.2437 | 4.572% | 1.978 | 43.2658
0.95 | 45.856 | 5.987% | 2.5902 | 43.2658